## struct
resource | resource | resource | resource | resource | resource | resource | resource | resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
[12 empty] | step |  |  | Tier 1: Penos
[12 empty] | step |  |  | Tier 2: Basement 5
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 4
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 3
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 2
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Ground
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 2
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 3
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 4
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 5
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 6
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 7
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 8
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 9
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 10
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 11
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 12
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 13
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 14
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 15
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 16
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 17
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 18
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 19
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 20
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Roof
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Peno - Floor | (LATEST) Peno - Wall | (LATEST) Peno - Cast In | [9 empty] | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 1: Drains Stacks and Vents
[12 empty] | step |  |  | Tier 2: Basement 5
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 4
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 3
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 2
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Ground
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 2
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 3
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 4
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 5
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 6
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 7
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 8
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 9
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 10
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 11
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 12
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 13
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 14
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 15
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 16
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 17
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 18
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 19
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 20
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Roof
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Drains: Underslung - Sewer, Stormwater & Vent | (LATEST) Drains: Stack Riser - Sewer, Stormwater & Vent | (LATEST) Drains: Syphonic - Underslung | (LATEST) Drains: Syphonic - Stack Riser | (LATEST) Drains: Greasy Waste - Underslung, Stacks & Vents | (LATEST) Drains: Trade Waste - Underslung, Stacks & Vents | (LATEST) Drains: Pumpline - Underslung & Stacks | (LATEST) Pod Drain Connection (Prefab Bathroom or Laundry) |  |  |  |  | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 1: Rough in
[12 empty] | step |  |  | Tier 2: Basement 5
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 4
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 3
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 2
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Basement 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Ground
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 2
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 3
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 4
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 5
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 6
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 7
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 8
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 9
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 10
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 11
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 12
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 13
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 14
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 15
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 16
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 17
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 18
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 19
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2
[12 empty] | step |  |  | Tier 2: Level 20
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Main Run Rough In (Cold Water) | (LATEST) Main Run Rough In (Hot Water) | (LATEST) Main Run Rough In (Non Potable/Rainwater) | (LATEST) Main Run Rough In (Gas) | (LATEST) Rough In - CW Design Components | (LATEST) Rough In - RW Design Components | (LATEST) Rough In - Mains Water Meter Assembly | (LATEST) Rough In - Meter Install (Fitout) | (LATEST) Rough In - Meter Manifold Install | (LATEST) Rough In: Commercial (High & Low Level Rough In) Water Services | (LATEST) Rough In: Apartment Water Services (High & Low Level Rough In) | (LATEST) Pod Rough In Connection (Prefab Bathroom or Laundry) | folder-with-checklists |  |  | Tier 3: Pour 2