## struct
resource | resource | resource | resource | resource | resource | resource | resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
[11 empty] | step |  |  | Tier 1: Plant & Equiment Install
[11 empty] | step |  |  | Tier 2: Basement 5 Inground
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 5
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 4
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Level 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Roof
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Plant & Equipment Install - Hot Water Plant | (LATEST) Plant & Equipment Install - Cold Water Pumpset | (LATEST) Plant & Equipment Install - Sewer Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Pumpwell/s | (LATEST) Plant & Equipment Install - Stormwater Treatment System/Filter | (LATEST) Plant & Equipment Install - Rainwater Tank | (LATEST) Plant & Equipment Install - Water Storage Tank | (LATEST) Plant & Equipment Install - GIT | (LATEST) Plant & Equipment Install - Diversion Valve | (LATEST) Plant & Equipment Install - Rainwater Filtration System |  | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 1: Commmissioning
[11 empty] | step |  |  | Tier 2: Basement 5 Inground
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 5
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 4
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Basement 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Level 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2
[11 empty] | step |  |  | Tier 2: Roof
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 1
(LATEST) Comm/HO - TMV | (LATEST) Comm/HO - Tempering Valve | (LATEST) Comm/HO - Apartment Final Commissioning - Fixture Group | (LATEST) Comm/HO - Commercial Final Commissioning - Fixture Group | (LATEST) FINAL Commissioning - Hot Water Plant | (LATEST) FINAL Commissioning - Cold Water Pumpset | (LATEST) FINAL Commissioning - Sewer Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Pumpwell/s | (LATEST) FINAL Commissioning - Stormwater Treatment System/Filter | (LATEST) FINAL Commissioning - GIT | (LATEST) FINAL Commissioning - Diversion Valve | folder-with-checklists |  |  | Tier 3: Pour 2