## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 8147cfd3-8368-4f90-b48d-621fbfa03d77 |  | checklist | Kaizon report |  |  |  |  | Yes | Kaizon report | 05a924b1-371b-4e55-929d-3064f4d3da68
checkpoint-status | 9f767b83-4820-415f-947d-6943870cf827 |  | checkpoint | Needing to be fixed/ area of concern
checkpoint-status | 5c8175f9-a7ff-495f-b33c-255384d606f3 |  | checkpoint | Fixing issue
checkpoint-status | 37622b75-cd20-43af-874e-8a579d4f2236 |  | checkpoint | Fixed issue
checklist-sectioned | d09a2499-a8b2-4c8b-b28c-8b587f5c35c6 |  | checklist | Coreflex - Wall floor junction / detail Checklist. Grids: |  |  |  |  | Yes | Coreflex - Wall floor junction / detail Checklist. Grids: | 0fdff7e5-c8fa-45ff-9b09-2d48e7b0a954
checkpoint-group | 15469853-de91-4b07-9caf-97bb6c628bd9 |  | section | Substrate checks
checkpoint-status | a40db2b1-4584-4c5d-b386-a8271ee96d61 |  | checkpoint | Substrate is acceptable and as per specification
boolean | 409c5dfd-2164-53fc-93fc-10c11774c4e7 |  | tickbox | No standing water / ice
boolean | ce671157-432e-5364-905f-b75d6fbc72cb |  | tickbox | Substrate is smooth
boolean | ac4451b1-b3e3-50cb-8d8d-41db0ff38fe7 |  | tickbox | No debris
boolean | 23a6d5a6-e5c6-5f39-aa93-b2364e0dad40 |  | tickbox | Weather is suitable for application
checkpoint-group | aa8f3452-bfab-43de-8c75-25251409410d |  | section | Wall floor junction / detail
checkpoint-status | d5a7890d-cfba-407c-b53b-942ca91caa1f |  | checkpoint | Voltex DPC must be removed 100mm minimum for lapping
checkpoint-status | 48220d11-924e-4cda-a575-29bceeaf6c37 |  | checkpoint | Volclay nailed flat
checkpoint-status | 495f0854-6d09-4d02-9ce5-b1c7b468ca9e |  | checkpoint | Coreflex60 min 300mm lapped onto the floor
checkpoint-status | a2a5298c-7d1b-45ab-92a7-18e5de476ede |  | checkpoint | Coreflex to floor lap welded minimum of 100mm
checkpoint-status | 0b82f094-6bf3-4bfa-bab2-a9c2332ec0ab |  | checkpoint | Cetseal bead to secure flap
checkpoint-status | db3e03a9-59bd-43e9-b569-3c199ed18464 |  | checkpoint | Protected with volclay
checklist-flat | a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 |  | checklist | Document: |  |  |  |  | Yes | Document Attach | 1018e60e-a747-46de-99c4-c4c6ec21f254
checkpoint-status | 700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 |  | checkpoint | Document Attached
checklist-sectioned | c041575b-eb5c-46a7-961d-6b67e06d8a72 |  | checklist | Coreflex - Typical Butt End Assembly Checklist. Grids: |  |  |  |  | Yes | Coreflex - Typical Butt End Assembly Checklist. Grids: | 187acf16-c960-4a97-86d5-0bd39f5c9a5b
checkpoint-group | 75178027-9322-4bc4-8af3-73a911dba875 |  | section | Substrate checks
checkpoint-status | ab2e36b1-c34f-4de3-9e17-36294de666b1 |  | checkpoint | Substrate is acceptable and as per specification
boolean | 8672857e-0365-5fea-93f7-27bbc2268a3a |  | tickbox | No standing water / ice
boolean | ad3bf442-bf53-57aa-8b91-02b70a7beb26 |  | tickbox | Substrate is smooth
boolean | 69db9bd0-8a4d-5cd1-95bb-d4caf10f2ee5 |  | tickbox | No debris
boolean | 171105ed-88f8-5a54-ae35-261e0ed1357b |  | tickbox | Weather is suitable for application
checkpoint-group | a4b5b21b-9418-4b00-99c3-4b64dfbb39dd |  | section | Typical butt end assembly
checkpoint-status | b6e87a47-f30b-4897-a14c-f18be5d947b0 |  | checkpoint | Coreflash minimum 225mm strip
checkpoint-status | 7b448eee-f5cd-4252-83ca-9c795e7c5e8a |  | checkpoint | Cetseal bead to stick Coreflex 60 with APC core facing installer
checkpoint-status | 2a02f755-05cf-4257-8700-2f3d6bb1c3b9 |  | checkpoint | Coretex minimum 225mm strip
checkpoint-status | 1410fe03-69c7-42ea-b583-e2900d4d11f6 |  | checkpoint | Voltex over Coreflex (only on floor)
checklist-sectioned | 17e999d0-7605-4bae-859e-14d1fc8f57be |  | checklist | Coreflex - Daily Checklist. Date: |  |  |  |  | Yes | Coreflex - Daily Checklist. Date: | 18d525d6-5f78-425e-ab56-462eae24ed8c
checkpoint-group | 0c21501a-643c-4698-b425-74329e04c1d4 |  | section | Ongoing Site Management Checks
checkpoint-status | 7ad8029b-2d69-4984-a36f-5df4a8a37b09 |  | checkpoint | Site management has been advised to ensure all contractors working nearby are aware of slip hazard
checkpoint-status | b5f2feb9-9c4a-4881-a162-a7e0dc7bb075 |  | checkpoint | Site management has been advised not to lay/sit/locate anything material or tool wise on membrane AT ALL
checkpoint-status | 9b54e432-cf99-413e-9b53-c96407c788d0 |  | checkpoint | Site management has been informed that no hot-works/grinding to take place near any membrane
checkpoint-status | 477d3998-c21f-4641-8865-0aeae5659b99 |  | checkpoint | Site management has been informed not to compromise water control in anyway
checkpoint-group | 51d02ddb-bc43-4200-96a4-e2be73f7f73d |  | section | Ongoing Checks During Application
checkpoint-status | 78a985d2-980f-4548-bbe1-0c64d01fd0cb |  | checkpoint | Have an awareness of direction of application
checkpoint-status | 9bb3635e-fd4a-42db-8d9b-6f893f323e81 |  | checkpoint | Ensure any laps are clear from pooled water
checkpoint-status | 2e2212d7-6a8f-41b3-b12a-6a4ee2915059 |  | checkpoint | Ensure foot/machinery traffic doesn't compromise any laps
checkpoint-group | 5cfde511-127a-4690-9a10-91828aad31a2 |  | section | PREINSTALLATION CHECKS
checkpoint-status | 73956fb9-5002-4c3e-9b4f-533e634c4a46 |  | checkpoint | Ensure water control is in place and maintained 24/7 with an appointed person
checkpoint-status | fb5cf58f-34b5-4c7c-9f21-7fc13dbb4624 |  | checkpoint | No hot-works/grinding to be carried out in close proximity to membrane without supervision to ensure membrane damage isn’t incurred
checkpoint-status | 70af4c06-7c13-4cf7-97f7-5ddf681c482f |  | checkpoint | Water control in place 24/7 with an appointed person
checkpoint-status | 94048e12-3bc0-43ea-a324-a7194ac93a84 |  | checkpoint | Substrate is smooth (no sharp edge aggregate)
checkpoint-status | 45972660-f477-4051-9e61-8476d42af1b3 |  | checkpoint | Substrate is free of debris, pooled water or ice
checkpoint-status | 0262f8cb-848a-45de-8ef5-6a485c58507e |  | checkpoint | Weather is going to be suitable for install
checkpoint-status | 68039e3d-42e9-4a77-8a0b-55c63eb6202f |  | checkpoint | No stones larger than 19mm in substrate
checkpoint-status | 1be6a2f3-6291-4b0b-9463-7ae7ecaf7f38 |  | checkpoint | Suitable profile of mud slab
checkpoint-status | 146d3daa-cf00-4073-805d-98379347fef3 |  | checkpoint | Standing ice, water, snow and debris removed
checkpoint-status | 2cdc60ad-04b1-4fa7-be71-c35417ac3093 |  | checkpoint | Ensure substrate doesn’t deteriorate compromising existing membrane
checkpoint-status | c49b4314-97ce-4b30-94bd-2f7e683ebc1a |  | checkpoint | Debris is not to blow onto existing membrane (check surrounding environment)
checkpoint-group | 8031b692-0ba6-456a-9093-b9d308dc61a9 |  | section | TEST WELD SECTION
checkpoint-status | 9f08417e-e932-42a2-a996-4a5e427b8a3a |  | checkpoint | Test weld made to calibrate welding equipment in AM
text | 9191480b-0781-5bd6-b10a-a1ed0f01474c |  | textbox | Time of weld
text | 978f6118-8497-523d-a7ad-61645f893c68 |  | textbox | Ambient temp
text | 18d319ae-d40b-53b6-bd71-8c9b5421034b |  | textbox | Temperature of welder
checkpoint-status | bd8d5ebe-8c27-4f40-a366-acc308da43f6 |  | checkpoint | Test weld made to calibrate welding equipment in PM
text | f7df2d58-3301-5ce3-82b2-257fa134e67b |  | textbox | Time of weld
text | f0ede35d-764f-5e54-8aa1-6d17b93d5d20 |  | textbox | Ambient temp
text | 3a654687-52ed-5d53-958b-a75bc9910207 |  | textbox | Temperature of welder
checklist-flat | e9cb9ee1-fca6-43b8-9eed-47abc9ff9cff |  | checklist | Input Area & Date: |  |  |  |  | Yes | Daily Conqa and Health and Safety Check Sheet | 2b5390d9-5f97-420b-810f-ca26bcc31774
checkpoint-status | d88ccee6-d7de-4671-ae38-4865b3b3c0b1 |  | checkpoint | Substrate Inspected
checkpoint-status | 54065d0a-296a-47a5-ab69-57506f42e863 |  | checkpoint | Plastic moisture test completed 12hrs prior to start
checkpoint-status | f66c65d9-f9eb-4c1e-9ea0-2e13109eb1b0 |  | checkpoint | Moisture Reading below 8% before starting work
checkpoint-status | 1b16a009-c032-407f-badc-870cc655b4e3 |  | checkpoint | Surface conditioner
checkpoint-status | e7dbdec9-f1ba-499d-ac19-86648ce675a6 |  | checkpoint | Daily bond test or as required
checkpoint-status | 90e259e1-9c72-4d96-b209-1f1d590b5935 |  | checkpoint | Detailing of any penetrations
checkpoint-status | 665ca94c-e7c4-4908-9291-08011dfedcc6 |  | checkpoint | Installation of FlexFlash UN
checkpoint-status | c9c5862b-9e1a-47b6-95c5-b5a0715125d8 |  | checkpoint | Hydrotech first layer 3mm
checkpoint-status | fdee6851-64b2-4eea-9e95-9a0912b9f3a8 |  | checkpoint | Flex Flash F
checkpoint-status | 1d1287c8-64ca-4799-b342-0540712d8ab0 |  | checkpoint | Hydrotech Second layer 3mm
checkpoint-status | 85c04bfe-9bc2-4c56-94c3-afbda84807f9 |  | checkpoint | Casali protection sheet
checkpoint-status | 46cb0cd8-8b1d-441c-998f-9340de025d0a |  | checkpoint | ILD test report attached
checkpoint-status | 7765f36e-6cb6-44d2-a529-1b945a27d624 |  | checkpoint | Drainage mat & XPS board installed if requried
checklist-flat | 555188ec-9e76-41e4-8c05-19707278ffcf |  | checklist | Pre-Fab Checklist |  |  |  |  | Yes | Pre-Fab Checklist | 2bbea521-a2f7-42ea-861e-01ece89b49bc
checkpoint-status | bff8d8a9-812c-4e9a-a02e-50e3ccb54179 |  | checkpoint | Area clean and tidy
checkpoint-status | c116622f-436e-4801-9e99-c33498a6f8ec |  | checkpoint | Pre weld checks (pull tests)
checkpoint-status | 37985ae4-9eb6-4af8-ace6-0fc55091338a |  | checkpoint | Leister checks, hand and machine (heat, speed, fan)
checkpoint-status | 0bfa062c-c6a5-47a2-9d12-bfe179cd85b1 |  | checkpoint | Lay membrane staggered starts
checkpoint-status | 64ebabaf-8f3c-40da-9263-017a6a0289e7 |  | checkpoint | Prep roll- extra cuts, folds etc
checkpoint-status | b0697e20-f92c-425f-90c7-203306991567 |  | checkpoint | Storage membrane for site
checklist-sectioned | 4ef43f34-ae10-4582-a90a-c34a4973552c |  | checklist | Coreflex - Wall floor junction / detail Checklist. Grids: |  |  |  |  | Yes | zSYS - Coreflex - Wall floor junction / detail Checklist. Grids: - (old version) | 33900ea4-6f5f-44bc-be1c-26707c639d61
checkpoint-group | b559b958-646a-4785-8421-827eb7750dfb |  | section | Substrate checks
checkpoint-status | 6972b8e6-8e58-48e6-bd95-c15088376876 |  | checkpoint | Substrate is acceptable and as per specification
boolean | d3acb5a5-629b-5070-98fa-86209fe74990 |  | tickbox | No standing water / ice
boolean | 64447e8c-e238-5aa6-a975-8d6e693dbb1d |  | tickbox | Substrate is smooth
boolean | 0b5304af-a5d8-5931-8822-4c0164a14ac7 |  | tickbox | No debris
boolean | 444702ea-8201-5aa6-ae59-13a857bf7e37 |  | tickbox | Weather is suitable for application
checkpoint-group | a391a68a-19dc-468b-99ac-6d1dd1676cd3 |  | section | Wall floor junction / detail
checkpoint-status | ed18538e-bf55-48d3-b16b-503152fc59c1 |  | checkpoint | Voltex DPC must be removed 100mm minimum for lapping
checkpoint-status | 4cdffc4e-e252-4131-9df7-e64649e19eb2 |  | checkpoint | Voltex SWR nailed flat
checkpoint-status | d5df6135-81ca-452f-a5a2-a1e7e6cb37a5 |  | checkpoint | Coreflex60 min 300mm lapped onto the floor
checkpoint-status | 84ab75be-1d05-4826-9ea7-b6d94fb327ab |  | checkpoint | Coreflex to floor lap welded minimum of 100mm
checkpoint-status | 4d5ff983-c7e4-4a67-a797-dfaa16c3833a |  | checkpoint | Cetseal bead to secure flap
checkpoint-status | 65945cd1-db09-48a4-ba2e-5cbe2e20eb1c |  | checkpoint | Protected with SWR
checklist-sectioned | a4de7069-cf30-4ff6-b11f-f9d591e0b88c |  | checklist | Coreflex - Wall Checklist. Grids: |  |  |  |  | Yes | zSYS - Coreflex - Wall Checklist. Grids: - (old version) | 38f70f7d-1d55-4d2f-bee3-e4b9bef9f2a8
checkpoint-group | 5e946272-fe7a-4b3d-84f4-aab2b0da3ab6 |  | section | Substrate checks
checkpoint-status | 5fc66391-1967-48f9-8fe6-fe63fd3be91a |  | checkpoint | Substrate is acceptable and as per specification
boolean | b2f0cb85-eedb-545b-9c9f-74eb1a768d9b |  | tickbox | No standing water / ice
boolean | a3b9dbc3-7ad5-5a52-8b07-d6484f1beff1 |  | tickbox | Substrate is smooth
boolean | ffdf3f07-6eed-5e17-9b9e-e42ec7d7bfc9 |  | tickbox | No debris
boolean | 104fb697-9846-577f-8f18-f4612c574fae |  | tickbox | Weather is suitable for application
checkpoint-group | a7754359-e2b1-48ff-92a4-da405c923063 |  | section | Wall
checkpoint-status | f98d53ef-0042-474a-b2d7-a95aeed1da82 |  | checkpoint | Voltex DPC must be removed 100mm minimum for lapping
checkpoint-status | 3ce1e691-9cdb-4ee7-b5d5-eb94f8e4e324 |  | checkpoint | Voltex SWR nailed flat
checkpoint-status | eacf41bf-6e7f-44c0-8119-d4ce7f3c1f82 |  | checkpoint | Coreflex60 min 300mm lapped onto the floor
checkpoint-status | 225428d6-1568-4626-bab7-3a29dbbbdc21 |  | checkpoint | Coreflex to floor lap welded minimum of 100mm
checkpoint-status | 4979e49c-a399-4431-9b27-9bc9c46a1a29 |  | checkpoint | Cetseal bead to secure flap
checkpoint-status | cbebf89f-cc53-44e7-9998-b99009dac76c |  | checkpoint | Protected with SWR
checklist-flat | 1deb4c80-9971-45d9-a931-9c5286145cca |  | checklist | Slab/ Wall Handover Before Reo |  |  |  |  | Yes | Slab/ Wall Handover Before Reo | 511f706c-9514-4e8d-8650-8b8df2bf3f00
checkpoint-status | bf7f4470-1d88-47cf-8d64-7dda024e56f2 |  | checkpoint | Coreflex 60 detailed to all areas as per specification
checkpoint-status | 958ea62b-e76a-4a33-b549-9ae50c98d142 |  | checkpoint | All laps welded on coreflex 60 to specification
checkpoint-status | 2c9deacc-bf47-4b6e-b1f5-1b682d2e2cdb |  | checkpoint | Volclay DS over/ under coreflex 60 for protection
holdpoint | 7f48da18-0c31-45b3-8300-f8c86a4f9060 |  | signoff | Request Sign Off
checklist-sectioned | 9dfbba07-37a1-462b-9b61-49b37b134138 |  | checklist | Coreflex - Pile Cap Terminations Checklist. Grids: |  |  |  |  | Yes | Coreflex - Pile Cap Terminations Checklist. Grids: | 6ad85f62-96aa-42f9-917e-e1f3a23ff4d5
checkpoint-group | 6ae2877d-f4ba-40bd-a993-e4d68d84d98e |  | section | Substrate checks
checkpoint-status | 176511b4-ae54-4c50-a067-213366dbee70 |  | checkpoint | Substrate is acceptable and as per specification
boolean | abfc6492-b9ed-5a9c-a7ea-53514b93dcbd |  | tickbox | No standing water / ice
boolean | 5d13253b-490e-5f53-b16d-baf4ec2d8c95 |  | tickbox | Substrate is smooth
boolean | f803bfdc-f51a-5dca-9af5-45a5fc806943 |  | tickbox | No debris
boolean | 1bc93ab8-6293-5f9d-a6f8-2c310065eb16 |  | tickbox | Weather is suitable for application
checkpoint-group | d8772b2f-2d9e-49e6-ae90-0d63c2bb47b9 |  | section | Pile cap terminations
checkpoint-status | dae5e1e3-e18b-41ed-8d7e-4c2ab15ba552 |  | checkpoint | Pile cap termination requires 1 coat of sika 42 at 10ml atop pile then Akwaswell
checkpoint-status | 6c56d424-d051-40dc-b51b-1f26d56a02ba |  | checkpoint | Place Coreflexx 60 100mm on to pile top termination bar
checkpoint-status | b35b9da7-5c49-4c12-b6db-575fb4c38073 |  | checkpoint | Tooled Cetseal bead to edge of Coreflex
checkpoint-status | 736b593d-ad2c-45e5-9c3f-d54ec3c94b16 |  | checkpoint | Watersop XP to sit between Cetseal bead and reo of the pile
checkpoint-status | 63c2146f-3b9b-4695-ac89-c82dd5d5b1de |  | checkpoint | Volclay protection
checklist-flat | bf220367-9c32-4059-a7fc-d75d668ae23b |  | checklist | Waterbar |  |  |  |  | Yes | Waterbar | 93294d57-190e-4d21-a0e6-92c288def3a9
checkpoint-status | becc15c1-6915-4ad0-b257-30d916848d55 |  | checkpoint | Substrate clean and tidy
checkpoint-status | 3daa20b6-a411-4807-ba53-de6583e75249 |  | checkpoint | Cetseal on waterbar
checkpoint-status | 9aea2558-b749-4472-b416-bbf49ef6c510 |  | checkpoint | Waterbar
checkpoint-status | fc616c76-ccb3-4f9a-b5b7-d892dc7fef88 |  | checkpoint | Overall photo
checklist-flat | b0e6393e-5020-4265-a53a-877dff85df17 |  | checklist | Pipe Penetration |  |  |  |  | Yes | Pipe Penetration | 95034def-15d2-4bff-bcd8-8bb59d94bcff
checkpoint-status | f0e5bca6-c58e-4bdf-ab96-0704df41c812 |  | checkpoint | PEF ROD around pipe.
checkpoint-status | c033172e-f0be-4a53-bbef-f85e6645d7f7 |  | checkpoint | Grout: sika 418.
checkpoint-status | 09c5a08d-2e04-41dc-9fe0-ea4f0f7119a0 |  | checkpoint | Akwaswell around pipe (9ml min).
checkpoint-status | 04984472-0aa6-40e1-9261-0ef1134f3f71 |  | checkpoint | Coreflash (200ml around pipe).
checkpoint-status | e2d01f2e-3391-4be3-ade4-910a4f5f7d5d |  | checkpoint | Coreflash NR (300ml around pipe).
checkpoint-status | e685d3fa-681f-4a12-ad62-710ee3f3fd63 |  | checkpoint | Akwaswell between NR and pipe
checkpoint-status | 9b458e80-f8b6-49db-a22f-88fbf63d2dcb |  | checkpoint | Hose clamps- 2 clamps.
checkpoint-status | cfe543ae-9d5f-4233-ac6b-5ba82691f843 |  | checkpoint | Cetseal around clamps.
checkpoint-status | 3cde8545-bb5a-4c83-863e-cc57271eb201 |  | checkpoint | Voltex around pipe (300ml on pipe) duct taped.
checkpoint-status | 51d3f0e7-e445-4c3d-91fc-738ae5695104 |  | checkpoint | Clamp around pipe.
checkpoint-status | 9463b2ab-d660-4c47-87f5-abb7afeca831 |  | checkpoint | Protection.
checklist-flat | 791e5187-8174-4836-a0ff-4af4077564ff |  | checklist | Pre-Pour Inspection |  |  |  |  | Yes | Pre-Pour Inspection | a0a55955-3261-4fec-9a19-d55da0f43be4
checkpoint-status | 3af42c77-ea88-4c98-9248-9d9127d8dc7e |  | checkpoint | no holes
checkpoint-status | 350f9bc4-6859-44e8-b1f4-bd2295325858 |  | checkpoint | overall area photo
checkpoint-status | eac9d3dc-b9d8-49be-b94e-f87983c9848c |  | checkpoint | markup photo
checklist-sectioned | ffdf286a-c3b7-4894-907f-8a36563bf90d |  | checklist | Coreflex Pre-Installation Checklist (PERFORMED AT START OF JOB) |  |  |  |  | Yes | Coreflex Pre-Installation Checklist (PERFORMED AT START OF JOB) | a18c2718-dddf-4052-9266-d7b7626c1142
checkpoint-group | 53b572c4-e3e3-44e8-91d6-739ac1053c48 |  | section | Pre-Installation Meeting
checkpoint-status | ffc0ff7d-dc9e-4da1-b4fa-6f064af07709 |  | checkpoint | Installer information input
text | 69581d54-0197-5ae3-8a58-4860aeb5dc2c |  | textbox | Name
text | eaff9d08-0f40-53be-9bbb-17b33ee48474 |  | textbox | Email
checkpoint-status | d454200f-bc6a-4106-b91b-1890d94608ab |  | checkpoint | Installer has signed on screen
checkpoint-group | 7a5cf05d-5ab9-4f0c-aa95-c0b7af36151f |  | section | General Substrate Requirements
checkpoint-status | 32e5008f-6ea9-4812-bd4f-43b5eca07f90 |  | checkpoint | Concrete substrate must be uniform smooth finish with 19mm max sized aggregate to be used
checkpoint-status | ef1ccf99-61a2-40e5-9bd0-c9d886098c6f |  | checkpoint | No sharp edge aggregate to protrude through the smooth substrate layer.
checkpoint-status | 5167ceb5-4f40-4e06-b97f-8be33c9af399 |  | checkpoint | Acceptable weather for application.
checkpoint-status | 78aed20e-96a8-4dd4-8e02-04cee8b010c6 |  | checkpoint | Substrate must be free of debris (windy conditions need to be accounted for)
checkpoint-status | 692c0024-711c-4ae5-8e16-ab9d4ed4f4a6 |  | checkpoint | No standing water to be present where application is to take place
checkpoint-status | 87137ee0-76e6-43c8-a473-8d79ff04582b |  | checkpoint | No ice to be present
checkpoint-status | 80d52406-11a1-4abc-9380-02d82e9cc29e |  | checkpoint | Weather forecase must be monitored to ensure substrate doesn't become compromised
checklist-sectioned | 2a62371a-dcce-4056-9331-74fd188214fb |  | checklist | Coreflex - Wall Checklist. Grids: |  |  |  |  | Yes | Coreflex - Wall Checklist. Grids: | a36e901a-4073-4fe1-baa3-6f08a42c37b8
checkpoint-group | 3bc7ed65-454b-4374-9f8d-ce14ceb36c89 |  | section | Substrate checks
checkpoint-status | 65723c52-7b43-4976-a480-128af6e3fa5d |  | checkpoint | Substrate is acceptable and as per specification
boolean | 0bbe788e-5fb6-5d8d-b178-767bc1e4ebe4 |  | tickbox | No standing water / ice
boolean | 1c24e31c-072c-516f-a489-a41e203c51c3 |  | tickbox | Substrate is smooth
boolean | 458ab05b-21dc-5a10-a29a-53e53abd9cd6 |  | tickbox | No debris
boolean | e64e12e2-c482-5a87-8649-4088409a8c40 |  | tickbox | Weather is suitable for application
checkpoint-group | ab64078a-49ac-443f-9f52-0cf375220558 |  | section | Wall
checkpoint-status | ab759841-a7a2-44e6-91b9-28476e3da3e3 |  | checkpoint | Voltex DPC must be removed 100mm minimum for lapping
checkpoint-status | d8f5c2df-1342-4ef9-96e7-347fed9932ca |  | checkpoint | Volclay nailed flat
checkpoint-status | 4096cdf7-7a24-43a2-85e4-b98e3e58be95 |  | checkpoint | Coreflex60 min 300mm lapped onto the floor
checkpoint-status | ad93376b-8599-4078-864d-53d3f9f11b82 |  | checkpoint | Coreflex to floor lap welded minimum of 100mm
checkpoint-status | f52e025d-5e1a-436e-8092-b6b18884c4de |  | checkpoint | Cetseal bead to secure flap
checkpoint-status | ab42252b-d9a6-4dcf-945d-ca04960a928d |  | checkpoint | Volclay protection
checklist-sectioned | 37e06b23-9203-460e-b9c1-3b70fe052dd4 |  | checklist | Coreflex - Pile Cap Terminations Checklist. Grids: |  |  |  |  | Yes | zSYS - Coreflex - Pile Cap Terminations Checklist. Grids: - (old version) | c1644e99-34b3-4b0d-aeec-687f768993a1
checkpoint-group | f083dd92-c97a-4561-8019-540cdf4e29ec |  | section | Substrate checks
checkpoint-status | e710e79e-2c44-452a-bea7-a3b020220e1f |  | checkpoint | Substrate is acceptable and as per specification
boolean | 14c1454d-93d0-55d7-b5aa-2f2e8de55ac6 |  | tickbox | No standing water / ice
boolean | 2d11f4cd-43e8-5843-bd98-cc0fe966aef5 |  | tickbox | Substrate is smooth
boolean | a3aaef68-25b5-5ccc-a984-a405b59091f7 |  | tickbox | No debris
boolean | 31b02d17-4cfd-5eaa-ad58-03f5e6b6c7be |  | tickbox | Weather is suitable for application
checkpoint-group | e267009e-9e1c-491a-a930-08f266130e8f |  | section | Pile cap terminations
checkpoint-status | d93a114e-8dbe-4779-aabc-4bd220c12505 |  | checkpoint | Pile cap termination requires 2 coats of Sikadur 42 atop pile then Akwaswell
checkpoint-status | 211561a8-be0d-491f-9a23-3e550476bebb |  | checkpoint | Place Coreflexx 60 100mm on to pile top termination bar
checkpoint-status | d5ece158-264e-4e61-8554-196836ef4f3e |  | checkpoint | Tooled Cetseal bead to edge of Coreflex
checkpoint-status | 88ffec84-a29f-4e9a-aaa4-b917f3c5b191 |  | checkpoint | Watersop XP to sit between Cetseal bead and reo of the pile
checkpoint-status | dc8ea9ad-c508-42f2-ad64-2b58c077de44 |  | checkpoint | Voltex SWR as the protection layer
checklist-flat | 8d5a143e-102c-440f-8ffe-aa9ef72b0ffb |  | checklist | Inspected By: |  |  |  |  | Yes | Inspected By: | db39ed72-687f-4e51-b053-6046053ff46a
checkpoint-status | 78d2409a-cb62-460d-9e63-378f76d0aa16 |  | checkpoint | Inspected By
text | 6da458f6-dc0f-51dc-8453-7ca438450396 |  | textbox | Name
checklist-flat | af1d1fb9-72e4-4f15-863c-2ddddf621936 |  | checklist | Capping Beam Detail |  |  |  |  | Yes | Capping Beam Detail | f508dcb9-4ad1-49d5-ba49-943703c9fbba
checkpoint-status | 96db3dba-d25d-4122-b283-7ecc6b17f440 |  | checkpoint | Substrate clean and ready
checkpoint-status | 4c802083-eaf5-4ca4-be3e-f136e33b76cc |  | checkpoint | Voltex to wall
checkpoint-status | f8411b62-9de6-49bc-b270-a901768195fe |  | checkpoint | Core flex 60 welded
checkpoint-status | 3cb080ff-e612-4161-b2d2-86657b76ce94 |  | checkpoint | Cetseal to core flex weld
checkpoint-status | a53b90d4-8a25-4fe1-af33-77e1729f6851 |  | checkpoint | Core flash adhered with SB100
checkpoint-status | 9f8c59ed-8872-4428-8827-c2e3e6e538e3 |  | checkpoint | Termination bar
checkpoint-status | 2ef15f26-5574-4ef7-b629-ff0363eea932 |  | checkpoint | Hydro drain to back of membrane