## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | dcccd0c9-ed49-46ba-9ad9-64794afb61d9 |  | checklist | Window Installation |  |  |  |  | Yes | Window Installation | 30d905cf-ca7a-4b2d-9a0a-7e378813f61b
checkpoint-group | e04a9e6f-bb45-4360-8e9d-e7ce02634704 |  | section | Prior to Commencement – The following documentation are completed and approved:
checkpoint-status | 19f37b62-b5f5-4156-bc2a-3c9a2bdb960a |  | checkpoint | Shop drawings submitted and approved (BY PDS)
holdpoint | b8630895-a06e-4a04-af24-58a2862ef1e2 |  | signoff | Shop Drawing Holdpoint
checkpoint-group | 066c6302-e3d4-4210-a238-cf61532a14fc |  | section | Take Delivery of Window Units:
checkpoint-status | ef2523be-ca92-4fe3-ac74-a09667629677 |  | checkpoint | The window has been identified and is the correct size to the shop drawings
checkpoint-status | 27ad2aa1-c0c8-44f2-98f4-6b4ea6030d94 |  | checkpoint | The window is sound & undamaged. No rusting to frame, or door leaf.
checkpoint-group | 33ce3192-5a04-4963-b0c0-137bdf81f14c |  | section | Preinstall Door Checks / Openings Prepared to Receive Windows:
checkpoint-status | 12194e46-2312-47c9-948c-eec1abdaff58 |  | checkpoint | Opening has been allocated by CPB
checkpoint-status | 54ae06e5-9fed-4565-a320-55de5d3ea8c6 |  | checkpoint | The window type is known and has been identified for fire rating, acoustic and containment
checkpoint-group | 6c56730e-5993-490f-8b93-6f32063462de |  | section | Window Installation (Part 1):
checkpoint-status | d2d2718b-5807-49f9-a25c-0b497a8f29d4 |  | checkpoint | Shop Drawings and typical details for appropriate window install have been sighted & understood.
checkpoint-status | d28b89ee-60e1-479f-aed6-cc7013822443 |  | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
checkpoint-status | e4c2361c-6c90-4a6e-a98e-814a8bdc18fb |  | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
checkpoint-status | a40e04c2-a0d6-4147-a483-85e3e2370aa8 |  | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
checkpoint-status | 1aac14a9-08ff-4b50-bb6d-4f01e5b00711 |  | checkpoint | The window is installed plumb, square, and at the correct wall lining schedule.
checkpoint-group | 346b91f2-eb4b-4963-8e44-bf0da2507664 |  | section | CPB Sign Off (Part 1):
checkpoint-status | ec2c9644-650b-42e4-93ae-01de9232eca2 |  | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
holdpoint | e95f3989-7cb7-49e9-8fc2-bafba1f10ca5 |  | signoff | CPB HOLDPOINT
checkpoint-group | bb019b20-572e-4d9e-bfa7-57291dc99a44 |  | section | Window Installation (Part 2):
checkpoint-status | 8e33312c-4aae-478b-8c63-6a4490a55fa0 |  | checkpoint | Sealant is applied to correct depth on back rod as required.
checkpoint-status | 9b15a886-00ce-470f-8764-7d8150a7e8d5 |  | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
checkpoint-status | 8ce2fc57-866b-45f1-bedd-254a1fa55cdb |  | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
checkpoint-status | 8864d850-43db-4bd5-8812-3455386a3bd7 |  | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
checkpoint-status | fff8de81-21ba-4842-961b-e5d125bf8897 |  | checkpoint | Check for any potential leak points for grouting.
checkpoint-status | da7c7806-04c2-4abc-b062-a2f8ae474198 |  | checkpoint | Leaf to frame clearances checked prior to grouting
checkpoint-status | 974b1d6b-1016-46ae-b72d-3770f9d1ac1b |  | checkpoint | Open Glass Pallet & check glass is undamaged, correct sizes including type & thickness
checkpoint-status | 5bc80bfa-76c0-436d-9a27-646469b6435f |  | checkpoint | Protective Film to glass is peeled back enough to allow sealant to bond fully to glass
checkpoint-status | 803ad4b5-c265-441a-8c5f-fea8c6899151 |  | checkpoint | Glazing tape set to 6mm from edge of glass to achieve correct sealant depth
checkpoint-status | af187e5b-377a-4bb6-99f9-cdca174aaa2e |  | checkpoint | DOWSIL 791 silicone weatherproofing sealant applied to exterior glazing in accordance with installation instructions
checkpoint-group | a2702646-b144-4eed-8c66-d2bcbc130152 |  | section | Final Checks
checkpoint-status | 0389fe1d-eeba-460a-8ca0-43bdc3d56135 |  | checkpoint | Window has been sealed
checkpoint-status | eb9c8091-1b01-4e50-ac45-32742208ba94 |  | checkpoint | Window has been grouted (if applicable)
checkpoint-status | 800d27de-e462-4c0c-ac89-55301a0d179f |  | checkpoint | Window has no damage or rustvisible
checkpoint-status | 2321904f-2b50-4319-b437-5fc178100621 |  | checkpoint | Glass checked for damage, scratches & ensure protective film is still in place
checkpoint-status | 1b99bb99-d05a-4e7c-8fb6-8bc9ff13385e |  | checkpoint | Sealant continuous, clean & no air pockets
checkpoint-status | 057f5d70-d4e6-4e4a-a8bb-b0b934931ea3 |  | checkpoint | All fixings installed & tightened with good hold & no signs of stripping
checkpoint-status | 1d65a5a1-52fe-4d1c-a706-ef631b1bd028 |  | checkpoint | Window has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
checkpoint-group | 4423e0b9-2c74-45e1-b6db-98c65ed85155 |  | section | CPB Sign Off (Part 2):
checkpoint-status | c277e4c5-3e2a-4ea5-b816-5916f496f162 |  | checkpoint | CPB to complete final checks & sign-off unit
holdpoint | 511819ac-4a96-45de-aaf7-24e8da760924 |  | signoff | CPB HOLDPOINT
checkpoint-group | e1bf6f79-852e-408e-9d97-fef27d99ad52 |  | section | Final Sealant
checkpoint-status | 1a494057-00e5-4f87-bfe1-fc1e5496abb4 |  | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
checkpoint-group | 8bed517c-2460-4caf-bbe9-4e9ef2050cfe |  | section | Site Hose Testing for External Windows:
checkpoint-status | ade53f84-b684-4636-abf2-3d5667971487 |  | checkpoint | Each window is to be site hose tested by approved & certified water testing specialists.
checkpoint-status | d1256493-2e6c-4b32-aa19-7383021c7c46 |  | checkpoint | Test Results to be included with this ITP
checklist-sectioned | 57545d33-ff22-47c2-be2f-269041c4ab77 |  | checklist | Partition Lining |  |  |  |  | Yes | SYS - Partition Lining ITP V1 | 3fa23a75-011e-4d06-af41-964501ef3c3e
checkpoint-group | c088ed6e-e8f7-4c70-b9a1-9f95d8d534d7 |  | section | Board Lining
checkpoint-status | 53ce2f58-4153-4303-96e7-da8dfac548bd |  | checkpoint | Area ready & accessible
label | c08e9936-a498-5be5-8ef5-690ba532e933 |  | note | 1400 Series & USG BORAL Specifications
checkpoint-status | 4f7588da-b0a3-4b7d-a145-00b7c66b3f85 |  | checkpoint | Inspect the sheeting of walls as per BORAL specification & checklist below
checkpoint-status | 4365b0d1-5aad-4174-b54a-e97c485ad13c |  | checkpoint | Run sheets across the framing members (refer BORAL standard details)
checkpoint-status | f56cb52c-ac83-4ec4-9be7-b527dafda7de |  | checkpoint | Stagger end joints in a brick pattern & locate them on framing members away from the corners of large opening
checkpoint-status | d57cfc77-f362-4b27-b400-021b5785d253 |  | checkpoint | Achieve level of finish as specified in the material, component & finishes schedule (Sec 4.2)
checkpoint-status | 16462055-ab04-48db-97b5-26a96e056b02 |  | checkpoint | Multiple sheet layers: Fill & flush up all joints & fixings in each layer & caulk up perimeters & penetrations before commencing succeeding layers
checkpoint-status | 938a1f17-def2-41c5-8360-abb5c63108a7 |  | checkpoint | Stagger all sheet joints by minimum 200mm
checkpoint-group | f2fdb579-ff64-48b0-b646-2ab6e489f5cb |  | section | Doors & Internal Windows
checkpoint-status | ede97bc9-9f28-4cbf-9a9d-f5fb7ae2f3c5 |  | checkpoint | Doors & internal window opening: check door schedule, window schedule & kit of parts
checkpoint-status | 59254f12-1dd7-48b1-b4de-68383b852c8f |  | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
checkpoint-status | 337ac63c-7025-4035-b6af-ecf1c8d8c2f9 |  | checkpoint | Butt joints: Provide perforated paper reinforcing tape
checkpoint-status | 9d503423-8216-4620-aaa5-730edbe7f116 |  | checkpoint | External corners: Provide matching purpose made beads
checkpoint-status | 7684dfb1-9cf7-4aea-9bb3-73baf464c38a |  | checkpoint | Internal corners: Provide paper tape & bedding compound
checkpoint-status | 5b362c5d-3f74-477e-8243-69713150a3b1 |  | checkpoint | Provide sealants at junctions between partition systems & with other building elements
checkpoint-status | 772c5a01-8e08-4917-95f6-4820dae6d8e5 |  | checkpoint | Provide trim such as beads, moulding & stops to make neat junctions between lining components, finishes & adjacent surfaces
checkpoint-group | eea424ef-e095-43df-bb2a-c359cd02b388 |  | section | Fire Walls
checkpoint-status | 0ee8af08-7931-4064-a3f7-6fb58ff0964f |  | checkpoint | Installed as per BORAL design & install specification
checkpoint-status | ea38d2a8-c2fa-48c6-988d-921d55b2c2e6 |  | checkpoint | Correct FRL achieved
checkpoint-status | 47484404-a6dd-4802-a2bc-23c159892fa2 |  | checkpoint | Deflection heads & all joints sealed, taped & set (fire sealant is approved prior)
checkpoint-status | 3d17cafd-1ccd-47a3-9157-3cf0b16af1e7 |  | checkpoint | All penetrations through fire walls below & above ceiling protected/sealed
checkpoint-group | 6577ad1d-01d0-4f94-801d-99697a53b2f7 |  | section | Smoke Walls
checkpoint-status | 320ba0b0-7f53-4314-bc1e-efc30f5eab9b |  | checkpoint | Installed as per BORAL design & install specification
checkpoint-status | 4285b8b7-f007-496e-8989-744cf9925370 |  | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
checkpoint-status | 2b57a1d6-ed3c-409e-8d0c-0d1f69ed416e |  | checkpoint | All penetrations through smoke walls below & above ceiling protected/sealed
checkpoint-group | 6f4ac8dc-8b8b-454e-87e8-3be727e41000 |  | section | Acoustic Walls
checkpoint-status | 4a513b34-6118-4bb8-963b-16e295fb1613 |  | checkpoint | Installed as per BORAL design & install specification.
checkpoint-status | b7c2a1e2-9a99-42c6-a213-c222c32e8ba0 |  | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
checkpoint-status | e299805b-5c82-4d4e-b1c6-296370fefd50 |  | checkpoint | All penetrations through acoustic walls below & above ceiling protected/sealed
checkpoint-group | 36abb64c-fa1a-46b2-9eca-3f76e78b00e0 |  | section | Sign Offs
checkpoint-status | 0454ba57-b719-464e-9d19-dfb2a0bdbff4 |  | checkpoint | Wadsworth final sign off - add signature
checkpoint-status | 7d11346b-fd2f-465d-877a-2a2274ae3f55 |  | checkpoint | CPB final sign off - add signature
checklist-sectioned | faafc124-00b2-41fa-9b03-71dd4cc90ff3 |  | checklist | Ceiling Lining ITP |  |  |  |  | Yes | Ceiling Lining ITP | 57905a85-4bc7-45d5-b2df-b95249222ad3
checkpoint-group | d9afdedb-2927-4211-87db-6d4c8cc394e9 |  | section | Construction – Tile ceiling, Grid ceiling, Lining
checkpoint-status | 7bc7c55e-bfa9-4338-93ac-5ab6a0fedf6d |  | checkpoint | Area accessible & ready
checkpoint-status | 7d1653b8-1299-4c83-bf87-f56ecec8523f |  | checkpoint | Provide board lining to a finish and workmanship as per supplier installation guides.
checkpoint-status | 25b575fa-6356-41eb-adf2-7d6cf6605538 |  | checkpoint | Fit accurately and neatly, without distortion and free from air leakage and staining.
label | c7dda36f-0739-5f6f-a5d8-0c7a829720c1 |  | note | Clip locks: Where ceiling units are exposed to loads from wind actions or as required, insert lock clips at the junction of carrier rails and units.
checkpoint-status | 3f7ac865-dea8-4cb4-8fba-f32dc4651ad8 |  | checkpoint | Set out patterned or heavily textured materials with a consistent direction of pattern or texture.
checkpoint-status | 9ff35720-de9a-4a4e-a95d-e054bbad2d4b |  | checkpoint | Cut ceiling unit edges: conceal, or finish to match prefinished edges.
checkpoint-status | 7244d0b8-0555-4a50-b9e8-df39a1609ef0 |  | checkpoint | Multiple sheet layers to fire rated and acoustic rated elements
label | 9340e218-7703-5d4f-ad5d-79d8fa69bb05 |  | note | Fill & flush up all joints and fixings in each layer and caulk up perimeters and penetrations before commencing succeeding layers. Stagger all sheet joints by minimum 200mm.
checkpoint-status | ca7edf95-b9e9-4438-bac0-3bdab440b89e |  | checkpoint | Board joints support: Provide framing parallel to the joint on each side. Do not fix the lining to abutting building surfaces
checkpoint-status | 3756876b-5a5e-4488-94f7-b84603fa9670 |  | checkpoint | Flush joints: Provide recessed edge sheets and finish flush using perforated paper reinforcing tape. Locate & position joints to intersect light fixtures, vents or air diffusers.
label | 2d583d71-b687-5faf-87e0-4b3b2a52aaeb |  | note | Tolerances: Suspension system bearing surface for flush lined ceiling to AS/NZS 2589 table 4.2.2
checkpoint-status | 44d28b4b-0279-44c1-be06-7c2822c532a6 |  | checkpoint | Levelness: Max tolerance of ±5mm relative to the documented height datum for the particular ceiling in each room or space.
checkpoint-status | 9a6e5496-26a9-4ac8-9711-9a28f52bd916 |  | checkpoint | Trims & accessories: Provide trims at junctions with other building elements and surfaces, including walls, beams and penetrations.
checkpoint-group | e12958dc-6422-4209-9d60-20b64c0afc97 |  | section | Control joints
checkpoint-status | 9e81255e-650b-4b85-8824-9d248393e824 |  | checkpoint | Align ceiling control joints with the structural control joints. Do not bridge structural control joints.
checkpoint-status | 5ed5e4f4-68e1-496e-ad21-95425ee6c16c |  | checkpoint | Provide purpose made metallic coated control joint beads where documented.
checkpoint-status | cc9af38c-a393-48a8-8500-64da89f06496 |  | checkpoint | Provide framing parallel to the joint on each side.
label | c45e3c9c-5d92-5f0e-a754-8abc6cfafd30 |  | note | Plasterboard lining: 12m centres
label | 7b5afa3d-6f8b-5995-a2a5-f8a813c5141d |  | note | Fibre cement lining: 7.2m centres
checkpoint-status | fd8d7ed7-6f90-4586-a8f0-4e513aaa485e |  | checkpoint | Infection control: Provide full depth paintable sealant, finished flush with the face of the lining, to locate where documented.
checkpoint-group | da78ad7d-e460-4698-bd10-40398bd73521 |  | section | Bulkheads
checkpoint-status | 29339282-92b4-4546-8694-2b8a7aac7218 |  | checkpoint | Integrate bulkheads with the ceiling structure and brace to prevent lateral movement. Where ceiling is terminated at the bulkhead, provide for seismic requirements
checkpoint-group | e32505f4-b75f-41d4-ad73-bce39ccaba9f |  | section | Access panels
checkpoint-status | 033e8d99-06b9-43fc-8818-b7178d7c2ccc |  | checkpoint | Match the access panels to the ceiling in appearance and performance
checkpoint-status | cda4aa89-d084-430f-b6b8-01fd52e0b876 |  | checkpoint | Provide each access panel with an ID - Record ID in comments
label | 70cb5b7b-c47f-52ed-9b8b-f4517d61bc5c |  | note | Provide access panels supported and anchored to permit ready removal and refixing
checkpoint-status | d1ae9687-fa85-4c66-887e-12c703ea69f7 |  | checkpoint | Reinforce the back of the access panel to prevent warping and facilitate handling
label | 8b71dade-5b7a-50ad-8f76-6e1ba1367f74 |  | note | Provide fire rated and acoustic rated panels where documented or where required to maintain the designated rating of the ceiling element
checkpoint-group | 23539a4c-2038-422e-9f4c-cceab0d8ac29 |  | section | Additional checks for fire-protective board lining
checkpoint-status | 6dcea947-2ccb-47a7-9b18-928618d351e5 |  | checkpoint | Check the fire resistance levels: Drawings and Spec Sec 4.6 Misc. Items Schedule
checkpoint-status | 45b04367-3d84-4694-9ea5-acab8c39d33f |  | checkpoint | Fixings: Direct to concrete elements and to purpose made steel framing
checkpoint-status | 3ab8d168-e1f0-4ac0-8c45-b94bb744dbfb |  | checkpoint | Penetrations: Seal penetrations in the board lining to maintain the integrity of the required fire resistance level including suspended ceiling hangers and suspension systems for services.
checkpoint-status | 192ad387-b9a6-450f-a972-6d5e87e8c8eb |  | checkpoint | Board perimeter: Provide fire sealant and trims at junctions with other building elements and surfaces, including walls, beams and penetrations to maintain the required fire resistance levels.
label | dd1900ab-95f6-5c89-8ad5-fec1fd63123b |  | note | Label each fire stopping to AS/NZS 2589.1
checkpoint-status | 8fd6e4fe-0c8d-40df-9533-7b474feb96f4 |  | checkpoint | CPB final sign off - add signature
checklist-sectioned | a4139b95-6069-4b9d-aa56-6087a76918d8 |  | checklist | Door Installation |  |  |  |  | Yes | Door Installation | 61efa196-645d-42b6-8766-6e5d723003cb
checkpoint-group | a6151564-819a-43f8-97f8-41e5505215d8 |  | section | Prior to Commencement – The following documentation are completed and approved:
checkpoint-status | 6bbf6002-1614-4a79-8471-488a028e0d9f |  | checkpoint | Shop drawings submitted and approved (BY PDS)
holdpoint | 1dff025d-ec8d-4d18-b955-68eed411ace2 |  | signoff | Shop Drawing Holdpoint
checkpoint-group | cde1fd8d-cc72-4b60-a440-2399c100bb59 |  | section | Take Delivery of Door Units:
checkpoint-status | eb3099c3-d5ad-4ec1-9b97-08b3594c2f8d |  | checkpoint | The door has been identified and is the correct size to the shop drawings
checkpoint-status | 4b4d27f7-7df9-4c7b-a9a3-dd84f9c65a82 |  | checkpoint | The door is sound & undamaged. No rusting to frame, or door leaf.
checkpoint-group | 6eb5f3f6-1e29-48c5-bf99-311b263b2834 |  | section | Preinstall Door Checks / Openings Prepared to Receive Doors:
checkpoint-status | 67f2ac55-c67b-4e86-b9a4-493391889e34 |  | checkpoint | Opening has been allocated by CPB
checkpoint-status | 90be55b7-d770-41eb-b061-1eb81e003640 |  | checkpoint | The door type is known and has been identified for fire rating, acoustic and containment
checkpoint-group | fccfdc0f-1ccb-41ff-9ab4-61124f597dfc |  | section | Door Installation (Part 1):
checkpoint-status | 17c3144d-8d00-48ce-bab6-d1d3bbfa3d7a |  | checkpoint | Shop Drawings and typical details for appropriate door install have been sighted & understood.
checkpoint-status | f51a2411-0711-418c-b47b-f11156c986a2 |  | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
checkpoint-status | 692d0085-09c6-437b-ad2d-da7f2ee01bd7 |  | checkpoint | Door frame is packed with Ceramic Wool / Acoustic Wool (if applicable).
checkpoint-status | a325482b-8a25-42db-afbf-05b44a4df775 |  | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
checkpoint-status | 66361ec1-f653-4fb2-9c8c-1d24345a2c0c |  | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
checkpoint-status | 48a156d9-192e-4f7b-ad7e-8659ad5bec53 |  | checkpoint | The door is installed plumb, square, and at the correct wall lining schedule.
checkpoint-group | 04461d76-7133-40d0-bceb-a8f13689db8c |  | section | Door Installation (Part 2):
checkpoint-status | a4a79d5a-7106-4590-bc23-342afb28eab8 |  | checkpoint | Wiring for the security has been chased & not damaged (By Honeywell).
checkpoint-status | 6f26c84d-a959-4904-a20b-43774a2dc1f1 |  | checkpoint | Security Contractor advised conduits & prewire can be complete (if applicable)
checkpoint-group | cce31cff-eea9-4e16-9e76-6bbd47f290c4 |  | section | Honeywell Sign Off:
checkpoint-status | ea6043c5-bb24-43aa-af96-852e9827093c |  | checkpoint | Confirmation from the security contractor that all their works are complete & installation can progress to final stage
holdpoint | e1ec5ae9-e355-43c4-b33f-84749cf91655 |  | signoff | Honeywell HOLDPOINT
checkpoint-group | 37810b88-198e-4a68-bee7-dfbc8df9562e |  | section | CPB Sign Off (Part 1):
checkpoint-status | cbec37cf-be68-4aa4-b2b4-ad784cdb8482 |  | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
holdpoint | c5a90d21-e4d7-42d3-ac94-98b7f1bb00ce |  | signoff | CPB HOLDPOINT
checkpoint-group | c01b2e21-bc98-4b76-b023-2121ad22d99d |  | section | Door Installation (Part 3):
checkpoint-status | aa7c76a0-3ae2-478c-a0b4-84dc87d91519 |  | checkpoint | Sealant is applied to correct depth on backing rod as required.
checkpoint-status | a4c059ba-957f-45ce-950a-045e923f24c4 |  | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
checkpoint-status | f89fd0bb-a899-42c6-9c2d-ab44a418855a |  | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
checkpoint-status | 3e9d90cb-fd1f-4a49-9106-2aa2fce7d957 |  | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
checkpoint-status | 633ceea7-f274-4162-a389-ce58fda6133d |  | checkpoint | Check for any potential leak points for grouting.
checkpoint-status | 9562eda5-afe3-45d2-b4c1-176ddf390132 |  | checkpoint | Leaf to frame clearances checked prior to grouting
checkpoint-status | 63660be8-981a-4a40-a128-77a6222a3215 |  | checkpoint | Frame is braced (if applicable)
checkpoint-group | e9888504-3100-4249-9cfa-79b7a9c4f12c |  | section | Final Checks
checkpoint-status | d6e57feb-fe03-46c7-b0d7-203d2f3f321b |  | checkpoint | Door has been sealed
checkpoint-status | c50ac79a-8c0c-4b8b-9fc1-c2428b7ae24e |  | checkpoint | Door has been grouted (if applicable)
checkpoint-status | e6ea1ac0-9b29-40fc-b323-fe3992f74f1f |  | checkpoint | Door has no damage or rust visible
checkpoint-status | 79b581ee-5ee3-406b-bf61-175e456b73e3 |  | checkpoint | Door has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
checkpoint-group | 74f5456d-2726-4721-8130-90ab99dc2134 |  | section | CPB Sign Off (Part 2):
checkpoint-status | d33407d4-75f8-4a06-94f3-4e7fc759d68d |  | checkpoint | CPB to complete final checks & sign-off unit
holdpoint | 0091e685-2704-423a-919f-6ca7c803864f |  | signoff | CPB HOLDPOINT
checkpoint-group | 15e88069-d943-48f0-9817-fd574fcea8b0 |  | section | Final Sealant
checkpoint-status | 382109d8-28ff-4493-a811-2d443a6c67df |  | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
checkpoint-group | 26b540e5-6f86-4455-9818-d5203fe8a9ec |  | section | Site Hose Testing for External Doors (Post hardware install):
checkpoint-status | 5057cb19-7a24-4492-9c8f-d522ed102585 |  | checkpoint | Each door is to be site hose tested by approved & certified water testing specialists.
checkpoint-status | 99a954d6-e3e1-4a04-9651-d21652d70c98 |  | checkpoint | Test Results to be included with this ITP
checklist-sectioned | 0b7666c0-7d1c-4688-a56e-bcde74de85b4 |  | checklist | Partition Framing ITP |  |  |  |  | Yes | Partition Framing ITP | 63a1c0cc-de09-4a96-86db-fa2d295868f3
checkpoint-group | 15a071ad-bd3e-49dc-9b1b-f3631d759621 |  | section | Prior to Commencement – The following documentation are completed & approved
checkpoint-status | ef15469a-6e36-4488-862a-ae0749656d27 |  | checkpoint | Area ready & accessible
label | eb8367cd-aa8c-5ff5-a754-f9be90ec90f4 |  | note | 1400 Series & Rondo PS1
label | 04168265-8ca3-5d4c-a2a7-9376eb773da9 |  | note | Structural design, documentation & certification for secondary structural steel elements providing support for partitions & fixtures
label | 720506cc-4533-5da3-a893-e061fbadcb74 |  | note | Shop drawings submitted & approved
label | 3fcb8e0f-ff60-5403-9482-46c7289723e0 |  | note | Samples & prototypes submitted & approved (Fire sealants approved)
label | e0981874-c802-5d10-9907-18899b582c6f |  | note | Test results of prototypes submitted (section 1.19)
checkpoint-group | 3a8ebcfb-c336-4750-8628-a35e63a1eff5 |  | section | Set out
checkpoint-status | 046c9ee6-e5b7-44ae-b786-a4b5e0849768 |  | checkpoint | Partitions set out plans current revisions checked & wall set out competed as per the current plans
text | 5edffdcd-f802-5fac-94f9-e4995c3a8405 |  | textbox | Revision no.
checkpoint-group | ab58594c-2fd1-45f0-aee9-da8c41126b19 |  | section | Stud Framing / Wall Strapping
checkpoint-status | 28d4324a-b5de-4e6c-9456-3a4f6394a23d |  | checkpoint | Inspect the framing of walls as per Rondo PS1
checkpoint-status | 08a8528b-8fa8-456d-8099-d8241888a4b2 |  | checkpoint | Check sizes & spaces as per the partition types
checkpoint-status | 70e29842-0541-4396-9d25-86e9a2237378 |  | checkpoint | Fix tracks 600mm centres & 100mm from ends
checkpoint-status | f250f93f-bbdf-4be9-aa5b-a6bb8f81431a |  | checkpoint | Fixing to post tensioned concrete: Maximum embedment for fixings = 45mm
checkpoint-status | 526302c1-9ad0-4b57-839e-8c52a9134c74 |  | checkpoint | Install boxed double studs at jambs to all openings
checkpoint-status | 86def223-ea82-4bb2-a1ac-fab3037987d0 |  | checkpoint | Part height partitions: Brace as per Rondo PS1
checkpoint-status | 51c67c5d-d71f-4464-baf3-0f3ecc4ea0a9 |  | checkpoint | Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm
checkpoint-status | 7252b957-a09c-4224-a8a9-b30a62dc4bec |  | checkpoint | Achieve overlap of at least 30mm of the deflection head channel’s section vertical leg with the top plate of the wall framing
checkpoint-status | 42fa99ed-6818-44ca-9fa8-c413437afc47 |  | checkpoint | Rotate intermediate studs into tracks for friction fixing
checkpoint-status | 538a1b7c-6dcc-469b-88b9-726a4bff4abd |  | checkpoint | Staggered stud framing walls: Studs staggered at 300mm centres set in oversized top & bottom plates to allow each face to have stud fixing at 600mm centres
checkpoint-status | b7181791-13cc-4907-9713-266dabbcb220 |  | checkpoint | Structural floor control joints: Disconnect partitions over joints with detached double studs & ensure bottom tracks, bracing & top tracks are not fastened across joints
checkpoint-status | cf29bb2e-0bf2-4688-9989-e733358674fb |  | checkpoint | Stud service holes: Splice additional stiffening to studs if site cut service holes exceed 1/3 the width of the member
checkpoint-status | 15bc5eb8-1aaf-42a4-8350-0020365bd0f8 |  | checkpoint | Metal separation: Provide isolation layers & lagging to isolate incompatible metals
checkpoint-status | 6bf52cd4-7d42-4db9-9407-7753a2bc1585 |  | checkpoint | Provide fire, smoke & acoustic sealing where indicated on the drawings/details
checkpoint-status | 1d2974ea-46e4-488c-9bce-82b9ee0b375c |  | checkpoint | Provide vermin barriers (where indicated on drawings / required)
checkpoint-group | df093996-771a-41b8-89d0-119ab83a168c |  | section | BVT Engineering Inspection
checkpoint-status | bb3edf92-f095-442e-b40c-1919db15c0c2 |  | checkpoint | BVT Sign Off - please attach any relevant documentation & photos
checkpoint-status | 0f2a2dab-fe27-4f34-a4f0-44be9646f32b |  | checkpoint | BVT to complete construction monitoring on walls, in line with Rondo PS1 & provide report.
checkpoint-status | e678cb1e-2035-4abc-8213-714330e26a0c |  | checkpoint | BVT to complete in depth sign-off sheet for all walls once engineering & construction is confirmed.B
checkpoint-group | 3c295086-50d9-492d-9011-0189b1d9f4ac |  | section | In-Wall Noggins / Fixtures
checkpoint-status | 9dba37bc-2f0f-419d-88ad-0f2528154786 |  | checkpoint | Fix noggins as required for the framing system, skirting, door stops & to accommodate in-wall & in-ceiling services
checkpoint-group | 0551c039-a852-49e5-88bd-d86d19e85150 |  | section | Insulation
checkpoint-status | f71aa428-15e9-461a-ba68-d03763e65b2b |  | checkpoint | Install acoustic. Refer to Component & Finishes Schedule, drawings & details.
checkpoint-status | 28c6fce0-7561-4568-8ce5-b3abace672fe |  | checkpoint | Thermal insulation Refer to Component & Finishes Schedule, drawings & details (Works Completion Test – IR to inspect – WCT-08)
checkpoint-group | 3faa033e-be76-4b48-a255-9bf3f33e3365 |  | section | In Wall Services
checkpoint-status | ee4c652e-ba3a-4326-b7d2-7e46311a759d |  | checkpoint | All service trades to complete sign-off on walls as per room sign of sheet prior to sheeting commencement.
checkpoint-group | 0600ebd2-c602-44be-9c35-07ea70f9fe46 |  | section | Sign Offs
checkpoint-status | f9df4baf-a32c-456c-a0ce-6a3b1a057267 |  | checkpoint | Wadsworth final sign off - add signature
checkpoint-status | 6ff507da-221c-4508-9757-73625e9cdddc |  | checkpoint | CPB final sign off - add signature
checklist-sectioned | 502ebda1-b5d0-4d1d-a2a9-3ae9a1d83659 |  | checklist | Louvre Installation |  |  |  |  | Yes | Louvre Installation | c57e6a6f-9203-4279-bacb-1c904a970d32
checkpoint-group | 9cb0f9b8-0f64-4d87-adfb-f8d372a8713b |  | section | Prior to Commencement – The following documentation are completed and approved
checkpoint-status | 1a2e0b03-172f-4300-b2b0-45c8603995f5 |  | checkpoint | Shop drawings submitted and approved (BY PDS)
holdpoint | 2bcf5fee-cee7-40d7-85f9-bd123bab4274 |  | signoff | Shop Drawing Holdpoint
checkpoint-group | b3bf13be-15e6-4c5a-bc36-b1d09e296424 |  | section | Take Delivery of Louvre Units
checkpoint-status | c697b5f4-3d19-4283-a63d-38da0c6886ac |  | checkpoint | The louvre has been identified and is the correct size to the shop drawings
checkpoint-status | a15be8c8-f125-4c49-a9e8-1e0a92f3b1e8 |  | checkpoint | The louvre is sound & undamaged. No rusting to frame, or door leaf.
checkpoint-group | a6efa0a2-756b-4a62-a3db-4fb3c1d07108 |  | section | Preinstall Door Checks / Openings Prepared to Receive Louvres:
checkpoint-status | ae04cf4a-ef52-4894-b46b-50027a6dcfe9 |  | checkpoint | Opening has been allocated by CPB
checkpoint-status | 3e4b6033-fa45-4a22-9395-160caf2e65a7 |  | checkpoint | The louvre type is known and has been identified for fire rating, acoustic and containment
checkpoint-group | adda802a-36c5-4da5-9de0-d79e9fcfad99 |  | section | Louvre Installation (Part 1):
checkpoint-status | 6eb7958d-90a1-42cb-93df-6d14c86630e8 |  | checkpoint | Shop Drawings and typical details for appropriate louvre install have been sighted & understood.
checkpoint-status | da684752-7f40-43d0-bfa4-03ddf547eff3 |  | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
checkpoint-status | 7278f256-3f7d-4e82-810b-45e7790729d8 |  | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
checkpoint-status | 84e953e9-916b-4b2f-a425-4eee96b25e82 |  | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
checkpoint-status | 9d51b874-08e8-424e-a634-b1f39abfd6cc |  | checkpoint | The louvre is installed plumb, square, and at the correct wall lining schedule.
checkpoint-group | b0488c04-8db9-4c84-8e8f-dd7cab218eec |  | section | CPB Sign Off (Part 1):
checkpoint-status | b7512924-ef0e-469e-98d5-5bada1907476 |  | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
holdpoint | 7c0b32e8-2051-45b3-b601-653799fe2e4a |  | signoff | CPB HOLDPOINT
checkpoint-group | 8d446dce-38a5-46b0-8a2e-c78a5113e7cc |  | section | Louvre Installation (Part 2):
checkpoint-status | 8a06b544-c42f-4306-bc4d-4a6c421c969f |  | checkpoint | Sealant is applied to correct depth on back rod as required.
checkpoint-status | d782f4a8-95cf-44d6-ac0f-8ad7e6f51ce2 |  | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
checkpoint-status | 36c16fc7-f1e5-4354-8411-64ec515f9fb5 |  | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
checkpoint-status | 78da56fb-6b9f-4698-bec9-532de4e9455d |  | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
checkpoint-status | 0e29e241-82cb-4538-86bc-393011363c17 |  | checkpoint | Check for any potential leak points for grouting.
checkpoint-status | d741c4cc-c429-43cd-b188-ca43b6434806 |  | checkpoint | Leaf to frame clearances checked prior to grouting
checkpoint-group | b21b1aec-532a-46de-a4f5-1984aa625bf9 |  | section | Final Checks
checkpoint-status | 50aab367-2150-4cb1-ad2c-5a459bab3234 |  | checkpoint | Louvre has been sealed
checkpoint-status | 9d2c2b9a-777e-450e-a3e0-de96cae855ee |  | checkpoint | Louvre has been grouted (if applicable)
checkpoint-status | b0af9f13-102c-46d9-bf25-2149af28a060 |  | checkpoint | Louvre has no damage or rustvisible
checkpoint-status | 9aabb693-496f-4ab0-bfc6-73af3c48e968 |  | checkpoint | Sealant continuous, clean & no air pockets
checkpoint-status | be3d78e9-bfc5-44f7-815f-b79de3c1c10c |  | checkpoint | All fixings installed & tightened with good hold & no signs of stripping
checkpoint-status | 76515eb7-ae3b-4590-8ca3-e1edab0cf240 |  | checkpoint | Louvre has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
checkpoint-group | 0b4c7f67-00e3-44ce-bdb9-13d14ad4c81a |  | section | CPB Sign Off (Part 2):
checkpoint-status | 9dfda7eb-855a-4de0-ba10-dbc7c5a3fcbb |  | checkpoint | CPB to complete final checks & sign-off unit
holdpoint | feca88ca-9162-474d-9f82-fd5112980ea9 |  | signoff | CPB HOLDPOINT
checkpoint-group | 8a9de0c8-d048-4def-9e65-cc5e6d4e9a59 |  | section | Final Sealant
checkpoint-status | 0571de78-0de3-4440-9fa3-291533da98cf |  | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
checklist-sectioned | a709390b-4ed6-47df-9e56-ce5b205d9e01 |  | checklist | Partition Lining ITP |  |  |  |  | Yes | Partition Lining ITP V2 | c6ff9560-a5a8-4b6e-9184-cf98d7e89637
checkpoint-group | dc459b33-d22a-4643-8207-2fc618299e21 |  | section | Board Lining
checkpoint-status | 4a95412f-9c46-4983-87e0-a5c07b2a3c65 |  | checkpoint | Area ready & accessible
label | 1d7fe3f8-0a75-5f5e-85c1-893f8a653b6e |  | note | 1400 Series & USG BORAL Specifications
checkpoint-status | e985c137-1cac-4db3-9ac0-7c214809a279 |  | checkpoint | Inspect the sheeting of walls as per BORAL specification & checklist below
checkpoint-status | 440a1416-544f-4812-b778-e3eba520b19d |  | checkpoint | Run sheets across the framing members (refer BORAL standard details)
checkpoint-status | 4452f96d-1353-44b8-be73-e9935a9f8183 |  | checkpoint | Stagger end joints in a brick pattern & locate them on framing members away from the corners of large opening
checkpoint-status | 0d4c8d25-a3c3-4e1f-b551-4849d4518899 |  | checkpoint | Achieve level of finish as specified in the material, component & finishes schedule (Sec 4.2)
checkpoint-status | 6855c3cb-589d-43e1-9072-5e742884907a |  | checkpoint | Multiple sheet layers: Fill & flush up all joints & fixings in each layer & caulk up perimeters & penetrations before commencing succeeding layers
checkpoint-status | 28d67939-0c70-4af6-8e6b-545395fe3d64 |  | checkpoint | Stagger all sheet joints by minimum 200mm
checkpoint-group | 1ff67000-b4c3-460c-affe-bf28bf0d0905 |  | section | Doors & Internal Windows
checkpoint-status | 6690d30d-bb71-4e78-8802-f4aaaed12e83 |  | checkpoint | Doors & internal window opening: check door schedule, window schedule & kit of parts
checkpoint-status | e48487bd-8f08-4c93-8d63-c8bb0f1055fe |  | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
checkpoint-status | b1577c20-986a-4e4d-9d89-41b6531ab863 |  | checkpoint | Butt joints: Provide perforated paper reinforcing tape
checkpoint-status | 780c4a39-690f-4b5d-b0e8-ef2b709a55db |  | checkpoint | External corners: Provide matching purpose made beads
checkpoint-status | a792f733-21f2-4bf9-b183-87712282334b |  | checkpoint | Internal corners: Provide paper tape & bedding compound
checkpoint-status | 930dda9f-a7ba-4ab8-9cdb-016ca596eb66 |  | checkpoint | Provide sealants at junctions between partition systems & with other building elements
checkpoint-status | cf0b2d6e-d070-425c-85a0-0995cf620c31 |  | checkpoint | Provide trim such as beads, moulding & stops to make neat junctions between lining components, finishes & adjacent surfaces
checkpoint-group | 48f3ca6b-b2e0-4458-81b0-c4db3d415dec |  | section | Fire Walls
checkpoint-status | 28e5c44a-2140-4a85-a40b-e6f466b083cf |  | checkpoint | 1st Fix - Installed as per BORAL design & install specification
checkpoint-status | f7fca3e1-7a8b-4676-b675-f9f6bb7540d8 |  | checkpoint | Council/Holmes Inspection of first fix (if required)
checkpoint-status | 35d58bf1-315e-4754-956f-3da89ceda357 |  | checkpoint | 2nd Fix - Installed as per BORAL design & install specification
checkpoint-status | 54fa40df-4ac2-4221-9581-83a4389fc52a |  | checkpoint | Council/Holmes Inspection of second fix (if required)
checkpoint-status | a51dde57-0c7b-44a9-9ec3-f1dffef122be |  | checkpoint | Correct FRL achieved
checkpoint-status | 551d294f-ba01-43d2-8e8b-a453ccec9259 |  | checkpoint | Deflection heads & all joints sealed, taped & set (fire sealant is approved prior)
checkpoint-status | 19366fe9-1a64-473d-8f17-377c70d4e18e |  | checkpoint | All penetrations through fire walls below & above ceiling protected/sealed
checkpoint-group | 5bbe2842-9a69-4f51-9751-68933ff4f7ac |  | section | Smoke Walls
checkpoint-status | cff7a502-c04a-46ff-9637-9920e8c3d2d3 |  | checkpoint | 1st Fix - Installed as per BORAL design & install specification
checkpoint-status | c80550b5-d6ef-42d4-a038-83fcb01e365e |  | checkpoint | Council/Holmes Inspection of first fix (if required)
checkpoint-status | 3dd4b1f3-d5e3-4534-bd37-b194c4735af6 |  | checkpoint | 2nd Fix - Installed as per BORAL design & install specification
checkpoint-status | aacb6793-0da4-4155-86c2-ec26bebc6917 |  | checkpoint | Council/Holmes Inspection of second fix (if required)
checkpoint-status | 1e2fd878-8fd8-49bb-8ded-6ba8f832872b |  | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
checkpoint-status | c9556ddd-1ed3-4e09-91d8-0f0e3a916671 |  | checkpoint | All penetrations through smoke walls below & above ceiling protected/sealed
checkpoint-group | 29362e10-a840-4171-bed2-e4d459e53602 |  | section | Acoustic Walls
checkpoint-status | 6e560a94-7a85-4f29-8af3-13f4dcffc7e8 |  | checkpoint | Installed as per BORAL design & install specification.
checkpoint-status | 0d5ba871-1363-4446-b54d-0570ab6d72d7 |  | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
checkpoint-status | e017d0cd-d537-42c8-b12d-88fca0d30f86 |  | checkpoint | All penetrations through acoustic walls below & above ceiling protected/sealed
checkpoint-group | 938e29e1-f39d-421d-9643-8c72c232398d |  | section | Sign Offs
checkpoint-status | 90a0f360-4d43-4135-b1f1-c8a5a24a4b8b |  | checkpoint | Wadsworth final sign off - add signature
checkpoint-status | 15e91fa1-36dc-40dd-b9b1-2ced8a8d5519 |  | checkpoint | CPB final sign off - add signature
checklist-sectioned | 4cbe5940-170d-4935-b20f-cae955dc5fe3 |  | checklist | Ceiling Framing ITP |  |  |  |  | Yes | Ceiling Framing ITP | d384a906-07e6-4214-9a6b-517a88c0e438
checkpoint-group | c7493462-d6bd-4a4c-8dd7-ef81351db250 |  | section | Prior to Commencement – The following documentation completed and approved
checkpoint-status | 8c697c39-27f7-48c9-a079-1d6ddbda46ec |  | checkpoint | Area accessible & ready
checkpoint-status | 4386d80e-6869-4d5f-a99f-6c6614dd2594 |  | checkpoint | Structural design, documentation and certification for framed ceiling and bulkheads
checkpoint-status | e3a35b1c-729c-4e7b-8917-01c9af6d9e24 |  | checkpoint | Shop drawings submitted and approved
checkpoint-status | eddb8fef-8380-4e45-bdfb-987872517f9d |  | checkpoint | Samples and prototypes submitted and approved (Fire sealants approved)
checkpoint-status | 6c1554e2-0468-4789-b5bb-68fa2c90b5f0 |  | checkpoint | Test results of prototypes submitted (section 1.19)
checkpoint-group | ef2fede1-a1e2-4d5e-943f-d68312f07a48 |  | section | Set out
checkpoint-status | bf7a46e3-e2fa-4d75-888b-8a4b257ea977 |  | checkpoint | Reflected ceiling plans current revisions checked and ceiling set out completed as per the current plans
checkpoint-group | 4d6fc46a-f352-484b-9f39-3f5bd4732e68 |  | section | Construction Generally
checkpoint-status | 6aea7b41-9208-471d-9d4f-497871ba3ad9 |  | checkpoint | Install & fix to prevent looseness or rattling of ceiling components
checkpoint-status | 3bd306c7-b734-4282-a7ec-1987ecc09a19 |  | checkpoint | Ceiling systems do not amplify structural-borne sounds.
checkpoint-status | b8f74a2c-b814-417c-a70c-d365ff81bafc |  | checkpoint | Install the ceiling to allow for differential movement at abutting surfaces
checkpoint-status | 3fa8dfa6-275f-43b8-9c7b-05b4d3e4ded3 |  | checkpoint | Post tensioned concrete: Minimum embedment for fixing: 45mm and minimum clearance of fixing from any tendon: 25mm
checkpoint-group | e2b0cb28-c7a0-4453-8371-cb9f579aa532 |  | section | Construction – Suspension system
checkpoint-status | f81b8515-4ec2-4bd3-bfc5-3fc15611bb2a |  | checkpoint | Provide suspension system and workmanship as per supplier installation guides.
checkpoint-status | 06daa44f-f0d0-41a7-9af5-46302f799aab |  | checkpoint | Services: Do not fix to the installed services
label | cb813e2e-8166-5271-813c-4968f9d6f030 |  | note | Where services obstruct the ceiling supports, provide bridging and suspension on each side of the services
label | 2c3e1ae9-ce65-5167-9dce-1b7516bfcf18 |  | note | Provide additional back support or suspension members to prevent distortion, overloading or excessive vertical deflection.
checkpoint-status | 861b6fb9-f8b8-4823-83d6-87c613af75cf |  | checkpoint | Ensure that the failure of any one suspension point does not cause a progressive failure of the ceiling.
label | 7d9daee3-452d-552f-a501-b0225afae07b |  | note | Provide height adjustment with a length adjustment device at each suspension point, permitting length variation of at least 50mm
label | 9f8bcb87-e275-5ea4-9662-a9b1e35096d1 |  | note | Seismic resistant: Provide bracing and clips to framing members to prevent lateral movement and to resist seismic action.
label | 1e0e35f7-cdd7-57d8-9637-6b1b954167b1 |  | note | Do not provide visible fixings (screws or rivets) where they will be exposed to view.
checkpoint-status | e4ed57fe-870d-49a4-a434-7042a4dedc94 |  | checkpoint | Uplift: Suspension system and framing to resist uplift.
label | 19d0c07d-90d3-5d69-a0fc-a7d23d379ad2 |  | note | Tolerances: Flatness, twist, winding and bow: 1.5mm deviation from a 1.5m straightedge places in any position
checkpoint-group | e5bf3530-b06a-4de3-8818-7901f984687e |  | section | Hold Point
checkpoint-status | fcb62ad7-ddd8-4cb9-baae-7056d501c216 |  | checkpoint | Suspension system completed – Ready for installation of ceiling tiles, lining and panels.
checkpoint-status | 6bc976ef-a184-4b62-8544-315f9e599708 |  | checkpoint | Confirm all service trades are complete & ready for closing in of ceilings.
checkpoint-group | 3d891320-9560-4a06-87f5-9f2141354047 |  | section | Bulkheads
checkpoint-status | 951303dc-25c9-4972-a396-1c534b22c4b6 |  | checkpoint | Integrate bulkheads with the ceiling structure and brace to prevent lateral movement. Where ceiling is terminated at the bulkhead, provide for seismic requirements
checkpoint-group | 9c152176-7ca5-423d-b157-74e73eaa1ce2 |  | section | Smoke baffles and acoustic baffles
checkpoint-status | 438a287f-2029-4e51-9951-b3556ae87f0d |  | checkpoint | Provide approved smoke and acoustic baffles secured fixed to metal angles and smoke sealed at board joints and to adjoining building elements
checkpoint-group | ec31beb7-3750-4c2a-aef5-b12c40a74dfd |  | section | BVT Engineering Inspection
checkpoint-status | de20b477-dd04-45cb-9e49-9e77566a49db |  | checkpoint | BVT to complete construction monitoring on ceilings, in line with Rondo PS1 and provide report.
checkpoint-status | 393fb255-4e25-48ce-ad8c-394734b76eb9 |  | checkpoint | BVT to complete in depth sign-off sheet for all ceilings once engineering & construction is confirmed.
checkpoint-status | cae2f248-79fa-45be-a944-117bfdf4d27d |  | checkpoint | Include sign off sheet & register with ITP
checkpoint-group | c50bdc52-0248-4016-9ceb-c0e464260262 |  | section | Acoustic installation
checkpoint-status | ef196022-4e08-40f6-bdf5-710564efdf45 |  | checkpoint | Place mineral fibre batts on top of ceilings system and butt to each other and to partitions.
checkpoint-status | 8bd3df4b-e043-458f-a7ea-e56ff21c5733 |  | checkpoint | Tightly butt and trim neatly around services items and other items
checkpoint-status | 5869fab8-071e-4074-a626-54aca6d1cc8b |  | checkpoint | CPB final sign off - add signature