## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Subgrade Preparation Rev2 | itp |  |  |  |  | ITP-001 - Subgrade Preparation Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 1.3 Selection and approval of disposal site
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements and in accorance with Yarra Trams site classification report.
label | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the authorities controlling disposal of material at that location.
label | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 2.2 Reinstatement of bonds
label | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
label | ○ All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 2.3 Inspection of subgrade material
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the standard.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams, Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Width and level conformity
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
label | ○ No point in the general surface shall vary more than 12mm from a 3m straight edge.
label | ○ Finished formation widths shall not vary more than -0 mm, +50mm from dimensions shown on the drawings
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | IP
label | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: