## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-006 - Track Placement Rev3 | itp |  |  |  |  | ITP-006 - Track Placement Rev3
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Check materials
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
label | ○ Check condition of rail sleepers
label | ○ Ensure rail jewellery is of sound condition
label | REFERENCE DOCUMENTS: AS 1085
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Client, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check special works components
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
label | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Check curved rail
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
label | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Welders qualifications
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails
label | ○ TLIW3015 Weld Rails using Aluminothermic welding process
label | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.6 Ultrasonic testers qualifications
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
label | ○ Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Installation of sleeper
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
label | ○ Dual block sleepers shall also comply with the design offsets at each chainage
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Placement of rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
label | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
label | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
label | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
label | ○ Geometry tolerances as follows:
label | – Centreline location: +/- 3mm
label | – Level: +/- 3mm
label | – Line measured (>10m chord): +/- 3mm
label | – Twist (3.5m chord): +/- 2mm
label | – Cant: +/- 3mm
label | – Gauge (open track): +3mm, -0mm
label | – Gauge,Turnouts (opposite crossings):+2, -0mm
label | – Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Cant shall be applied uniformly over transitions
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completion of track charts
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Placement of jewellery
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
label | ○ Clips shall be installed with panpuller or equivalent
label | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Rail end preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
label | ○ Minimum closure length from proximity of welds shall be 2m
label | ○ Rail end conditions shall match (i.e flame cut - flame cut)
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Welding of rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Joints shall be square across the track
label | ○ Maximum skew at square joints shall be 65mm
label | ○ Portions shall match rail type (i.e HHR, Ordinary)
label | ○ Welds shall not be within:
label | 3m of another weld
label | 3m of a rail end
label | 1.5m of a glued insulation joint assembly
label | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
label | ○ Weld Return forms shall be completed by qualified welder
label | ○ Welds shall be grinded after 1 hour
label | ○ Welds shall be free of water
label | ○ Post grinding, welds shall be cleaned for visual inspection
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Grinding & cleaning welds
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
label | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
label | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Track adjustment
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer.
label | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
label | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.8 Track bonds
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
label | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Track testing
label | FREQUENCY: Track testing
label | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
label | ○ Failed welds shall be cut out and replaced
label | ○ Testing documentation shall be recorded and supplied to the superintendent
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer/NDT
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: