## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-019 - Line Marking Rev3 | itp |  |  |  |  | ITP-019 - Line Marking Rev3
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Position of Markings
label | FREQUENCY: Prior to application
label | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
label | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Tolerance of Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Raised Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
label | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: