## Enabling Works
Local Board Projects
Site Location |  |  | 81 Saddleback Rise
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Materials
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every site | Type 1 Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5 | In process Inspection | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
2.1 | Euro Kerbs | QA FORM | TDM Technical Standards - KC0002 | Every site | Type 8 Kerb to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5 | In process Inspection | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | FH concrete QA sheet | Site Engineer
CIVIL WORKS
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish. Saw cut for every 3m and at joints. Crossfall 2% preferred (Min 1% and Max 3%) | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5 | Tactiles | Visual | TDM Technical Standards - FP0010 | Each PX | Warning TGSI tiles should have 100mm concrete slab underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5.1 |  |  | NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | In process Inspection | Photos | Site Engineer
5.2 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep. | In process Inspection | Photos | Site Engineer
5.3 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing | In process Inspection | Photos | Site Engineer
6 | Pram Crossing | QA FORM | TDM Technical Standards - FP006 | Each Crossing | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 40mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | Inprocess Inspection | Photos | Site Engineer
7 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer
RAMM DATA
8 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | As built records | Supervisor and Engineer
9 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Divnish Chand | Initial | DC |  | Date: | 2025-06-10
Approving Delegate |  | Sumesh Sharma | Initial | SS |  | Date: | 2025-06-11

## Concrete Speedtable
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Local Board Projects |  | FH Engineer |  | DC
|  |  |  | Procedure: | Raised Speed Table |  | FH Manager |  | SS
Inspection & Test Plan / Checklist
Detailed Location |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
81 Saddleback Rise
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer/MSQA Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed | Prior to commencement | Document Review | Signed Subcontractor and Supplier Agreements | Subcontract and Supplier Agreements | Site Engineer
2.1 |  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by CAR manager for each site and works are only completed within the approved dates.. | TMP on MyWorksites/On Site | Site Engineer
2.2 |  | H | Ensure all Sub-Contractors and Suppliers go through FH induction | On site daily | Induction | Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation | Hazard ID and Pre-starts to safety team | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Prior to commencement | Document Review | IFC drawings have been received by Contractor | Check Drawing Register | Site Engineer | Design Engineer
4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control in place | Prior to commencement | Visual Inspection | Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | Environmental Controls Audit | Environmental Manager/Site Engineer
5 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey + Smart Level | Consistency with Construction Drawing | Site Photos post surveying | Site Engineer
6 | Locate Existing Services by Hand Digging | H | Ensure all services conflicting with the line of trench has been exposed by hand digging | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | Digging and excavation checklist, service planes,As-Built Drawings Doc. Review | Site Engineer
7 | Material Compliance | H | LESA dowels to be used at all construction joints at 600mm clearance | Prior to pouring concrete | Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.1 |  | H | 0.25mm polythene layer placed across all surface area at bottom of raised table | Prior to pouring concrete | Visual Inspection, Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.2 |  | H | 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer. | Prior to pouring concrete | Visual Inspection | CIV >15 | Delivery Dockets | Site Engineer
7.3 |  | H | Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating. | Prior to pouring concrete | Visual Inspection | Photos | Photos
7.4 |  | H | All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder | Prior to pouring concrete | Concrete Delivery Dockets | Delivery Docket added to QA folder | Concrete Delivery Dockets | Site Engineer
8 | Temporary Works (Formwork) | W | Formwork to be set to correct line and level | Prior to pouring concrete | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.1 |  | H | Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15) | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.2 |  | H | Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.3 |  | H | Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp with broom finish. Toe to be 1.5m across for both entry and will be exposed concrete finish. | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.4 |  | H | Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road | Prior to pouring concrete | Measurement | Designer to inspect gradient level | Site photos / Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.5 |  | H | The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
9 | Reinforcing | H | All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @300mm centres placed across the construction joint | Prior to pouring concrete | Measurement | Concrete Inspection Record | Site photos/Concrete Formwork Checklist | Site Engineer | MSQA Engineer
10 | Concreting | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection | Engineer will be notified via email/SMS at least 24 hours before required for inspection | Email / SMS | Site Engineer
10.1 |  | W | Vibrator to be used throughout concrete pour | When pouring concrete | Visual Inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
10.2 |  | H | Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top. | At completion of pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
11 | Curing | M | Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. | Post Pour | Monitoring the time allowed for curing | 48 hours minimum have passed | Concrete Formwork Checklist | Site Engineer
12 | Remove formwork | W | Remove formwork after 48 hours | Post Curing | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
13.1 | Asphalt- Concrete extension slab/ Toe | H | 225mm thick 40MPa Concrete with two layers of 663 mesh | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer
13.2 | AC Surfacing or Asphalt reinstatement extent | W | Mill existing as per survey setout. No exposed subgrade. Pavement thickness to be 35mm to 60mm or match with existing. Compacted granular base with CIV>35 | Post excavation | Visual inspection | Photos + Clegg + Scalar for exposed subgrade | Site photos | Site Engineer
13.3 | Asphalt Reinstatement | W | 35mm to 60mm thick AC10 on compacted granular base with tack coat | Prior to laying Asphalt | Inspection/Measurement | Photos + Delivery Docket added to QA folder | Site photos,delivery dockets | Site Engineer
14 | Lot Number QA File | W | Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file | At completion of Lot | Document Review | All QA files compiled and sumbitted to client | QA records | Site Engineer
14.1 |  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review | Delivery Dockets to be included in QA file | QA records | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer

## Signage
ITP - Saddleback Rise
Site Location |  |  | 81 Saddleback Rise
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Every site | All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA FORM | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4a | Ground Socket | QA FORM | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
4b | Pole and Impact recovery post | QA FORM | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
5 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Each Sign | All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately. | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
6 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Divnish Chand | Initial | DC |  | Date: | 2025-06-10
Approving Delegate |  | Sumesh Sharma | Initial | SS |  | Date: | 2025-06-11