## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Saddleback Rise - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - Saddleback Rise - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Type 1 Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2.1 - Euro Kerbs
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Type 8 Kerb to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish. Saw cut for every 3m and at joints. Crossfall 2% preferred (Min 1% and Max 3%)
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Each PX
label | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.1 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.2 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.3 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Pram Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | FREQUENCY: Each Crossing
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Tactiles Directional & warning - 40mm; 600mm flares; width as per design;
label | ○ Slope no greater than 1:12 where practicably possible
label | ○ Clegg CIV > 12
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | RAMM DATA
checkpoint | 8 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: As built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 9 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma
checklist | ITP - Saddleback Rise - Raised Speed Table | itp |  |  |  |  | ITP - Saddleback Rise - Raised Speed Table
section | Raised Speed Table
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS: Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | RECORDS: TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
label | FREQUENCY: On site daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
label | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | RECORDS: Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Erosion & Sediment Control in place
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | RECORDS: Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
label | CONFORMANCE CRITERIA: Consistency with Construction Drawing
label | RECORDS: Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: LESA dowels to be used at all construction joints at 600mm clearance
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: CIV >15
label | RECORDS: Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Photos
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
label | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
label | RECORDS: Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Formwork to be set to correct line and level
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 8.1 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp with broom finish. Toe to be 1.5m across for both entry and will be exposed concrete finish.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect gradient level
label | RECORDS: Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @300mm centres placed across the construction joint
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | RECORDS: Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Concreting
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Vibrator to be used throughout concrete pour
label | FREQUENCY: When pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 10.2 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | FREQUENCY: At completion of pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | FREQUENCY: Post Pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
label | CONFORMANCE CRITERIA: 48 hours minimum have passed
label | RECORDS: Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Remove formwork after 48 hours
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 225mm thick 40MPa Concrete with two layers of 663 mesh
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 - AC Surfacing or Asphalt reinstatement extent
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Mill existing as per survey setout. No exposed subgrade. Pavement thickness to be 35mm to 60mm or match with existing. Compacted granular base with CIV>35
label | FREQUENCY: Post excavation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Photos + Clegg + Scalar for exposed subgrade
label | RECORDS: Site photos
checkpoint | 13.3 - Asphalt Reinstatement
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: 35mm to 60mm thick AC10 on compacted granular base with tack coat
label | FREQUENCY: Prior to laying Asphalt
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Inspection/Measurement
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos,delivery dockets
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
label | RECORDS: QA records
checkpoint | 14.1 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Delivery Dockets to be included in QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
label | RECORDS: QA records
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Red pen mark up drawings to be included in QA file
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | RECORDS: Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - Saddleback Rise - Signage | itp |  |  |  |  | ITP - Saddleback Rise - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 4a - Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4b - Pole and Impact recovery post
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Post or pole
label | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation.
label | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma
checklist | ITP - Torbay Kindergarten - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - Torbay Kindergarten - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Each PX
label | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.1 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.2 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.3 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | RAMM DATA
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: As built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma
checklist | ITP - Torbay Kindergarten - Traffic Islands | itp |  |  |  |  | ITP - Torbay Kindergarten - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infil
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma