## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Saddleback Rise - Concrete Speedtable | itp |  |  |  |  | ITP - Saddleback Rise - Concrete Speedtable
section | Raised Speed Table
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS: Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | RECORDS: TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
label | FREQUENCY: On site daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
label | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | RECORDS: Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Erosion & Sediment Control in place
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | RECORDS: Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
label | CONFORMANCE CRITERIA: Consistency with Construction Drawing
label | RECORDS: Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: LESA dowels to be used at all construction joints at 600mm clearance
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: CIV >15
label | RECORDS: Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Photos
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
label | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
label | RECORDS: Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Formwork to be set to correct line and level
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 8.1 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp with broom finish. Toe to be 1.5m across for both entry and will be exposed concrete finish.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect gradient level
label | RECORDS: Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @300mm centres placed across the construction joint
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | RECORDS: Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Concreting
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Vibrator to be used throughout concrete pour
label | FREQUENCY: When pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 10.2 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | FREQUENCY: At completion of pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | FREQUENCY: Post Pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
label | CONFORMANCE CRITERIA: 48 hours minimum have passed
label | RECORDS: Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Remove formwork after 48 hours
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 225mm thick 40MPa Concrete with two layers of 663 mesh
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 - AC Surfacing or Asphalt reinstatement extent
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Mill existing as per survey setout. No exposed subgrade. Pavement thickness to be 35mm to 60mm or match with existing. Compacted granular base with CIV>35
label | FREQUENCY: Post excavation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Photos + Clegg + Scalar for exposed subgrade
label | RECORDS: Site photos
checkpoint | 13.3 - Asphalt Reinstatement
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: 35mm to 60mm thick AC10 on compacted granular base with tack coat
label | FREQUENCY: Prior to laying Asphalt
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Inspection/Measurement
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos,delivery dockets
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
label | RECORDS: QA records
checkpoint | 14.1 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Delivery Dockets to be included in QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
label | RECORDS: QA records
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Red pen mark up drawings to be included in QA file
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | RECORDS: Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT