## Project Structure
St Johns. Summerset.
Mulcahy Manufacturing
Block A
Level 4
Apt401
Mulcahy - Frame Checks
Apt 402
Mulcahy - Frame Checks
Apt 403
Mulcahy - Frame Checks
Apt 404
Mulcahy - Frame Checks
Apt 405
Mulcahy - Frame Checks
Apt 406
Mulcahy - Frame Checks
Apt 407
Mulcahy - Frame Checks
Apt 408
Mulcahy - Frame Checks
Apt409
Mulcahy - Frame Checks
Apt 410
Mulcahy - Frame Checks
Apt 411
Mulcahy - Frame Checks
Apt 412
Mulcahy - Frame Checks
Apt 413
Mulcahy - Frame Checks
Level 5
Apt 501
Mulcahy - Frame Checks
Apt 502
Mulcahy - Frame Checks
Apt 503
Mulcahy - Frame Checks
Apt 504
Mulcahy - Frame Checks
Apt 505
Mulcahy - Frame Checks
Apt 506
Mulcahy - Frame Checks
Apt 507
Mulcahy - Frame Checks
Apt 508
Mulcahy - Frame Checks
Apt 509
Mulcahy - Frame Checks
Apt 510
Mulcahy - Frame Checks
Apt 511
Mulcahy - Frame Checks
Apt 512
Mulcahy - Frame Checks
Apt 513
Mulcahy - Frame Checks
Belcanto Manufacturing
Block A
Level 4
Apt 401
QA - Belcanto - Manufacturing Checklist
Apt 402
QA - Belcanto - Manufacturing Checklist
Apt 403
QA - Belcanto - Manufacturing Checklist
Apt 404
QA - Belcanto - Manufacturing Checklist
Apt 405
QA - Belcanto - Manufacturing Checklist
Apt 406
QA - Belcanto - Manufacturing Checklist
Apt 407
QA - Belcanto - Manufacturing Checklist
Apt 408
QA - Belcanto - Manufacturing Checklist
Apt409
QA - Belcanto - Manufacturing Checklist
Apt 410
QA - Belcanto - Manufacturing Checklist
Apt 411
QA - Belcanto - Manufacturing Checklist
Apt 412
QA - Belcanto - Manufacturing Checklist
Apt 413
QA - Belcanto - Manufacturing Checklist
Level 5
Apt 501
QA - Belcanto - Manufacturing Checklist
Apt 502
QA - Belcanto - Manufacturing Checklist
Apt 503
QA - Belcanto - Manufacturing Checklist
Apt 504
QA - Belcanto - Manufacturing Checklist
Apt 505
QA - Belcanto - Manufacturing Checklist
Apt 506
QA - Belcanto - Manufacturing Checklist
Apt 507
QA - Belcanto - Manufacturing Checklist
Apt 508
QA - Belcanto - Manufacturing Checklist
Apt 509
QA - Belcanto - Manufacturing Checklist
Apt 510
QA - Belcanto - Manufacturing Checklist
Apt 511
QA - Belcanto - Manufacturing Checklist
Apt 512
QA - Belcanto - Manufacturing Checklist
Apt 513
QA - Belcanto - Manufacturing Checklist
Belcanto Installation.
Block A
Level 4
Apt 401
QA - Belcanto - Installation Checklist
Apt 402
QA - Belcanto - Installation Checklist
Apt 403
QA - Belcanto - Installation Checklist
Apt 404
QA - Belcanto - Installation Checklist
Apt 405
QA - Belcanto - Installation Checklist
Apt 406
QA - Belcanto - Installation Checklist
Apt 407
QA - Belcanto - Installation Checklist
Apt 408
QA - Belcanto - Installation Checklist
Apt409
QA - Belcanto - Installation Checklist
Apt 410
QA - Belcanto - Installation Checklist
Apt 411
QA - Belcanto - Installation Checklist
Apt 412
QA - Belcanto - Installation Checklist
Apt 413
QA - Belcanto - Installation Checklist
Level 5
Apt 501
QA - Belcanto - Installation Checklist
Apt 502
QA - Belcanto - Installation Checklist
Apt 503
QA - Belcanto - Installation Checklist
Apt 504
QA - Belcanto - Installation Checklist
Apt 505
QA - Belcanto - Installation Checklist
Apt 506
QA - Belcanto - Installation Checklist
Apt 507
QA - Belcanto - Installation Checklist
Apt 508
QA - Belcanto - Installation Checklist
Apt 509
QA - Belcanto - Installation Checklist
Apt 510
QA - Belcanto - Installation Checklist
Apt 511
QA - Belcanto - Installation Checklist
Apt 512
QA - Belcanto - Installation Checklist
Apt 513
QA - Belcanto - Installation Checklist

## Resources
checklist | Belcanto - Manufacturing Checklist | Per Balcony
section | Soffit Check
checkpoint | Rivet sizes
label | As per assembly diagram
label | Visual Check
label | Frequency: Every Rivet
checkpoint | Rivet integrity
label | Ensure rivets are pulled up tight
label | Visual Check
label | Frequency: Every Rivet
checkpoint | Joints tight
label | All soffit panels pulled tight to each other with siliconed joints
label | Visual Check
label | Frequency: Every Soffit Panel
checkpoint | Z Brackets
label | Ensure Z Brackets Installed corectly
label | Visual Check
label | Frequency: Every Z Bracket
checkpoint | Promate Board
label | Ensure PromateBoard Installed Correctly
label | Visual Check
label | Frequency: Every Promate Board
checkpoint | Surface finish
label | No imperfections visible beyond 3m
label | Visual Check
label | Frequency: Every Soffit Panel
section | Balustrade (including Fascia) Check
checkpoint | All parts fitted
label | As per drawings and schedules
label | Visual Check
label | Frequency: Every Balustrade
checkpoint | Surface finish
label | No imperfections visible beyond 2m
label | Visual Check
label | Frequency: Every Balustrade
checkpoint | Supports added
label | Supports fitted to side balustrades
label | Visual Check
label | Frequency: Side Balustrades
checkpoint | Bolt tightness
label | Torque Wrench: M8 Bolts to 29Nm
label | Mark thread with 'torque mark' as visual indicator
label | Frequency: Every Bolt
checkpoint | Fascia secure
label | All fixings present and well secured
label | Visual Check
label | Frequency: Every Fascia
checkpoint | Handrail secure
label | All fixings present and well secured
label | Visual Check
label | Frequency: Every Handrail
section | Flooring Check
checkpoint | Connection points accessible
label | All connection points (clamps, sprinkler, vents, etc.) accessible via access panels
label | Visual Check
label | Frequency: Every Balcony
checkpoint | Decking Screws Teightened
label | All decking screws tightened properly
label | Phycial Check
label | Frequency: Every Screw
Ceckpoint | Decking Defects
Label | No Defects in the Stabiwood
label | Visual Check
label | Frequency: Every Board
section | Completion Check
checkpoint | Fascia protection applied
label | All fasciae are protected by stretchwrap
label | Visual Check
label | Frequency: Every Balcony
checkpoint | Handrail/capping protection applied
label | All handrail/capping protected by low-tack tape
label | Visual Check
label | Frequency: Every Balcony
checkpoint | Paving restraint
label | Pavers restrained from transport movement by strapping plywood over top
label | Visual Check
label | Frequency: Every Balcony
checkpoint | Lifting slings inserted correctly
label | In accordance with slinger training
label | Visual Check
label | Frequency: Every Balcony
checkpoint | Site pack compiled
label | Site pack includes fixings, cut slabs, side fasciae, post cladding and any other site required parts
label | Visual Check
label | Frequency: Every Balcony
Section | Balcony Installation
Checkpoint | Packers in place
checkpoint | Balcony Level
checkpoint | Clamps Tighetened
checkpoint | Anti Slip Bracket Installed
Checkpoint | Remainder of Decking Installed
checkpoint | Any PC defects touched up
checklist-flat | Mulcahy - Frame Checks
checkpoint | Verify barcode label has been stuck in place
label | Well adhered with no wrinkles or bubbles
checkpoint | Frame squareness
label | Measure Diagonals and compare
label | Diagonals to match +/- 2mm
checkpoint | Verify all parts have been fitted as drawings and schedules
checkpoint | Bolt tightness
label | Torque Wrench: M8 Bolts to 29Nm
label | Mark thread with 'torque mark' as visual indicator