## HB AWPT-Material Testing
HAWKE'S BAY NOC - INSPECTION TEST PLAN - MATERIAL TESTING
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | TASK TIMING OR MINIMUM TASK FREQUENCY | TASK ASSIGNED TO | MEASURING DEVICES OR METHOD | CRITERIA | QA Form | TESTING RECEIVED | COMPLIANT
CONSTRUCTION PROGRAMME
Prepare & submit programme, ensure appropriate construction timeframe |  |  | Prior to start of construction | Project Engineer |  | Complies with agreed (Higgins & NZTA) programmed works timeframes
Weekly progress reports |  |  | By 4pm on the Monday of the following week | Project Engineer |  | Summary of works completed, summary of QA testing completed, record of inclement weather days, updated construction programme
TEMPORARY TRAFFIC MANAGEMENT
Ensure appropriate TMP used | HB NOC Generic TMP's with a site specific TMP for this project | Check with TMC that appropriate TMP is selected | As per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms | Project Engineers/STMS/Site Foreman |  | As per TMP and ensure TMC advised in advance of works. | On site records
SERVICES LOCATION AND PROTECTION
Services location confirmation |  |  | Prior to start of construction. Power Authority overhead power lines. Chorus underground cables - including fibre optic. Chorus contact person is Nick.vanDruten@chorus.co.nz phone 027 4412119. Wairoa DC Water, Sewer, Stormwater. | Project Engineer |  | Services locations marked on site. Standover requirements identified.
DRAINAGE
BASECOURSE MATERIAL TESTING
Approved Aggregate | TNZ M/4 Table 4 | Grading | 1 independent test per 500m3, prior to basecourse placement | IANZ accredited laboratory | NZS 4407:2015, Test 3.8 | Napier River Gravel 78-100% 26.5mm 13-25% passing 1.18mm 10-19% passing 600µm 7-14% passing 300µm 5-11% passing 150µm 3-8% passing 75µm | QA Measurement Sheet
BITUMEN MANUFACTURE
Note: These tests are reproduced from NZTA M/1 for information only. A copy of current approval letter will be required for each grade and source of binder used on the project to verify the binder is approved.
Penetration | NZTA M/1 Table 1 | Penetration at 25°C, 100g, five seconds |  | IANZ accredited laboratory | ASTM D5
Viscosity | NZTA M/1 Table 1 | Viscosity PaS at 60°C |  | IANZ accredited laboratory | AS 2341.2 or ASM D2171 | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| NZTA M/1 Table 1 | Viscosity mm2/s at 135°C |  | IANZ accredited laboratory | AS 2341.3 or ASM D2170 | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
Flash Point | NZTA M/1 Table 1 | Flash point (Cleveland open cup), °C |  | IANZ accredited laboratory | ASTM D92 | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
Solubility | NZTA M/1 Table 1 | Solubility in Trichloroethlyene, % or Solubility in Toluene, % |  | IANZ accredited laboratory | ASTM D2042, AS 2341.8 | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
Penetration | NZTA M/1 Table 1 | Penetration of residue, at 25°C, 100g, five seconds, % of original. |  | IANZ accredited laboratory | ASTM D5 | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
NZTA Approved | NZTA M/1 5 | Letter from NZTA | 1 per source and grade of binder used | NZTA |  | Complies with requirements for penetration grade as per TNZ M/01 Table 1.
SEALING CHIP MATERIAL TESTING
Crushing Strength | NZTA M/6 3.2 | Crushing Resistance Test | Once per year - 1 test | IANZ accredited laboratory | NZS 4407:2015, Test 3.10 | <10% fines passing 2.36mm under 230kN load
Weathering Quality | NZTA M/6 3.3 | Weathering Quality Index Test | Once per year - 1 test | IANZ accredited laboratory | NZS 4407:2015, Test 3.11 | AA or BA
Weak Particles Test | NZTA M/6 3.4 | Australian Weak Particles Test | Only undertaken in case of dispute. | IANZ accredited laboratory | AS 1141.32-1995 | Maximum of 1%
Polished Stone Value | NZTA M/6 3.5 | Polished Stone Value Test | Once per year - 1 test | Accredited PSV Testing Agency | BS 812 : Part 114 | PSV Required = 53
Cleanliness | NZTA M/6 4.1.1. | Cleanliness Test | 1 test per 500m3 | IANZ accredited laboratory | NZS 4407:2015, Test 3.9 | Grade 3 - 87 min Grade 5 - clean & free of soft, weathered, disintegrated or deleterious material
Size & Shape | NZTA M/6 4.1.2. | Size & Shape | 1 test per 500m3 | IANZ accredited laboratory | NZS 4407:2015, Test 3.13 | Grade 3 - ALD 7.5 - 10.0, 70%Min within 2.5% ALD
Broken Faces | NZTA M/6 4.1.2. | Broken Faces Test | 1 test per 500m3 | IANZ accredited laboratory | NZS 4407:2015, Test 3.14 | 98% with minimum two broken faces
Grading | NZTA M/6 4.2.2. | Grading | 1 test per 500m3 | IANZ accredited laboratory | NZS 4407:2015, Test 3.8 | Grade 5 95-100% passing 9.5mm, 0-8% passing 4.75mm 0-2% passing 2.36mm