## HB AWPT-Rakaipaka A
HAWKE'S BAY NOC - INSPECTION TEST PLAN - Rakaipaka A
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | TASK TIMING OR MINIMUM TASK FREQUENCY | TASK ASSIGNED TO | MEASURING DEVICES OR METHOD | CRITERIA | QA Form | TESTING RECEIVED | COMPLIANT
CONSTRUCTION PROGRAMME
Prepare & submit programme, ensure appropriate construction timeframe |  |  | Prior to start of construction | Project Engineer |  | Complies with agreed (Higgins & NZTA) programmed works timeframes
Weekly progress reports |  |  | By 4pm on the Monday of the following week | Project Engineer |  | Summary of works completed, summary of QA testing completed, record of inclement weather days, updated construction programme
TEMPORARY TRAFFIC MANAGEMENT
Ensure appropriate TMP used | HB NOC Generic TMP's with a site specific TMP for this project | Check with TMC that appropriate TMP is selected | As per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms | Project Engineers/STMS/Site Foreman |  | As per TMP and ensure TMC advised in advance of works. | On site records
SERVICES LOCATION AND PROTECTION
Services location confirmation |  |  | Prior to start of construction. Power Authority overhead power lines. Chorus underground cables - including fibre optic. Chorus contact person is Nick.vanDruten@chorus.co.nz phone 027 4412119. Wairoa DC Water, Sewer, Stormwater. | Project Engineer |  | Services locations marked on site. Standover requirements identified.
DRAINAGE
PRELIMINARY/ ESTABILISHMENT
Estabilish TTM |  | Visual Inspection | AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms | STMS/Site Foreman | Visual | As per TMP and ensure TMC advised in advance of works. | Daily Diary
Permits | Permit to Work,Digging Check list (inc. locating services),Close approach permit | Document Review | Before Work begins(only if required) | Site Foreman | Visual | Obtain permits and mark outs prior to construction | Copy of Permit on site
Clear-Shoulder and Side drain |  | Visual Inspection |  | Project Engineers/Site Foreman | Visual |  | Daily Diary
Digout Failed Areas |  | Visual Inspection | As Requested | Project Engineers/Site Foreman | Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth. | Backfill with Basecourse | Daily Diary
INSPECTION TEST PLAN - IN SITU CEMENT STABILISATION
Cement for stabilisation | NZTA B/5:2008, 4.1.2 NZS 3122 | Certified in accordance with NZS 3122 | As per NZS 3122 Appendix E
Production plan | NZTA B/5:2008, 7.2.2 |  | 1 per site
Stabilisation mix properties (including cement): - Maximum dry density (MDD) - Optimum water conent (OWC) - Solid density (SD) | NZTA B/5:2008, 7.7 NZS 4402 Test 4.1.3 NZS 4407 Test 3.7.1 | Material properties for compaction verification | 1 per 5000m2 of material stabilised | Hold Point - Approval required by site engineer |  |  | QA Measurement Sheet
In-situ moisture content of existing pavement aggregate | NZTA B/5:2008, 7.5 NZS 4402 Test 41.3 | In-situ moisture content Between 90% to 100% of OWC | As required | Inspection - Lab |  |  | QA Measurement Sheet
Top-up metal | TNZ M/4 Table 4 | Placed to required depth and design levels | 20m intervals - Stringline | Site Foreman |  |  | QA Measurement Sheet
Cement spreading | NZTA B/5:2008, 7.3 - Mat test (1m2 canvas mat) - Average usage test | - Mat test ± 0.5 kg/m2 of specified rate; - Average usage ±2.5% of specified rate | - Every 400 m2 - Upon emptying spreader and bulk tanker | Inspection & sign off by Site Supervisor |  |  | QA Measurement Sheet
In-situ mixing - Cut depth | NZTA B/5:2008, 7.6.1 | Maximum variation -5mm and +15mm | - Every 200m along cut length at both ends of the drum | Inspection & sign off by Site Supervisor |  |  | QA Measurement Sheet
Compaction | NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3 | Plateau testing Mean value ≥ 98% of MDD Minimum value ≥ 95% of MDD | - 5 Randomly selected locations / lot - Lot size ≤ 1000m2 | Hold Point - Approval required by site engineer | Nuclear Densometer | Minimum value 95% of MDD | Test Reports
Surface shape | NZTA B/5:2008, 7.8 | - ≤10mm from 3-metre straight edge - No depression - Vertical variations -5 + 15mm | 20m intervals | Inspection & sign off by Site Supervisor | Stringing, Tape measure |  | QA Measurement Sheet
Crossfall | NZTA B/5:2008, 7.9 | Not less than exisitng crossfall at the start of construction | 20m intervals | Inspection & sign off by Site Supervisor | Stringing, Tape measure |  | QA Measurement Sheet
Surface finish | NZTA B/5:2008, 7.10 | See clause | 20m intervals | Hold Point - Approval required by site engineer prior to Sealing | Visual
* Normal Risk = < 5 x 106 ESA's (or< 500 HCV per lane per day)
** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
CHIPSEAL CONSTRUCTION (NZTA P29)
Ensure appropriate TMP used | Refer TEMPORARY TRAFFIC MANAGEMENT Section
Seal design |  |  | Prior to surfacing (HOLD POINT) | Project Engineer |  | Seal design to be reviewed prior to surfacing | Seal design template
Location/Size Confirmation |  | Mark up extent of chipseal | Prior to surfacing | Project Engineer |  |  | Daily Diary
Surface Cleanliness |  | Visual Inspection | Prior to application of binder | Site Foreman |  | To confirm that all loose material is removed from the surface and surrounding area. | QA Measurement Sheet
Plant Resource |  | Visual Inspection | Prior to start of Sealing | Site Foreman | Visual | Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.) | Daily Diary
Binder Application |  | Binder type, Cutback, Temp, Application rates | Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start. | Site Foreman/ Bitumen Sprayer Operator | Visual | Binder Type = 180/200. Cutback to suit 1st coat seal 4pph kero max. Temp = 150deg celcius min Application = Design l/m2, +/- 0.1 l/m2. | Bitumen Spray Sheets
Chip Application |  | Chip type Chip Application | Prior to application of chip and preferably prior to application of binder | Site Foreman | Visual | Trucks loaded with correct chip. Chip clean. (G4/6 Racked example) G4 application = windows big enough for 1-2 G6 chips to fall between G4. G6 application = Enough to just fill the voids around the G4. | QA Measurement Sheet
Compaction |  | Visual | At completion of rolling | Site Foreman | Visual | Ensure sufficient passes with roller to embed chip (typically 4-5 passes) | QA Measurement Sheet
Site Measure |  | Record final site measure | Completion of works | Site Foreman | Measuring Wheel or Tape | Sketch and record seal area and QA detail | QA Measurement Sheet
Post Seal Care |  | Visual inspection | 4 hours after Surfacing | Site Foreman | Visual | Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours. | Daily Diary
CHIP REMOVAL, PAVEMENT MARKING, TRAFFIC SERVICES
Removal of excess chip |  | Visual Inspection | Within 48 hours of surfacing | Project Engineers/Site Foreman | Visual | Ensure all excess chip removed from site. No chip windrows left on site in Shoulders. | Daily Diary
Pavement Marking |  | Visual Inspection | Within 48 hours of surfacing | Project Engineers/Site Foreman | Visual | Linemarking must be completed within 48 hours of surfacing. | Daily Diary
Removal of TTM |  | Visual Inspection | Within 48 hours of surfacing | Project Engineers/Site Foreman | Visual | All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed). | Daily Diary
Traffic Services |  | Visual Inspection | Within 48 hours of surfacing | Project Engineers/Site Foreman | Visual | Completed installation of all EMPs, RRPM's, Signs etc | Daily Diary