## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 0. HB AWPT ITP - Material testing | [5 empty] | 0. HB AWPT ITP - Material testing
section | Basecourse Material Testing
checkpoint | Approved Aggregate
label | Specification Reference - TNZ M/4 Table 4
label | Test Required - Grading
label | Task Timing / Minimum Task Frequency - 1 independent test per 500m3, prior to basecourse placement
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.8
label | Criteria - Napier River Gravel
label | ○ 78-100% 26.5mm
label | ○ 13-25% passing 1.18mm
label | ○ 10-19% passing 600µm
label | ○ 7-14% passing 300µm
label | ○ 5-11% passing 150µm
label | ○ 3-8% passing 75µm
label | QA Form - QA Measurement Sheet
section | Bitumen Manufacture
checkpoint-no-status | Note: These tests are reproduced from NZTA M/1 for information only. A copy of current approval letter will be required for each grade and source of binder used on the project to verify the binder is approved.
checkpoint | Penetration
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Penetration at 25°C, 100g, five seconds
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - ASTM D5
checkpoint | Viscosity (1)
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Viscosity PaS at 60°C
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - AS 2341.2 or ASM D2171
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint | Viscosity (2)
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Viscosity mm2/s at 135°C
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - AS 2341.3 or ASM D2170
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint | Flash Point
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Flash point (Cleveland open cup), °C
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - ASTM D92
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint | Solubility
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Solubility in Trichloroethlyene, % or Solubility in Toluene, %
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - ASTM D2042, AS 2341.8
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint | Penetration
label | Specification Reference - NZTA M/1 Table 1
label | Test Required - Penetration of residue, at 25°C, 100g, five seconds, % of original.
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - ASTM D5
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint | NZTA Approved
label | Specification Reference - NZTA M/1 5
label | Test Required - Letter from NZTA
label | Task Timing / Minimum Task Frequency - 1 per source and grade of binder used
label | Task Assigned To - NZTA
label | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
section | Sealing Chip Material Testing
checkpoint | Crushing Strength
label | Specification Reference - NZTA M/6 3.2
label | Test Required - Crushing Resistance Test
label | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.10
label | Criteria - <10% fines passing 2.36mm under 230kN load
checkpoint | Weathering Quality
label | Specification Reference - NZTA M/6 3.3
label | Test Required - Weathering Quality Index Test
label | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.11
label | Criteria - AA or BA
checkpoint | Weak Particles Test
label | Specification Reference - NZTA M/6 3.4
label | Test Required - Australian Weak Particles Test
label | Task Timing / Minimum Task Frequency - Only undertaken in case of dispute.
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - AS 1141.32-1995
label | Criteria - Maximum of 1%
checkpoint | Polished Stone Value
label | Specification Reference - NZTA M/6 3.5
label | Test Required - Polished Stone Value Test
label | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | Task Assigned To - Accredited PSV Testing Agency
label | Measuring Devices or Method - BS 812 : Part 114
label | Criteria - PSV Required = 53
checkpoint | Cleanliness
label | Specification Reference - NZTA M/6 4.1.1.
label | Test Required - Cleanliness Test
label | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.9
label | Criteria - Grade 3 - 87 min, Grade 5 - clean & free of soft, weathered, disintegrated or deleterious material
checkpoint | Size & Shape
label | Specification Reference - NZTA M/6 4.1.2.
label | Test Required - Size & Shape
label | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.13
label | Criteria - Grade 3 - ALD 7.5 - 10.0, 70%Min within 2.5% ALD
checkpoint | Broken Faces
label | Specification Reference - NZTA M/6 4.1.2.
label | Test Required - Broken Faces Test
label | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.14
label | Criteria - 98% with minimum two broken faces
checkpoint | Grading
label | Specification Reference - NZTA M/6 4.2.2.
label | Test Required - Grading
label | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | Task Assigned To - IANZ accredited laboratory
label | Measuring Devices or Method - NZS 4407:2015, Test 3.8
label | Criteria - Grade 5: 95-100% passing 9.5mm, 0-8% passing 4.75mm, 0-2% passing 2.36mm