## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 8. HB AWPT ITP - Clarkesons Hill A | [5 empty] | 8. HB AWPT ITP - Clarkesons Hill A
section | Preliminary / Establishment
checkpoint | Establish TTM
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | Task Assigned To - STMS/Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - As per TMP and ensure TMC advised in advance of works.
label | QA Form - Daily Diary
checkpoint | Permits
label | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | Test Required - Document Review
label | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Obtain permits and mark outs prior to construction
label | QA Form - Copy of Permit on site
checkpoint | Clear-Shoulder and Side drain
label | Test Required - Visual Inspection
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Visual
label | QA Form - Daily Diary
checkpoint | Digout Failed Areas
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - As Requested
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | Criteria - Backfill with Basecourse
label | QA Form - Daily Diary
section | Kerb Construction
checkpoint | Basecourse layer construction (1)
label | Specification Reference - TNZ B/2
label | Test Required - Level and alignment
label | Task Timing / Minimum Task Frequency - Every 20m
label | Task Assigned To - Project Engineer
checkpoint | Basecourse layer construction (2)
label | Specification Reference - TNZ B/2
label | Test Required - Compaction
label | Task Timing / Minimum Task Frequency - Every 20m
label | Task Assigned To - Project Engineer
label | Criteria - 25min on the 4th drop
label | QA Form - QA Measurement Sheet
checkpoint | Kerbing
label | Test Required - Set-out level and alignment
label | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
label | Measuring Devices or Method - survey check
label | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
checkpoint | Concrete Works
label | Test Required - 20MPa
label | Measuring Devices or Method - Copy of delivery docket
label | Criteria - 20MPa, 28days
section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint | Cement for stabilisation
label | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | Test Required - Certified in accordance with NZS 3122
label | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint | Production plan
label | Specification Reference - NZTA B/5:2008, 7.2.2
label | Task Timing / Minimum Task Frequency - 1 per site
checkpoint | Stabilisation mix properties (including cement):
label | – Maximum dry density (MDD)
label | – Optimum water conent (OWC)
label | – Solid density (SD)
label | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | Test Required - Material properties for compaction verification
label | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | Task Assigned To - Hold Point - Approval required by site engineer
label | QA Form - QA Measurement Sheet
holdpoint | HOLD POINT
checkpoint | In-situ moisture content of existing pavement aggregate
label | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | Task Timing / Minimum Task Frequency - As required
label | Task Assigned To - Inspection - Lab
label | QA Form - QA Measurement Sheet
checkpoint | Top-up metal
label | Specification Reference - TNZ M/4 Table 4
label | Test Required - Placed to required depth and design levels
label | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | Task Assigned To - Site Foreman
label | QA Form - QA Measurement Sheet
checkpoint | Cement spreading
label | Specification Reference - NZTA B/5:2008, 7.3
label | – Mat test (1m2 canvas mat)
label | – Average usage test
label | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | Task Assigned To - Inspection & sign off by Site Supervisor
label | QA Form - QA Measurement Sheet
checkpoint | In-situ mixing - Cut depth
label | Specification Reference - NZTA B/5:2008, 7.6.1
label | Test Required - Maximum variation -5mm and +15mm
label | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | Task Assigned To - Inspection & sign off by Site Supervisor
label | QA Form - QA Measurement Sheet
checkpoint | Compaction
label | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | Test Required - Plateau testing
label | ○ Mean value ≥ 98% of MDD
label | ○ Minimum value ≥ 95% of MDD
label | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | Task Assigned To - Hold Point - Approval required by site engineer
label | Measuring Devices or Method - Nuclear Densometer
label | Criteria - Minimum value 95% of MDD
label | QA Form - Test Reports
holdpoint | HOLD POINT
checkpoint | Surface shape
label | Specification Reference - NZTA B/5:2008, 7.8
label | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | Task Timing / Minimum Task Frequency - 20m intervals
label | Task Assigned To - Inspection & sign off by Site Supervisor
label | Measuring Devices or Method - Stringing, Tape measure
label | QA Form - QA Measurement Sheet
checkpoint | Crossfall
label | Specification Reference - NZTA B/5:2008, 7.9
label | Test Required - Not less than exisitng crossfall at the start of construction
label | Task Timing / Minimum Task Frequency - 20m intervals
label | Task Assigned To - Inspection & sign off by Site Supervisor
label | Measuring Devices or Method - Stringing, Tape measure
label | QA Form - QA Measurement Sheet
checkpoint | Surface finish
label | Specification Reference - NZTA B/5:2008, 7.10
label | Test Required - See clause
label | Task Timing / Minimum Task Frequency - 20m intervals
label | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | Measuring Devices or Method - Visual
holdpoint | HOLD POINT
checkpoint-no-status | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
section | Chipseal Construction (NZTA P29)
checkpoint | Ensure appropriate TMP used
label | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint | Seal design
label | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | Task Assigned To - Project Engineer
label | Criteria - Seal design to be reviewed prior to surfacing
label | QA Form - Seal design template
holdpoint | HOLD POINT
checkpoint | Location/Size Confirmation
label | Specification Reference - Mark up extent of chipseal
label | Test Required - Prior to surfacing
label | Task Timing / Minimum Task Frequency - Project Engineer
label | QA Form - Daily Diary
checkpoint | Surface Cleanliness
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Prior to application of binder
label | Task Assigned To - Site Foreman
label | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | QA Form - QA Measurement Sheet
checkpoint | Plant Resource
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | QA Form - Daily Diary
checkpoint | Binder Application
label | Test Required - Binder type, Cutback, Temp, Application rates
label | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | Measuring Devices or Method - Visual
label | Criteria - Binder Type = 180/200.
label | ○ Cutback to suit 1st coat seal 4pph kero max.
label | ○ Temp = 150deg celcius min
label | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | QA Form - Bitumen Spray Sheets
checkpoint | Chip Application
label | Test Required - Chip type, Chip Application
label | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Trucks loaded with correct chip.
label | ○ Chip clean. (G4/6 Racked example)
label | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | ○ G6 application = Enough to just fill the voids around the G4.
label | QA Form - QA Measurement Sheet
checkpoint | Compaction
label | Test Required - Visual
label | Task Timing / Minimum Task Frequency - At completion of rolling
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | QA Form - 'QA Measurement Sheet
checkpoint | Site Measure
label | Test Required - Record final site measure
label | Task Timing / Minimum Task Frequency - Completion of works
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Measuring Wheel or Tape
label | Criteria - Sketch and record seal area and QA detail
label | QA Form - QA Measurement Sheet
checkpoint | Post Seal Care
label | Test Required - Visual inspection
label | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | Task Assigned To - Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | QA Form - Daily Diary
section | Chip Removal, Pavement Marking, Traffic Services
checkpoint | Removal of excess chip
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | QA Form - Daily Diary
checkpoint | Pavement Marking
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | QA Form - Daily Diary
checkpoint | Removal of TTM
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | QA Form - Daily Diary
checkpoint | Traffic Services
label | Test Required - Visual Inspection
label | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | Task Assigned To - Project Engineers/Site Foreman
label | Measuring Devices or Method - Visual
label | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | QA Form - Daily Diary