## Sheet1
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | CIDD Alerts
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | Enviro Shield
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro Flex FC/ Sika Flex FC
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro 200P Ultra
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Site engineer/foreman batch inspection review
SIGNOFF | site engineer/foreman sign off
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Sample Approval Ref.
SIGNOFF | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Records - Site Engineer/ Foreman Confirmation
SIGNOFF | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
Label | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
Label | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat, including all nails, penetrations and corners. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
Label | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
Label | Records - Site Engineer/ Foreman Confirmation
SIGNOFF | Hold Point (Mandatory) - work not to proceed without approval
Checkpoint | Cracks in Substrate - AS2870 Table 2.10
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman pre commencement inspection review
SIGNOFF | Site engineer/ foreman inspection - sign off
SECTION | SUBSTRATE PREPERATION - EACH LOCATION
Checkpoint | Substrate Preperation - AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman substrate preperation inspection review
SIGNOFF | Site Engineer/Foreman Inspection sign off
SECTION | PRIME COAT- EACH LOCATION
Checkpoint | Moisture Content - Enviro Shield Product TDS
Label | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Weather/RH - Enviro Shield Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Mixing - Enviro Shield Product TDS
Label | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute.
select | Inspection | Surveillance point, Witness point
Checkpoint | Application - Enviro Shield Product TDS
Label | Apply primer using a brush or roller.
Label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
Label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Priming Inspection Review
SIGNOFF | Site Engineer/Foreman Inspection sign off
SECTION | BOND BREAKER- EACH LOCATION
Checkpoint | Caulking - AS 3740 2021 & AS 4654.1
Label | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
Label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
Label | Allow to be tack free prior to over coating with membrane coats.
Label | Records - Time stamped photograph
Label | Records - Thickness with fillet gauge
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman bond breaker inspection review
SIGNOFF | Site Engineer/Foreman bond breaker inspection sign off
SECTION | FIRST BASE COAT - EACH LOCATION
Checkpoint | Weather/RH - 200P Ultra Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Mixing - 200P Ultra Product TDS
Label | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | Application - 200P Ultra Product TDS
Label | • 200P Ultra to be applied by roller vertically on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor first base coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman first base coat inspection review
SIGNOFF | Site Engineer/foreman base coat inspection sign off
SECTION | SECOND BASE COAT- EACH LOCATION
Checkpoint | Weather/RH - 200P Ultra Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Mixing - 200P Ultra Product TDS
Label | 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | Application - 200P Ultra Product TDS
Label | 200P Ultra to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Allow membrane to cure for 3 days prior to testing.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor second base coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman second base coat inspection review
SIGNOFF | Site Engineer/foreman base coat inspection sign off
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Flood Testing
Label | Mark water level and conduct a 24 hour flood test for internal wet areas
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman QA inspection review
SIGNOFF | Site Engineer/foreman base coat inspection sign off