## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 4. Site survey and set out of levels. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 04. Site survey and set out of levels. | 060aceb2-de73-460e-9f91-f3ec409d50af
checkpoint-status |  |  | checkpoint | All levels and set outs as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Existing services located, marked, and protected if required. All works to be accordance with CTS Excavation works Specification. CTS General civil construction Specification
label | 7d6c91ab-12d4-51b5-9d8a-fa0b627a3ecd |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023
label | 1342c53d-f9a7-57c9-8140-e846c8774ec8 |  | note | Leading Hand - P - Surveyor
label | aee2882f-b145-55f3-a81f-63183a9e3c52 |  | note | Supervisor - Surveyor - H
label | 4249eaa0-49b7-5377-b71a-456e7071a0c0 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP 002 - Capping Layer |  |  |  |  | Yes | TEST - ITP 002 - Capping Layer | 0baf8a97-f864-420f-bebc-3bf9ba4a7c93
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
date | ebcbaaac-056a-5129-b26f-c8e1c47c3a54 |  | date | Lot Opened On
date | 1a5126b0-9a30-52ab-a62e-f5220f33c9ee |  | date | Date of Works
text | 37a3eaac-9459-5094-8545-253d6e8f119c |  | textbox | Lot Type
text | 9e704441-9ffa-5882-879a-ed7e3f5375e7 |  | textbox | Start Chainage
text | 72893085-2488-5449-bc3e-85674cd171ff |  | textbox | End Chainage
checkpoint-group |  |  | section | Procurement
checkpoint-status |  |  | checkpoint | Physically located all utility locations
label | 6864abb3-9df0-5f84-8fff-277f3573ae2d |  | note | Detail of Activity - Permit to work around services (Gas, Power, Fibre, etc.)
label | f96506b3-ab10-5739-8b82-60e3a5cfe483 |  | note | Minimum Test Frequency - as required per section of works
label | 1a576b75-5b06-5fae-a49b-24a50f59771a |  | note | Inspection/Test Method - Document Review
label | b26bedb5-e360-5ff5-9f54-62b28affd2bd |  | note | Acceptance Criteria - All services physically located
label | 6ecad2c3-8e2d-57e6-ba43-91aca82b5348 |  | note | Verifying Documentation - Permit attached or permit number noted
label | 22518f1d-32ca-5f0e-bca8-1e94ae566e69 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.2 - Contract Document Signed
label | 8ef9deaa-91b6-5e50-8883-431ce7f92f3e |  | note | Detail of Activity - Ensure Contract is signed
label | 80ecb48a-6c96-5999-a7a7-cf44036bc0cb |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | edcb6a82-54a5-5d6f-99ac-be6fdaa7a369 |  | note | Inspection/Test Method - Document Issue
label | 78798a09-7b46-5c50-8e77-b1baba650ec7 |  | note | Acceptance Criteria - N/A
label | c24d467a-57f9-50f4-99ca-4a0d854fbe3c |  | note | Verifying Documentation - Issued with a NTC
label | c4d58cd1-177a-5371-acc5-89c9c9eba13b |  | note | Responsibility - Downer / BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.3 - For Construction Drawings Issued
label | a3831201-4855-5d4e-b568-cb7e7aa6fa62 |  | note | Detail of Activity - Ensure "For Construction" drawings are issued
label | 8f6be392-4d68-5533-b98b-68105e180846 |  | note | Ensure Contract is signed
label | b16016d8-e64c-5a0c-a208-5b6407a1b383 |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | 76cdc54e-877b-5f86-8b51-7a4f2f618169 |  | note | Inspection/Test Method - Document Issue
label | eb8ac336-7c40-57b6-8169-ee0e29dfdc51 |  | note | Acceptance Criteria - N/A
label | 0724fb78-69bb-5215-ae26-224920b18fcf |  | note | Verifying Documentation - Issued with a NTC
label | c98573c5-9bb5-5d61-9c36-2bf747c23b97 |  | note | Responsibility - Downer/BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 100.4 - Traffic Management Plan
label | 84b0c8f4-09da-559f-a544-6d9aa677edd1 |  | note | Detail of Activity - Ensure TMP is approved and check that the requirements are fully understood by the STMS
label | a58b12ca-93f8-5fca-830f-475cc8ea50de |  | note | Minimum Test Frequency - every morning and/or when the TMP changes
label | bfbfa7ea-e5f1-5846-a5b9-d3439f8e2da9 |  | note | Inspection/Test Method - Document and Physical works review
label | 0d3ab922-999b-53b6-96b1-2293de6a2a95 |  | note | Acceptance Criteria - COPTTM
label | e84146f6-e813-5590-8158-42646c90d8ce |  | note | Verifying Documentation - TMP from contractor
label | 60121b19-a2b9-5fc7-b1c5-4b28b0be31b0 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.5 - Design
label | 4805c05e-058d-5ec2-9f65-71dff8a5d3e3 |  | note | Detail of Activity - Ensure that Design is approved and Drawings are the latest version
label | 9c647a57-f512-52da-b051-59acd87a1ebb |  | note | Minimum Test Frequency - Prior to commencement
label | 2927b4ed-7b1e-51db-88f5-17b1f7c4a928 |  | note | Inspection/Test Method - TNZ M/20; TNZ M/7; TNZ M/24
label | a168b25f-e3de-5f8c-a2f6-c629e2d02471 |  | note | Acceptance Criteria - Is a copy of approved consent(s) available on site
label | f957a63d-d785-53dd-967e-7e73543455f3 |  | note | Verifying Documentation - Check Drawing register
label | 1d1b10e9-bb37-52e5-a6cd-1ea9a11b05a4 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 100.6 - Approved Consents
label | c1cca32e-ab0d-5fa6-9203-92235ba039e9 |  | note | Detail of Activity - Is a copy of approved consent(s) available on site
label | 4c6fbe48-6447-5455-92d0-bcbabe8787d0 |  | note | Minimum Test Frequency - Prior to commencement
label | 8094a0f5-8173-5f5e-912a-d1eb6c1eb6ba |  | note | Prior to commencement
label | 5ed48067-2ad2-57db-9c31-8da04baefe46 |  | note | Inspection/Test Method - Visual Inspection
label | 9525406d-0172-599a-9c1e-dcdc9600354f |  | note | Acceptance Criteria -
label | 47f3b81a-8379-566a-8f8e-59b9be60ac82 |  | note | Verifying Documentation - This ITP
label | ac17e8f2-8c41-5c5f-85cf-b7ccef556caa |  | note | Responsibility - BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.7 - Pre-start meeting
label | ace4ff17-0643-5535-80ac-cd324f7c19d1 |  | note | Detail of Activity - Pre-start meeting to confirm work strategy and safety measures
label | b612c74c-7450-54bb-a169-959fb3615c1d |  | note | Minimum Test Frequency - Before commencing work each day
label | 0b4eea31-d4de-5b54-ae3e-2c0a28083e97 |  | note | Inspection/Test Method - N/A
label | a58cc459-f633-563c-b23b-3ec6230a5cbf |  | note | Acceptance Criteria - 100% attendance
label | 8c8c30d2-f3ea-5786-8655-bb0a1e758511 |  | note | Verifying Documentation - Pre-start sign on register / site diary
label | ecc389b8-2a78-52b0-b92c-1f4d1bdc4208 |  | note | Responsibility - BBO
checkpoint-status |  |  | checkpoint | 100.8 - Contractor's methodology
label | 9f91cb1e-a77d-585d-863c-bdbce0f15bd5 |  | note | Detail of Activity - Site inspection
label | f5cc98ba-cd74-5a48-b917-28516ff35db6 |  | note | Minimum Test Frequency - Prior to commencement
label | a7278459-d6a7-57fa-bd65-c21b51001134 |  | note | Inspection/Test Method - Document review
label | 3c0d404a-cea6-54ef-aa10-7d835c404372 |  | note | Acceptance Criteria - Methodology conforms with all relevant specifications
label | f7a78c1c-ed9d-5f0a-b15f-7cb4405a8d6a |  | note | Verifying Documentation - Methodology submitted via NTE
label | fa47d607-4c76-5ed3-9841-0cf83472637d |  | note | Responsibility - BBO's Rep.
checkpoint-group |  |  | section | Post Work
checkpoint-status |  |  | checkpoint | 100.9 - Laydown area / stockpile sites
label | 13bf4188-5a93-5ef5-bcd4-73f66b3b42a3 |  | note | Detail of Activity - Site inspection
label | e4dfa1d4-312f-5535-a482-d3b6277b1571 |  | note | Minimum Test Frequency - Prior to commencement
label | 3e668999-5d00-5f71-aab1-a8a4225fcf2f |  | note | Inspection/Test Method - Visual Inspection
label | 354347c7-33eb-51b6-9743-2fb66c5e1b44 |  | note | Acceptance Criteria - Approved by NZTA
label | 5edf3e24-5235-5c79-b967-2e902d927062 |  | note | Verifying Documentation - Request for approval (RFA) via NTE
label | 1d68918e-3c4f-599f-9439-3ac7b627e746 |  | note | Responsibility - BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.1 - Weather
label | be400cd3-252d-553f-9eaf-7c6fd44a73b1 |  | note | Detail of Activity - Assessment of forecast
label | dcc211c8-2dc1-5f0f-8dbe-2b3792e233fe |  | note | Minimum Test Frequency - Daily prior to and during works
label | 79bb2a07-313f-5dae-971e-d98f18b0a506 |  | note | Inspection/Test Method - Check local and national weather forcast services
label | 10731880-499f-51c2-9700-72dbdf2350b4 |  | note | Acceptance Criteria - No imminent rain or adverse weather conditions. Consideration of wind and project location/environment
label | 040da5ef-033c-5850-9f86-1d11d6dc9d4d |  | note | Verifying Documentation - Contractor's site diary
label | c1a4688a-3e0c-52ed-85fa-ba5bfe3780bb |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 101.2 - Environmental Protection
label | 6373a627-af35-5fa0-9d92-9d170241e5ce |  | note | Detail of Activity - Site evaluation
label | 3d87c19b-7294-5177-b6d9-d5091c1d2d6a |  | note | Minimum Test Frequency - Prior to commencement
label | 68aa1a74-7384-5c9c-bf47-3f2840f6c2fa |  | note | Inspection/Test Method - Inspection
label | 1622f9d5-52f3-5d48-98f7-6da1f4d606b3 |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | c8ee7dca-8060-502b-9c85-eb4fdbbdf818 |  | note | Verifying Documentation - Contractor's site diary
label | b7d2586e-4e75-5364-9e6e-faad24205065 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.3 - Precondition Survey
label | d7a05c90-7831-56de-98ff-fa073d87d141 |  | note | Detail of Activity - Examine extent of the site
label | 215530e9-f1ea-560a-8834-f33dbd8f3d00 |  | note | Minimum Test Frequency - Prior to commencement
label | f4447c99-baf8-59bd-b861-3089814e614f |  | note | Inspection/Test Method - Inspection
label | 38325e46-d99a-5556-9f82-66cdb48a953b |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | 34cb80b0-b912-5bea-a08e-1f20160184ed |  | note | Verifying Documentation - Contractor's site diary
label | 23ba5dc9-55bc-54ea-b589-49f9d46bcd75 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | af075329-0c12-5eb8-83e3-d4944ea37ff6 |  | textbox | Lot Verified By:
select | 9d80efe1-5e0a-5b6b-8ee1-7dae584e450c |  | dropdown | Lot Status | Outstanding, Closed
date | a27fcb93-b1b7-5626-a291-362efe471529 |  | date | Lot Closed Date:
button | 18eb12e7-f2b6-57b1-b18c-f59a11b9ea78 |  | button | Submitted to Client | Yes, No, N/A
text | 40624a80-929c-50fa-9c09-197e1899d8b3 |  | textbox | Reviewed by Client
text | fc062a2d-e346-518f-9f86-b2e3b8027a7a |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | 20. Install Denso steel coat base protection or approved equivalent (Viscotaq) around tank annular |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 20. Install Denso steel coat base protection or approved equivalent (Viscotaq) around tank annular | 0bb2a8f1-49ef-4eb2-be44-89002dd9301e
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Viscotaq installed in accordance with manufacturers recommendations. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 3a0afbf9-e05f-5285-863b-8478938e73e0 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Product manufactures specifications Site plan with inspected areas
label | 3842f58d-6221-5ca1-a00e-05f86c213754 |  | note | Leading Hand - N/A - Leading Hand
label | 34f559ff-92a2-51bb-afdb-b0d8d002dc66 |  | note | Supervisor - Leading Hand - W
label | 68a710f0-071e-5077-af62-591618a4c67d |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 13. Install 1.5mm PE liner on tank shoulder. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 13. Install 1.5mm PE liner on tank shoulder. | 0d67bc23-4105-48f7-b88b-db3582ac10fd
checkpoint-status |  |  | checkpoint | PE liner installed with Bidim A64 cloth T&B PE liner installed as per installers QA-QC and Worley’s QC requirements as per Civil /Struct Design pack 310449/C1 Rev A drawing notes T3084782 on IFC drawings issued 05 May 2023 Review installers QC documentation before placing Bidim Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 2ea1b228-7075-50d3-8593-f9b63fdc5cc6 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | d7fd8dd9-c45b-5ec6-b78c-436f876f04b8 |  | note | Leading Hand - N/A - Leading Hand
label | 1826221e-5f24-53d1-9d41-bd1ef869a0e5 |  | note | Supervisor - Leading Hand - W
label | 34b74a81-54c1-5076-bd38-89d605bd617d |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 18. Compound Flood Test |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 18. Compound Flood Test | 103ef413-51cd-4660-9caa-e61eb510ca1a
checkpoint-status |  |  | checkpoint | Timing of the flood test will be conducted as per the approved Compound C3 Flood test methodology. All items on Compound Pre-Flood Check Sheet to be completed by relevant parties. The infiltration test will be as detailed in HSWA COP 47 ‘Secondary Containment Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | fca553ae-aeca-5900-ab1f-4cd43ecad4b2 |  | note | Applicable Documents - UCCL Compound C3 Flood test methodology HSWA COP 47 ‘Secondary Containment’
label | e83a41db-4bb8-5d11-bdee-19fccf0fdedb |  | note | Leading Hand - N/A - Leading Hand
label | 465c31ef-b097-5115-b946-f1eaafcdfc68 |  | note | Supervisor - Leading Hand - H
label | 1e7abad5-4fad-59aa-9406-3574d47c0c3a |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Lot Signoff |  |  |  |  | Yes | Lot Signoff | 10596494-0490-4674-aaf3-bbdc9053e9e5
checkpoint-status |  |  | checkpoint | Lot Information complete
date | 93e726b9-d478-5167-accc-3e0fb1f87d6d |  | date | Date
text | e7c3eb0d-43ce-5dae-80e4-0b5342589508 |  | textbox | Lot Type
text | c43abea1-a8aa-5220-bff9-41ee7d8e707f |  | textbox | Start Chainage
text | 5c23eae7-76ac-5da1-a69f-7669c32bf51d |  | textbox | End Chainage
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 16. Concrete pre-pour inspection Tank Shoulder |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 16. Concrete pre-pour inspection Tank Shoulder | 1f4c2225-9db9-44de-8fbe-9bcaafec962a
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 All works in accordance with CTS General Civil Construction Specification Concrete pre-pour check sheet completed and filed with ITP General Civil Construction Specification Concrete shall be high or special grade certified “ready mixed concrete” manufactured at a currently certified plant and shall comply with NZS 3104. Delivery dockets retained. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 0c181d79-124c-5823-acf2-69c444367599 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | 73c9e3eb-9ccc-5cf5-9c47-d9f89ca1ec06 |  | note | Leading Hand - N/A - Leading Hand
label | a4ebea82-591d-5fce-914a-3c554a922bfe |  | note | Supervisor - Leading Hand - W
label | c2f60af6-f133-53bb-afe3-7e7d401f620e |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 27. Compilation of inspection and test record |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 27. Compilation of inspection and test record | 226be7ba-0ca8-4711-a8d4-303214fc9780
checkpoint-status |  |  | checkpoint | CTS General Civil Construction Specification CTS QC Requirements for Civil Works
label | a5807a29-0d3a-5c26-8f28-9100cc3fbb95 |  | note | Applicable Documents - Signed off ITP & work pack, Section 7 and 8 UCC Producer Compliance Statement. These documents will be compiled to form a complete MDR/QC Pack.
label | 81c12676-8c0c-5dc1-85c7-efb260910f75 |  | note | Leading Hand - N/A - N/A
label | 595aa7bd-24ce-5b15-a642-aa63cc861b71 |  | note | Supervisor - N/A - H
label | fcec7d48-6354-59f2-a81c-d3536d32f0f9 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 2. Change Details |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 02. Change Details | 249af915-394f-4577-a87c-bdbc7ef30898
checkpoint-status |  |  | checkpoint | Change Details. Details of design changes Details of approved scope changes
checklist-flat |  |  | checklist | 22. Complete final Civil inspection and close off ITP. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 22. Complete final Civil inspection and close off ITP. | 29372d70-c292-4347-8b65-34bc5085e000
checkpoint-status |  |  | checkpoint | ITP / QC has been completed; all steps & hold points signed by relevant party. All work scope completed as per design pack and any field instructions issued during construction. Job site has been left tidy.
label | 4aa95d40-8292-5a3e-97e4-1cfe2105f6cf |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023
label | d1fc134f-5065-5346-9eba-d46edb8ede69 |  | note | Leading Hand - N/A - N/A
label | 42a47edc-1de1-5f53-8ded-b3d3d79211bb |  | note | Supervisor - N/A - H
label | 65377666-0710-5438-bd27-ae8f3f14909a |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 11. Install subsoil drainage. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 11. Install subsoil drainage. | 29a7060d-1fbe-4c47-8065-a8344fcd8327
checkpoint-status |  |  | checkpoint | All levels and set outs as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Existing services located, marked and protected if required. All works to be accordance with CTS Excavation works Specification. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 82235ec1-b087-57aa-abe2-5c50012e2437 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 CTS General Civil Construction Specification Site plan with inspected areas
label | 381556cc-11b6-57e9-bb3d-7e8b204af316 |  | note | Leading Hand - N/A - Leading Hand
label | 3a97e4d2-a78a-5e0f-b651-8f3fa81c96b8 |  | note | Supervisor - Leading Hand - H
label | e2ec5a75-13df-5fe0-a46d-8fd9cb9c2305 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 23. Non-Conformance reporting |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 23. Non-Conformance reporting | 2ce78e3d-4438-49cd-990f-3986969d5432
checkpoint-status |  |  | checkpoint | In accordance with the approved Work Pack, drawing, Field Instruction and agreed scope of work. CTS General Civil Construction Specification CTS QC Requirements for Civil Works
label | 6f14e852-6918-5523-9684-4b24a9301774 |  | note | Applicable Documents - UCC internal NCR and or CTS Lucidity event NCR CTS QC Requirements for Civil Works
label | 6f5fb261-725c-5dfd-9b69-0c54a2e61a69 |  | note | Leading Hand - N/A - N/A
label | f8ce29ad-8e27-5dbf-a7e4-7899bfacda69 |  | note | Supervisor - N/A - H
label | 835794cf-e72e-57c9-9e14-48152675b96c |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP 003 - Subbase Layer |  |  |  |  | Yes | TEST - ITP 003 - Subbase Layer | 30a2d497-448a-4aee-b7df-6ce4ad1aa4ce
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
date | 408e2de0-d76a-5654-9009-99565a9ada02 |  | date | Lot Opened On
date | 666660ee-17f3-546e-bdb2-d7cc7f22d333 |  | date | Date of Works
text | 046f2834-7640-566a-bb5c-2c03d69be0f5 |  | textbox | Lot Type
text | 786e34a6-943e-5260-aa51-b48ac9607f02 |  | textbox | Start Chainage
text | 77c58c4a-3292-5b9b-8649-d8d6826ffd7e |  | textbox | End Chainage
checkpoint-group |  |  | section | Procurement
checkpoint-status |  |  | checkpoint | Physically located all utility locations
label | a8ae8054-4f60-56f4-97a4-88c4ef6b36e5 |  | note | Detail of Activity - Permit to work around services (Gas, Power, Fibre, etc.)
label | 5eeba223-7907-5cde-b793-a1c47898ec32 |  | note | Minimum Test Frequency - as required per section of works
label | 5585a794-9266-54d6-b142-d0211e28eae5 |  | note | Inspection/Test Method - Document Review
label | a429cc36-1b2d-5ef7-99b0-d8d21447b9e5 |  | note | Acceptance Criteria - All services physically located
label | 346977ff-d8d8-59d5-8302-8afabeb7ba62 |  | note | Verifying Documentation - Permit attached or permit number noted
label | b3000fb5-331e-5422-9672-454c40880074 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.2 - Contract Document Signed
label | 88b65d94-da50-5c73-b711-3f4343c497cc |  | note | Detail of Activity - Ensure Contract is signed
label | ef266196-1b31-5a8b-b9c1-5df424264a4e |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | de1a60ee-a4c0-54de-9228-39a1b58bbb00 |  | note | Inspection/Test Method - Document Issue
label | 1ed99eee-83e2-570d-87ec-f4a06fe2913f |  | note | Acceptance Criteria - N/A
label | 43c37d3c-ffa6-5501-baf7-16e975943fd8 |  | note | Verifying Documentation - Issued with a NTC
label | 0bd32e80-a110-5aa1-8441-f6daa545802b |  | note | Responsibility - Downer / BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.3 - For Construction Drawings Issued
label | a727d340-b25c-58bb-8973-a63e492e8da6 |  | note | Detail of Activity - Ensure "For Construction" drawings are issued
label | b7b3626c-dbd8-56e6-8647-5ed678084e2d |  | note | Ensure Contract is signed
label | 3dc8e932-25a4-5a5f-96ac-1a15d592e776 |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | 19dbad00-7d5a-5ad2-9bba-68a7a9266896 |  | note | Inspection/Test Method - Document Issue
label | 68560b8d-7d7a-5937-a5c8-330c4e30d22b |  | note | Acceptance Criteria - N/A
label | 4e68f7fe-2757-5533-ba4a-d1a0dcb1e06e |  | note | Verifying Documentation - Issued with a NTC
label | 35162dc3-5e24-59dd-b385-b84e31f6fb4c |  | note | Responsibility - Downer/BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 100.4 - Traffic Management Plan
label | c5272bf1-7036-5552-b848-b0d14c03a1f7 |  | note | Detail of Activity - Ensure TMP is approved and check that the requirements are fully understood by the STMS
label | 18437fe7-411c-52ae-a2b0-6dd0171fc278 |  | note | Minimum Test Frequency - every morning and/or when the TMP changes
label | a57353df-4e77-5d79-b87b-6cef5efe27c9 |  | note | Inspection/Test Method - Document and Physical works review
label | 8113a43d-2289-5cb6-9d36-78d5ef5582b7 |  | note | Acceptance Criteria - COPTTM
label | 08a80483-6820-56fe-93e7-58fbfd956000 |  | note | Verifying Documentation - TMP from contractor
label | c252e7dd-96d8-5cd5-a901-cef297dcbcfe |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.5 - Design
label | 7f8c824e-9471-53dc-9c94-70d42d1d8d49 |  | note | Detail of Activity - Ensure that Design is approved and Drawings are the latest version
label | f6f88d38-0ae5-564c-ba91-01f02bebdf88 |  | note | Minimum Test Frequency - Prior to commencement
label | adcf8940-9a8a-57f4-9e3a-8de6ca51a884 |  | note | Inspection/Test Method - TNZ M/20; TNZ M/7; TNZ M/24
label | f7e4f64e-384f-598e-aff6-4a11f1e08612 |  | note | Acceptance Criteria - Is a copy of approved consent(s) available on site
label | b6392706-c9e4-5d1b-a35c-66dc8490c572 |  | note | Verifying Documentation - Check Drawing register
label | ff8c3e2f-2595-5e23-b539-dee94aca832f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 100.6 - Approved Consents
label | 893ab715-dbeb-5391-b93a-f52de0364d2f |  | note | Detail of Activity - Is a copy of approved consent(s) available on site
label | 96b705c7-af0f-55f4-9cc3-b1a3eadca622 |  | note | Minimum Test Frequency - Prior to commencement
label | 3ce7721f-214c-5fa1-89b5-3cee7ed9e902 |  | note | Prior to commencement
label | 8bb2dede-b652-520c-ae63-4ba595e9e09f |  | note | Inspection/Test Method - Visual Inspection
label | 082310a9-9b26-5e87-b604-e9330ee85513 |  | note | Acceptance Criteria -
label | b37a98b9-9bb4-5946-8c90-666daa27d3c5 |  | note | Verifying Documentation - This ITP
label | 0755237c-ef39-509f-91e7-05aba2a9cb15 |  | note | Responsibility - BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.7 - Pre-start meeting
label | f4d60d8a-712b-52e2-8a6c-a4bf3675bb09 |  | note | Detail of Activity - Pre-start meeting to confirm work strategy and safety measures
label | 337e8f7b-b6bd-54f1-9e20-51c809e64ae7 |  | note | Minimum Test Frequency - Before commencing work each day
label | c96d407e-501c-54d3-af1e-b92f1b87aa14 |  | note | Inspection/Test Method - N/A
label | 33387768-9757-5401-bc9c-6eb0e6ab63b8 |  | note | Acceptance Criteria - 100% attendance
label | d8fa4a21-611a-5569-8ea0-c09465569665 |  | note | Verifying Documentation - Pre-start sign on register / site diary
label | b9577ea6-e02a-598a-b2f0-7cf6d12c036b |  | note | Responsibility - BBO
checkpoint-status |  |  | checkpoint | 100.8 - Contractor's methodology
label | 62ce3b0d-bf72-5c96-a9f5-a6401b5131e9 |  | note | Detail of Activity - Site inspection
label | babc3379-1bcc-50a0-a224-4b11c3584293 |  | note | Minimum Test Frequency - Prior to commencement
label | 9cb718bc-3428-5223-9ba0-e29c2d719be2 |  | note | Inspection/Test Method - Document review
label | 380f9e3e-70d7-54cb-b817-035642aa98b6 |  | note | Acceptance Criteria - Methodology conforms with all relevant specifications
label | 4dd46eb2-54b4-5753-af17-5418069013c1 |  | note | Verifying Documentation - Methodology submitted via NTE
label | fb44b67a-fbff-5b0b-83bc-e99993f79ff1 |  | note | Responsibility - BBO's Rep.
checkpoint-group |  |  | section | Post Work
checkpoint-status |  |  | checkpoint | 100.9 - Laydown area / stockpile sites
label | 486e1e9e-a636-5c17-a5c8-ef0b3d5b3972 |  | note | Detail of Activity - Site inspection
label | fc6727cd-04c6-5f33-a63b-8cf3c0e1f52f |  | note | Minimum Test Frequency - Prior to commencement
label | c7ffa64e-713a-5c60-82b2-af7ecdad455c |  | note | Inspection/Test Method - Visual Inspection
label | 1cab6316-a2ec-5fef-a2b2-9fd91343d388 |  | note | Acceptance Criteria - Approved by NZTA
label | c3994e4f-f3c4-5764-852b-23305d173e89 |  | note | Verifying Documentation - Request for approval (RFA) via NTE
label | 874d2848-0020-598f-81e5-5b38597da69f |  | note | Responsibility - BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.1 - Weather
label | 529587b4-1fee-55fd-847f-c964ede4cc46 |  | note | Detail of Activity - Assessment of forecast
label | 0ac712ef-7ef1-5852-8878-0565394c8ca2 |  | note | Minimum Test Frequency - Daily prior to and during works
label | 4e7612d2-e57f-59b0-8579-ee4b53d2a2e8 |  | note | Inspection/Test Method - Check local and national weather forcast services
label | 500fc0db-a587-597d-9557-ed7c7b646ae0 |  | note | Acceptance Criteria - No imminent rain or adverse weather conditions. Consideration of wind and project location/environment
label | 31d44841-95bf-5d94-9fdb-2cc21287d267 |  | note | Verifying Documentation - Contractor's site diary
label | 74085e74-b59f-5319-9503-f14ac1043c79 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 101.2 - Environmental Protection
label | 62ab42f5-d3ae-5448-b1c0-42cb5a387468 |  | note | Detail of Activity - Site evaluation
label | 00f5c6e6-a48f-501e-af81-321668e70531 |  | note | Minimum Test Frequency - Prior to commencement
label | 5349127e-dbce-5fe0-b20c-cba7f527c02a |  | note | Inspection/Test Method - Inspection
label | 95db073b-1fd6-5b52-98ac-e4d272794975 |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | 5b6676f7-a145-59b7-aa2c-ba2be776d9e0 |  | note | Verifying Documentation - Contractor's site diary
label | 598bb5b7-c4c4-54c9-85e9-56163e9db38e |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.3 - Precondition Survey
label | 858ddd6a-10ee-5b6e-a6b9-3233eac4e048 |  | note | Detail of Activity - Examine extent of the site
label | e28589f6-27c4-50bc-bf28-e1e4610aed5c |  | note | Minimum Test Frequency - Prior to commencement
label | e62a4e2a-1879-537a-a007-b5857dd35deb |  | note | Inspection/Test Method - Inspection
label | 4d9129bb-2359-5fc5-b959-6ff93206ef93 |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | 5e69f24e-1a90-5773-8a69-6959308d3674 |  | note | Verifying Documentation - Contractor's site diary
label | e17b059c-f8df-556b-9ff5-be93036ae551 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | edc41a54-d35b-5e15-825d-334828b938a4 |  | textbox | Lot Verified By:
select | 21e16131-ddc5-5518-8220-5d7b30a90dc4 |  | dropdown | Lot Status | Outstanding, Closed
date | 4590a2c7-c196-5f94-9d5a-797d37fcf7b7 |  | date | Lot Closed Date:
button | 1db4fea4-71dc-5640-a059-e03e355ce52a |  | button | Submitted to Client | Yes, No, N/A
text | e4b961fd-4069-5717-8125-a5bf8c58edeb |  | textbox | Reviewed by Client
text | 90f7342b-c845-556a-b8c9-84a45707c53e |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | 7. Demolition scope and removal of bitumen and concrete from compound floor |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 07. Demolition scope and removal of bitumen and concrete from compound floor | 46f7b2b4-2fca-48c3-b184-c854b18c1ec9
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Structures footings are not undermined. Inspection once the bitumen/concrete has been removed prior to sand blinding. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 5cf58501-bfd5-594e-b326-0a50b5207486 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | d7a2e7c5-8ad8-5818-9718-0c89da4ea51f |  | note | Leading Hand - N/A - Leading Hand
label | 38a91b2d-2977-5842-bc1c-d994379d2975 |  | note | Supervisor - Leading Hand - H
label | 7f7fe736-75b0-5e2b-887d-757031b04462 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 12. Install 1.5mm PE liner on Bund Walls. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 12. Install 1.5mm PE liner on Bund Walls. | 497180b3-6098-4ca7-817f-a8f8db36a24d
checkpoint-status |  |  | checkpoint | PE liner installed with Bidim A64 cloth T&B PE liner installed as per installers QA-QC and Worley’s QC requirements as per Civil /Struct Design pack 310449/C1 Rev A drawing notes T3084782 on IFC drawings issued 05 May 2023 Review installers QC documentation before placing Bidim Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 0e2b4eec-3301-5ca8-928a-f4437eacdd0d |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | 0dff8067-edcd-573f-8e20-66ade34d8853 |  | note | Leading Hand - N/A - Leading Hand
label | 3c2c51d5-63b7-5912-ba5d-fb1c21a8958a |  | note | Supervisor - Leading Hand - W
label | f312b117-90aa-5480-8b22-0b88a2382081 |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 8. Subbase preparation under liner compound bund walls |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 08. Subbase preparation under liner compound bund walls | 4e83bcbf-e33f-4e92-a7f9-fc3a38560954
checkpoint-status |  |  | checkpoint | All levels and set outs as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Existing services located, marked and protected if required. All works to be accordance with CTS Excavation works Specification. 50mm sand/cement bedding clean and free of debris Sand/cement placed to line and level. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 4598452a-4480-535f-b805-51c706657e79 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas.
label | f37d2b6e-fefd-5160-96dd-17389899631d |  | note | Leading Hand - N/A - Leading Hand
label | 5c943679-809f-5922-b494-2466ea3b775b |  | note | Supervisor - Leading Hand - H
label | 826726fd-38d5-5212-bc56-aff1176fa40c |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 25. Reference info, specifications etc |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 25. Reference info, specifications etc | 4fef4776-af48-4b28-b806-0be0283e0162
checkpoint-status |  |  | checkpoint | Applicable Documents - Relevant sections of Controlled doc’s Material specs (Epcon, coatings etc)
checklist-sectioned |  |  | checklist | ITP 001 - Subgrade Preparation |  |  |  |  | Yes | TEST - ITP 001 - Subgrade Preparation | 5363ab8d-811c-488c-8dff-ccd9af08f74e
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
date | 05120bb5-d4bf-521d-807f-7023d43b58e2 |  | date | Lot Opened On
date | 21481dbe-2f3f-5d85-9d29-39f1574069a3 |  | date | Date of Works
text | 00473c34-2933-561c-8314-d8797418a2ad |  | textbox | Lot Type
text | 2b6ca99e-2ec3-5dd6-b5ae-fe7d13de0b07 |  | textbox | Start Chainage
text | 50a2a081-d1b9-5935-b1c9-ed6dcc22d6ba |  | textbox | End Chainage
checkpoint-group |  |  | section | Procurement
checkpoint-status |  |  | checkpoint | Physically located all utility locations
label | 0daff645-d77f-5e5f-8ae5-f411aed6172a |  | note | Detail of Activity - Permit to work around services (Gas, Power, Fibre, etc.)
label | 790dc180-5645-5084-a8c4-a22bf2c89834 |  | note | Minimum Test Frequency - as required per section of works
label | 2c5f1451-8f23-59a0-9c63-785caedc4715 |  | note | Inspection/Test Method - Document Review
label | 8ff9b370-8869-5522-9ab8-3c28a604406b |  | note | Acceptance Criteria - All services physically located
label | 1e6d17e5-46ae-5c6d-a840-465ef7281693 |  | note | Verifying Documentation - Permit attached or permit number noted
label | 3d409afa-978a-5c67-9287-77e2e9480ef6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.2 - Contract Document Signed
label | d0298961-4e45-5241-ab49-845e45af843c |  | note | Detail of Activity - Ensure Contract is signed
label | 9559d1b5-6aac-5990-8287-e5b27f6f45b5 |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | 947d960e-9ddc-53d9-8fee-4ce45ecbdcc7 |  | note | Inspection/Test Method - Document Issue
label | 537f443b-dd10-5eeb-b374-11aeef8be586 |  | note | Acceptance Criteria - N/A
label | 4d7fd03c-5476-538b-be98-52a9bb8ab4b2 |  | note | Verifying Documentation - Issued with a NTC
label | a27f370a-4985-5a59-bdcd-c60f8213b18b |  | note | Responsibility - Downer / BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.3 - For Construction Drawings Issued
label | d22e0be1-6309-519e-bcc9-9bbb230b4401 |  | note | Detail of Activity - Ensure "For Construction" drawings are issued
label | b650208e-5868-5afa-816c-c8913530ce35 |  | note | Ensure Contract is signed
label | 8c18305e-4208-5e18-95be-819718766c8b |  | note | Minimum Test Frequency - at the Contract kickoff meeting
label | 321dab2c-f953-556d-b8d2-3a0b4305fede |  | note | Inspection/Test Method - Document Issue
label | 8a14e99c-6410-5c82-b1a8-d19727f66166 |  | note | Acceptance Criteria - N/A
label | 25298f71-bd79-55f9-8a30-c433517fd933 |  | note | Verifying Documentation - Issued with a NTC
label | e9f3a47b-a013-5984-8433-46ae84d2f9fc |  | note | Responsibility - Downer/BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 100.4 - Traffic Management Plan
label | 210e46cb-cdfa-5f93-be1c-1e2fd143393f |  | note | Detail of Activity - Ensure TMP is approved and check that the requirements are fully understood by the STMS
label | 4ce22e44-7555-5522-9cb1-ff1d40e40dc7 |  | note | Minimum Test Frequency - every morning and/or when the TMP changes
label | 3e84efe5-c91c-5a52-ba4b-2c23c1e4f1e3 |  | note | Inspection/Test Method - Document and Physical works review
label | 33ce09a2-c19e-5bc5-819c-ad56b7e1bc25 |  | note | Acceptance Criteria - COPTTM
label | 278143c5-eb28-5532-ab2e-718d946d706e |  | note | Verifying Documentation - TMP from contractor
label | df50b5c4-5f65-5d56-8486-dbce00fe3e3b |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 100.5 - Design
label | 0617a8d1-51f1-5796-a611-435081b2b57f |  | note | Detail of Activity - Ensure that Design is approved and Drawings are the latest version
label | eb9005d0-be3a-518b-a6e2-03ca080e4ff9 |  | note | Minimum Test Frequency - Prior to commencement
label | f3e53d47-b28b-5b3e-ae75-ded800153bbe |  | note | Inspection/Test Method - TNZ M/20; TNZ M/7; TNZ M/24
label | 8f366595-4886-52f0-b53f-df93c6afac5a |  | note | Acceptance Criteria - Is a copy of approved consent(s) available on site
label | faf13066-3a58-524b-a8c5-43f92c1b9700 |  | note | Verifying Documentation - Check Drawing register
label | 166a8de3-7214-54a2-86a9-f7a3ddf4eb7e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 100.6 - Approved Consents
label | 2f603023-5ab2-5723-82cb-f9bf7a6687af |  | note | Detail of Activity - Is a copy of approved consent(s) available on site
label | ae372bcc-bb1f-5c46-94ed-0a233d343311 |  | note | Minimum Test Frequency - Prior to commencement
label | 24364bae-3324-5d55-813e-b06b4b650b25 |  | note | Prior to commencement
label | ba7759a3-89e5-5112-91e0-877a6cd46a76 |  | note | Inspection/Test Method - Visual Inspection
label | cefa0a2d-6b52-5271-ad8c-756fb1afcddd |  | note | Acceptance Criteria -
label | 8b075374-2d38-59d9-a074-c116e019d5b7 |  | note | Verifying Documentation - This ITP
label | 7cc1053a-3069-5fec-8843-04dd2e2ab24c |  | note | Responsibility - BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.7 - Pre-start meeting
label | e6ec85c6-7b20-59f9-bdea-e479f3f5e675 |  | note | Detail of Activity - Pre-start meeting to confirm work strategy and safety measures
label | e40ab7bd-33a7-5bc9-93e1-18954150789b |  | note | Minimum Test Frequency - Before commencing work each day
label | c0b8cf65-dcdd-55e7-9d15-c4caea5a2197 |  | note | Inspection/Test Method - N/A
label | 9641704d-dffb-54ce-92a8-575b25013732 |  | note | Acceptance Criteria - 100% attendance
label | 3bc84022-89c8-5b7e-bc59-81b437b0460d |  | note | Verifying Documentation - Pre-start sign on register / site diary
label | e92f511e-ba3c-5f9b-a00b-56bc06545e63 |  | note | Responsibility - BBO
checkpoint-status |  |  | checkpoint | 100.8 - Contractor's methodology
label | 019ade75-5865-55d2-afa3-3d3013593698 |  | note | Detail of Activity - Site inspection
label | 06eef761-6df4-5ad8-9c39-df1f74f824f7 |  | note | Minimum Test Frequency - Prior to commencement
label | 3ce1571e-81ab-5587-b623-50775ec16861 |  | note | Inspection/Test Method - Document review
label | f19428ef-6587-53f1-ab6e-16bddd43d482 |  | note | Acceptance Criteria - Methodology conforms with all relevant specifications
label | 2260e019-8ae1-51aa-9f6b-0bde354b35a3 |  | note | Verifying Documentation - Methodology submitted via NTE
label | 19c5002e-9438-5229-a19d-cbc4ba50d9bb |  | note | Responsibility - BBO's Rep.
checkpoint-group |  |  | section | Post Work
checkpoint-status |  |  | checkpoint | 100.9 - Laydown area / stockpile sites
label | cfcb6ca8-deab-5f6d-a9e5-7f004ea4a9cc |  | note | Detail of Activity - Site inspection
label | dad93464-1605-5ea6-9a76-ca3e6ed70d37 |  | note | Minimum Test Frequency - Prior to commencement
label | 0775bd7b-7ee7-5cb3-ae03-6ff9002c241b |  | note | Inspection/Test Method - Visual Inspection
label | 0ac9edfb-0cfd-54d3-bec1-44430bc11d01 |  | note | Acceptance Criteria - Approved by NZTA
label | 7455835d-ee0a-5c1c-94e6-1e5ce2ba5114 |  | note | Verifying Documentation - Request for approval (RFA) via NTE
label | 2d9a3402-767f-5a21-af6c-1e1e4583fdad |  | note | Responsibility - BBO's Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.1 - Weather
label | 052808d9-18b7-58a7-ab9a-eb6137fd0c06 |  | note | Detail of Activity - Assessment of forecast
label | 9ca2e115-efaa-5280-9d60-0a60c8c3eb6c |  | note | Minimum Test Frequency - Daily prior to and during works
label | 9b0657ee-b009-5bb0-a572-be0a7b760002 |  | note | Inspection/Test Method - Check local and national weather forcast services
label | c7af84f2-c3b5-5d35-be93-977004935b67 |  | note | Acceptance Criteria - No imminent rain or adverse weather conditions. Consideration of wind and project location/environment
label | 1b15eed5-445a-5a67-8dab-4d5972011f82 |  | note | Verifying Documentation - Contractor's site diary
label | 2b74f64c-d587-5e4b-a956-581b76f9c1dd |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 101.2 - Environmental Protection
label | d1ff1df5-6bf7-5556-a880-eb4748cda0f3 |  | note | Detail of Activity - Site evaluation
label | 475446ea-ba66-5a4e-8ef0-03b15a5631ea |  | note | Minimum Test Frequency - Prior to commencement
label | f31cf18d-1e93-56c1-b93f-c88909627801 |  | note | Inspection/Test Method - Inspection
label | c89cd882-712a-51a6-acd9-f9bd2420e281 |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | e202d083-2f84-5050-a59c-4795f620bc5d |  | note | Verifying Documentation - Contractor's site diary
label | f630990b-8c36-5ea0-87ab-7e5c4e8a0e6e |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 101.3 - Precondition Survey
label | 3aa69012-5ec8-53fa-9a2d-084df0778df7 |  | note | Detail of Activity - Examine extent of the site
label | b7025122-0e1a-58f8-bb31-f7124823168e |  | note | Minimum Test Frequency - Prior to commencement
label | f8e08d1a-7614-56e6-bff0-261e6d3141be |  | note | Inspection/Test Method - Inspection
label | 6ef3e200-1e73-50d9-bc27-a71f0d11fced |  | note | Acceptance Criteria - Supervisor assessment of conformance
label | a0341198-cd71-541b-b8b7-830e52fd1350 |  | note | Verifying Documentation - Contractor's site diary
label | 5064aab6-5d22-5e1f-a5a2-3155534f8a64 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | cc89755a-4626-5f8b-9668-e9840365e4e5 |  | textbox | Lot Verified By:
select | 9b1ea8cc-996a-5048-96a5-3958ae96409d |  | dropdown | Lot Status | Outstanding, Closed
date | daeefbd4-5d50-5673-9c97-3378ed8def62 |  | date | Lot Closed Date:
button | 73842cfa-a2b6-5922-ac94-a25562fd3a97 |  | button | Submitted to Client | Yes, No, N/A
text | 1fed631f-22b4-5631-ac5b-ac8ab893122e |  | textbox | Reviewed by Client
text | 0d5d2de0-d06b-5ec0-91eb-399ed842b441 |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | 14. Install 2mm PE liner on compound floor. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 14. Install 2mm PE liner on compound floor. | 6b365391-b67e-4c24-9983-e090ee206cb6
checkpoint-status |  |  | checkpoint | PE liner installed with Bidim A64 cloth T&B PE liner installed as per installers QA-QC and Worley’s QC requirements as per Civil /Struct Design pack 310449/C1 Rev A drawing notes T3084782 on IFC drawings issued 05 May 2023 Review installers QC documentation before placing Bidim Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 0c366490-8216-5175-b45a-90d3b377a580 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | 542211fe-ce30-5da1-98e8-e8b9cdd4fe14 |  | note | Leading Hand - N/A - Leading Hand
label | aaf3c399-a30f-512d-b180-92be8434853e |  | note | Supervisor - Leading Hand - W
label | 3d5fcd31-ce1f-54d7-852a-090e4faecd56 |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 15. Concrete pre-pour inspection Bund Walls |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 15. Concrete pre-pour inspection Bund Walls | 6ed12754-e970-4784-b522-1381f2bca3df
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 All works in accordance with CTS General Civil Construction Specification Concrete pre-pour check sheet completed and filed with ITP. General Civil Construction Specification Concrete shall be high or special grade certified “ready mixed concrete” manufactured at a currently certified plant and shall comply with NZS 3104. Delivery dockets retained. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | f2cb0bc5-42bc-54d6-b0eb-9f86abb4dde9 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas
label | b2d18204-9031-5118-9fe8-f4e9b6756538 |  | note | Leading Hand - N/A - Leading Hand
label | e8ff2228-6344-5b82-97e1-12bceb54a62a |  | note | Supervisor - Leading Hand - W
label | 33452c39-0817-55c5-926a-b8dba6d3ad06 |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 24. “As- Built” Information/Drawing |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 24. “As- Built” Information/Drawing | 76f5c50e-e1f7-4ba2-9fb7-20378c014dfa
checkpoint-status |  |  | checkpoint | CTS General Civil Construction Specification CTS QC Requirements for Civil Works
label | 2a7211a2-a378-593d-8b4e-4656c4c274bf |  | note | Applicable Documents - Section 9 CTS QC Requirements for Civil Works
label | 56f389f2-532f-5d87-9baa-398ce5d8a2db |  | note | Leading Hand - N/A - N/A
label | 4aab0fac-b204-5ed4-9153-e67a987ea182 |  | note | Supervisor - N/A - H
label | ffc98fef-dc60-5e4b-b9a6-bcf9e4a3e55b |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 17. Replace 50mm sand on top of HDPE liner followed by recovered in situ aggregate then 75mm AP40 aggregate. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 17. Replace 50mm sand on top of HDPE liner followed by recovered in situ aggregate then 75mm AP40 aggregate. | 8b01ab1b-0e63-48e1-9618-e99885c21a5a
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 All works in accordance with CTS General Civil Construction Specification 50mm sand/cement bedding clean and free of debris All layers placed to line and level. Compound floor to be graded to allow free draining to lowest point. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 2e6a09c8-6993-5389-8194-5602ed7767dd |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 CTS General Civil Construction Specification Site plan with inspected areas
label | 6553031c-1042-5d2b-9043-5383b234aa3a |  | note | Leading Hand - N/A - Leading Hand
label | db57aa83-ff43-5cf3-b0f6-c74657585f29 |  | note | Supervisor - Leading Hand - W
label | 108df430-c8d6-56a6-9cef-9f8cfe08c20e |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 1. Issued for Construction Drawings |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 01. Issued for Construction Drawings | 8b34247c-5439-4472-9287-ebcbd1681cc2
checkpoint-status |  |  | checkpoint | IFC drawings issued. Clear scope of work
label | 0e17550c-3b90-5dfc-9855-ef43c7cb476b |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023
label | 0025b9f5-2e1e-5877-ba77-6e6c932a9e41 |  | note | Leading Hand - N/A
label | 2719fd41-d2bf-5c45-a926-d5023a05af7f |  | note | Supervisor - N/A
label | 19f768bd-51ef-52a1-8084-bd01bd82e35d |  | note | Third Party (state) - P - Worley’s project engineer
checklist-flat |  |  | checklist | 9. Subbase preparation under liner around annular |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 09. Subbase preparation under liner around annular | a348413c-05fc-4bb1-ae34-db738071f45e
checkpoint-status |  |  | checkpoint | All levels and set outs as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Existing services located, marked, and protected if required. All works to be accordance with CTS Excavation works Specification. 50mm sand/cement bedding clean and free of debris Sand/cement placed to line and level. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | f553f0d2-7427-54ae-8443-7cc10c785cce |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 CTS General Civil Construction Specification Site plan with inspected areas.
label | e599ca26-b8b9-583d-b057-135a9543493c |  | note | Leading Hand - N/A - Leading Hand
label | d9a77602-d000-51ef-abfa-9aa838a45ff2 |  | note | Supervisor - Leading Hand - H
label | 0cd038ec-3b74-59b7-9391-f0398caf35d3 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 3. Waste Management/Disposal |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 03. Waste Management/Disposal | ae8803f3-b658-4b9b-8fcf-c38eca888446
checkpoint-status |  |  | checkpoint | Waste Management methodology produced by civil contractor and confirmed by CTS Environment Department. All excavated contaminated material and concrete to be taken off site. To be taken to landfill.
label | 4698783f-ec6e-5d20-bf90-cfde4c17cec5 |  | note | Applicable Documents - CTS General Civil Construction Specification CTS Containment Environmental Ground Soil Management plan RW-231
label | 5430428d-81e7-5e65-8710-db3fc5579b9a |  | note | Leading Hand - N/A - Leading Hand
label | 4ff7448e-62b3-5cce-b5ea-5dfb7e5785d8 |  | note | Supervisor - H - UCCL Supervisor or Project Engineer
label | e109757d-a898-537b-8a69-83005b7e8513 |  | note | Third Party (state) - H - Environmental team/ Client Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 26. Punch listing |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 26. Punch listing | c2a105ed-4421-4299-adee-06f489f3592e
checkpoint-status |  |  | checkpoint | CTS QC Requirements for Civil Works
label | 49cb1a04-4022-5d22-96c6-37b96b0b09cd |  | note | Applicable Documents - Section 10 CTS QC Requirements for Civil Works
label | de64f149-502e-53cd-83da-445556b73679 |  | note | Leading Hand - N/A - N/A
label | 9cab090d-73c6-555f-87a2-f027d0c2cf2b |  | note | Supervisor - N/A - H
label | f1cde280-d554-5091-9a8b-dd33dac49504 |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Photos |  |  |  |  | Yes | Photos | c556f1cf-13aa-4718-a838-a31d9944a2fb
checkpoint-no-status |  |  | checkpoint | Add photos/files here
text | 3ce42dcb-bb35-50e3-b3b8-0a55fb55dac4 |  | textbox | Lot/Area
checklist-flat |  |  | checklist | 6. Demolition scope and removal of bitumen and concrete away from tank annular |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 06. Demolition scope and removal of bitumen and concrete away from tank annular | c5b5c449-e91a-49b7-b52f-4ee9c41a04dd
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Tank annular is not undermined. Inspection once the bitumen/concrete has been removed prior to sand blinding. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 16ca7d1a-1d86-5420-8163-1f1327c742a0 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspected areas.
label | c1436631-296a-59bb-9d36-06c8f3467926 |  | note | Leading Hand - N/A - Leading Hand
label | 4bdd0229-f4d5-5c90-91e0-b401841c74d8 |  | note | Supervisor - Leading Hand - H
label | ff6de013-0554-5efc-b475-1ff0a876a43b |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 21. Sealing construction/expansion joints on bund walls |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 21. Sealing construction/expansion joints on bund walls | c60b8395-d209-496f-82cc-dab1a70a5b1d
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | a0b7ac6e-cf1e-5661-8907-f2b67beea4c0 |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Product manufactures specifications Site plan with inspected areas
label | ece80e22-d5ec-5b3a-9c10-c17d62490e76 |  | note | Leading Hand - N/A - Leading Hand
label | 780e6e13-7dd7-5ce4-9b34-342c288bb414 |  | note | Supervisor - Leading Hand - W
label | 9e605fd1-581e-5bdb-82a4-8cf8d62bcae6 |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer
checklist-flat |  |  | checklist | 5. Demolition scope and removal of bitumen/grass/concrete from compound bund walls and prepare and shape. |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 05. Demolition scope and removal of bitumen/grass/concrete from compound bund walls and prepare and shape. | d2c83746-7e65-4e7e-9054-c56ba1cd6473
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Structures footings are not undermined. Inspection once the bitumen/concrete has been removed prior to sand blinding. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 08e661d4-f80a-57ab-9115-e54cfa16dc8b |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Site plan with inspection areas inspection.
label | 43aba6b6-af31-5c18-93be-d5c79ac08e74 |  | note | Leading Hand - N/A - Leading Hand
label | 77b7d251-eed0-59f2-8e12-b81853294cda |  | note | Supervisor - Leading Hand - H
label | d0e7b2d9-6b57-5b9f-993c-264a2ef1019a |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 10. Subbase preparation under liner over compound floor |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 10. Subbase preparation under liner over compound floor | d86326af-30c2-43cf-8fb8-065249d5036e
checkpoint-status |  |  | checkpoint | All levels and set outs as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Existing services located, marked, and protected if required. All works to be accordance with CTS Excavation works Specification. 50mm sand/cement bedding clean and free of debris Sand/cement placed to line and level. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | a2913cb8-2c7c-582c-8e54-09d9bc07718a |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 CTS General Civil Construction Specification Site plan with inspected areas
label | 96d3dd03-a4b9-5f37-8d0a-efcde90447f8 |  | note | Leading Hand - N/A - Leading Hand
label | f3335744-bd4f-5506-960c-5c44f17258b6 |  | note | Supervisor - Leading Hand - H
label | 877f0df6-09a4-5fff-862b-af2fdc3ac29c |  | note | Third Party (state) - H - UCCL Supervisor or Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | 19. Sealing construction/expansion joints on tank annular |  |  |  |  | Yes | ITP T04 T06 Tank Upgrade T039/C1 - 19. Sealing construction/expansion joints on tank annular | ee753c81-42d9-4269-a3d5-b9bbc80d9366
checkpoint-status |  |  | checkpoint | All works carried out as per Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Seal manufactures specifications followed. Site plan of area inspected to be signed off by Civil inspector after each inspection.
label | 6d0d1887-62b1-51a5-ace8-4ea9133c552d |  | note | Applicable Documents - Civil /Struct Design pack 310449/C1 Rev A IFC drawings issued 05 May 2023 Product manufactures specifications Site plan with inspected areas
label | 92eebef7-1b32-547b-9452-5c828928d724 |  | note | Leading Hand - N/A - Leading Hand
label | 0ccf7b25-3d0f-50e1-8857-14d46f3625bc |  | note | Supervisor - Leading Hand - W
label | 4c9db8ea-24cb-5fa8-b929-78d41ec78849 |  | note | Third Party (state) - W - UCCL Supervisor or Project Engineer