## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
71cda829-2699-40f8-bba5-6cd9efe8d24d | checklist | ITP - Area 1 Carpark |  | Area 1 Carpark
006f5f0c-f4da-4f3c-aa95-70a5637af3c4 | section | Details
8b701483-af19-4f94-9e5f-430f4587820f | checkpoint | Inspect and prepare substrate – ensure surface is clean, dry, and free of all loose particles and contaminants.
6d27397b-644e-4e0b-9ee1-f050a7adedd9 | checkpoint | Install sealant at all junctions and penetrations.
282a58a4-f04e-49d4-84f5-8b7f4ddfa81e | checkpoint | Apply high-build epoxy (HBE) primer as per product data sheet.
5fd0ed18-1bbc-4f4f-bbb7-d38319892524 | checkpoint | Apply membrane system in full compliance with the manufacturer’s technical data sheet and AS 3740 requirements.
d29af513-56af-4b78-b3ac-1326961c48c1 | checkpoint | Execute reglet cut for vertical termination as per design detail.
1547cb8a-57ff-4a9c-888c-977b324392dc | checkpoint | Install termination flashing to vertical surfaces to achieve a compliant watertight seal.
d3e566ac-dc36-44e3-97b5-d31cef883d7d | checkpoint | Conduct ILD (Integrity Leak Detection) testing and submit final test report.
a570883b-42ff-409d-817e-98934604acf3 | checkpoint | Project close-out – confirm all works are completed, documented, and compliant.