## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d7d58dae-2b82-4d10-81b5-b9c01d6b565c | checklist | FH-927-QU-ITP001 - Site Establishment - Rev 0 | itp | ITP001 - Site Establishment
7babd8cc-c8b9-46a3-ae60-ce22fda1a40f | section | 1 - Work and Site Arrangements
c33e8a06-7540-4604-998a-d5cca9129e76 | checkpoint | 1.1 - Dilapidation and Survey Report
43faea0a-4f02-5998-96d5-65158ceddf8a | note | Frequency - Not less than 2 weeks prior the commencement of the demolition
81557e9f-7638-503c-870b-ffec0a3f8322 | note | Acceptance Criteria - Dilapidation Report for all existing roads and tracks and any other areas utilised by the Contractor for the construction of the Works proposed for use by the Contractor in execution of the Works prior to commencement of physical works on site
d967e0a8-4f5b-5fff-9070-fd7eae32d9de | note | Reference Documents - Vol1: 1211-1 & 1211-2 HP
c62df700-8dd1-5549-aab0-69a871d6aa57 | note | Inspection/Test Method - Check
580ddac5-76b5-5fd8-993f-60eb2af2c84e | note | Record of conformity - Submission of Dilapidation Report
de23d31a-efb8-543a-a72c-6026fcea8552 | note | HP
0c614a86-05ef-548f-815b-deccc9332df6 | note | Responsibility - Project Manager / Quality Engineer
b4709456-aaab-534d-ab2b-17f6072b8a7a | date | Date Completed:
38db9133-2e8d-4469-9b05-aa6eefd62751 | signoff | AUTHORITY HOLDPOINT
fdabfcc2-8aa5-4a71-ba9b-0c9d51359e28 | checkpoint | 1.2 - Site Establishment Methodology Statement
22aea52d-05ec-53a0-824b-6bb0ee361ff8 | note | Frequency - Not more than three weeks after the award of the Contract
affd291e-c444-510c-a269-156ee1bd142c | note | Acceptance Criteria - The Contractor must submit a methodology statement describing all activities required for site establishment to the Contract Administrator for approval
205838a1-b3df-5457-b4da-1f7f40910b76 | note | Reference Documents - Vol1: 1220-1 HP
d5da910b-2cc8-5978-8c39-b83c1fe67ef8 | note | Inspection/Test Method - Check
071af4c1-2e58-568a-a159-d61fdc611e02 | note | Record of conformity - Submission of Site Establishment Methodology Statement
e622e8be-68f3-5592-82b2-ac3798e8d846 | note | HP
93245cde-02e3-55e2-8600-560405bd8109 | note | Responsibility - Quality Engineer
5637f41e-c867-5097-add4-aeedf93ab673 | date | Date Completed:
d794caab-d860-4ccb-a307-689af2ef1bec | signoff | AUTHORITY HOLDPOINT
9fbde557-6d20-40c0-ad15-7f7427715322 | checkpoint | 1.3 - Water Supply
0ff966c2-a661-5ab4-b3cf-167bded05182 | note | Frequency - Monthly
d0277fbe-874a-5395-9097-f2157bf47e6e | note | Acceptance Criteria - The Contractor is responsible for installation (and removal) of the metered water supply point, the supply of the meter and arranging for the reading of the meter, and submission of the readings, monthly. The Contractor must arrange for the Contract Administrator to be present for the initial and final readings.
2923b6cb-c2ae-598b-864f-b7a724ab02d5 | note | Reference Documents - Vol1: 1222-1 HP
429ee1aa-27cf-5f5e-ab4b-f0c074a5ced2 | note | Inspection/Test Method - Check
cccb6948-dd27-5961-91f4-8e9ee76b1d15 | note | Record of conformity - Picture or formal notification
909885a1-be55-51cc-b883-b030549e86e6 | note | HP
c3dc5427-3fe6-5280-83bd-95798acadd20 | note | Responsibility - Quality Engineer
93edaaf0-2535-52eb-a9c7-9f8c63cc8d58 | date | Date Completed:
799be748-2a65-4369-a149-bb3aebb0d256 | signoff | AUTHORITY HOLDPOINT
f278ab40-5686-45f8-a4e5-0747f66fc1b7 | checkpoint | 1.4 - Plant, Equipment and Tools
ba837a56-6539-50a4-b934-eea0b536705a | note | Frequency - Prior to bringing any on to the site
6614fb93-ca75-5da5-86d5-bdc81d4dd4e5 | note | Acceptance Criteria - List of each item of plant, equipment and tools to be used in the Works including type, maker, details of general configuration, weight, maximum wheel load, tyre pressure and maximum height
7585dd3d-ae5b-5c6a-9066-fe97a2fddcd7 | note | Reference Documents - Vol1: 1227-1 HP
2b0703d0-ca7c-5684-95c8-420ec5031390 | note | Inspection/Test Method - Check
e0d5a3ce-ed7b-5a89-93a8-a54646ca4629 | note | Record of conformity - Notification
d252d5e7-4ec6-57b1-9503-9911b787a968 | note | HP
416e4559-31d5-5588-a00b-b4c2976b49cf | note | Responsibility - Quality Engineer
125d69dd-c314-5847-90f4-2429210d4f69 | date | Date Completed:
cd6e3284-3548-42ad-936d-5fec02c00ced | signoff | AUTHORITY HOLDPOINT
4421b9df-c753-4702-9b94-259b4a4b1069 | checkpoint | 1.5 - Removal and Rehabilitation
286de53c-5081-526f-8f8e-870316d2b1ee | note | Frequency - Not less than 1 week prior to commencing removal
266af119-0d40-57b8-af03-2adaaea1d6b9 | note | Acceptance Criteria - When the Contractor's compound is no longer required for the Works being constructed under the Contract, the Contractor must remove from the compound area all sacrificial crushed rock layers and geotextile liners from the Contractor's compound.
a8760931-8711-51e4-8f2b-aea59d6f5b7c | note | Reference Documents - Vol1: 1220-2 HP
b7fe46ce-b294-5c87-81a0-40d457af52e4 | note | Inspection/Test Method - Check
441bb1bd-9095-57ef-9a9c-e7c86a0878b2 | note | Record of conformity - Notification
c31a5633-e218-5c3a-b30d-f276f7850d14 | note | HP
1b879858-7cf6-5e83-8b2a-d8d7f86d2502 | note | Responsibility - Quality Engineer
3cfbfaf0-2fb1-5be5-bd79-6af10d3db113 | date | Date Completed:
dc44ea27-2aa0-4543-9f9c-ee302ab3b2e8 | signoff | AUTHORITY HOLDPOINT
394ec1a5-83c5-458f-a2e4-b31d13bd95c1 | checkpoint | 1.6 - Stockpiles
0347d3d1-f2ee-5c58-95d7-2a762224e92f | note | Frequency - Prior to commencing asphalt works
3469004e-694c-5b44-8209-8ed38568f03a | note | Acceptance Criteria - Details of the location of proposed stockpile sites specifying the maximum dimensions (including height) of the proposed stockpile, material(s) to be stockpiled, proposed separation of stockpiles and methods of management of material(s) to be stockpiled
20ab32ee-066d-5516-b932-23c940fa40a7 | note | Reference Documents - Vol1: 1230-1 HP
7b981109-428a-56de-9b5e-feba37bb5bdd | note | Inspection/Test Method - Check
e9174231-9ff5-5545-8130-8db473c7bcc8 | note | Record of conformity - Notification
fe82fe36-3d67-5b7f-b4b2-8243d3da46c9 | note | HP
c4633004-dcf0-5a55-8690-416bd6fdb046 | note | Responsibility - Quality Engineer
732e157b-5dbc-5258-8e1d-afdc6fd15e32 | date | Date Completed:
e2f59e1a-1941-47f3-adae-f7e30db8adb4 | signoff | AUTHORITY HOLDPOINT
4f992f87-acd2-47c8-a3a9-9392c609af95 | checkpoint | 1.7 - Cold Planned Asphalt Stockpiles
5f085775-e7cc-5382-b9e4-136b467f4b01 | note | Frequency - Prior to commencing asphalt works
d9416cbc-a648-5c1f-aaf8-d94bfe1190de | note | Acceptance Criteria - The location of a temporary stockpile of cold planed asphalt must be proposed by the Contractor and approved by the Contract Administrator.
8c897f97-8f18-59e7-8935-78df9dc1f01d | note | Reference Documents - Vol1: 1230-2 HP
e369b714-64c5-55ce-8f7d-5034e93b000c | note | Inspection/Test Method - Check
4ef8f664-125f-5509-904f-1281b39804ce | note | Record of conformity - Notification
d2eb52a7-e6ad-5b79-baf5-eb06432bda2e | note | HP
92399a23-9a72-555a-9a7e-607316e6505d | note | Responsibility - Quality Engineer
c76a7ece-acdd-56f2-92bc-6163ab93a9c5 | date | Date Completed:
c6b817b9-cc46-4c96-a7f6-f8666d11c9dc | signoff | AUTHORITY HOLDPOINT
e4a12b03-46a5-4f73-9271-32e963600feb | checkpoint | 1.8 - Rehabilitation of stockpile sites
35292e9b-fdad-5f3f-8c82-2886f81f0076 | note | Frequency - Conclusion of works
4bc74673-5ab4-5394-8b57-2d134a09b3d8 | note | Acceptance Criteria - At the conclusion of the Works, the Contractor must dispose of surplus stockpiled material off-site and return the stockpile area to a condition similar to that which it was found, including regrading, replacement of topsoil and establishing grass to the satisfaction of the Contract Administrator.
3acd76ba-9de0-566a-8d7a-3099c12ed599 | note | Reference Documents - Vol1: 1230-3 HP
479fc997-13ab-5aaf-8f75-e6a1a9b1cbb6 | note | Inspection/Test Method - Check
b65a3c92-4747-559c-8bb6-c0a5744fd9a3 | note | Record of conformity - Notification
8f52cbd1-f383-588a-b8fa-7ded5cb67ea1 | note | WP
81468ba9-aa56-5a8d-b16d-aeedd35e9cfd | note | Responsibility - Quality Engineer
ee0ada4d-2631-5876-9328-c031ce4849d7 | date | Date Completed:
88e2e528-b421-47ff-ab84-a5da3950f819 | section | 2 - Quality Assurance and Environmental Management
9df74e3f-9621-403c-8cc3-eae1d707c9d5 | checkpoint | 2.1 - Appointment of Project Quality Representative
469fbc5e-560e-5f67-8283-653cb419e1b9 | note | Frequency - Prior to commencement of works
c03005d5-afaa-5609-bcbf-e76f874401c5 | note | Acceptance Criteria - Submission of Details and credentials of Project Quality Representative
252557fa-43e7-5957-a873-70cff898619a | note | Reference Documents - Vol1: 1303-1 HP
c3f3f718-cb96-57da-8027-86e5d5edc19b | note | Inspection/Test Method - Check
94e83a56-02dd-584d-b51d-d301f5ffe3ae | note | Record of conformity - Notification
327a9064-c8f5-5e2e-a674-7cd89a497755 | note | HP
0e3756dd-e7f8-5da5-beb3-4231a1cdd97c | note | Responsibility - Quality Engineer
2cffc075-1289-516b-a0c7-61b4d730825c | date | Date Completed:
c1285e43-2413-41b2-948a-ec10230ed37b | signoff | AUTHORITY HOLDPOINT
08ebb289-6bb2-4166-89ad-395fe515c9bc | checkpoint | 2.2 - Project Quality Plan
28ec0ec5-7d49-5cd8-b5e5-87e944c74793 | note | Frequency - Prior to commencement of works
b3290842-2c03-51a9-a4b4-9632ad6acca0 | note | Acceptance Criteria - Submission of Draft and final Project Quality Plan
6b3e65df-a8c0-59ff-bb26-d3c00e58a802 | note | Reference Documents - Vol1: 1304-1 HP
ad5dbecd-bef2-570f-85a3-8ce064c758b1 | note | Inspection/Test Method - Check
e3c9a24d-22df-5fc0-bef5-773361699b98 | note | Record of conformity - Notification
2a5af145-d5cc-5ea6-bfb2-a4be6c95c79b | note | HP
92bd11ff-36f4-5fdf-aa5b-849b99328f1b | note | Responsibility - Quality Engineer
9eee38dd-0c7e-5865-bf8e-345ef4b5caf3 | date | Date Completed:
ac7e6280-a9d5-4b35-99c8-2d10290344b8 | signoff | AUTHORITY HOLDPOINT
087e259e-210e-4c6d-8034-0c8b33b47580 | checkpoint | 2.3 - Changes to the Quality System
43fa60c5-745f-5b2b-aa48-31d46f859318 | note | Frequency - Within 24 hours of implementing the change
aaebf8ee-d3c3-5a34-a224-2a184134a339 | note | Acceptance Criteria - Changes to the Quality System may be made by the Contractor at any time. Such changes must comply with the requirements of the specification and must be subject to the prior written approval by the Contract Administrator.
b5514f61-b9b0-5fb5-9c54-879b8d3e1759 | note | Reference Documents - Vol1: 1305-1 HP
77a4dc47-4c4f-5cc9-8178-88af5d3695a8 | note | Inspection/Test Method - Check
4af4f7ef-e046-5f31-8948-0879bdea8ecf | note | Record of conformity - Notification
e6622e9a-a10c-52c6-9ac6-b2cf2ef3f16b | note | HP
90e5dafa-95d2-5b23-b9aa-ae5cc5ac48fb | note | Responsibility - Quality Engineer
436ad682-1428-5a59-9af1-32d63c1cec1b | date | Date Completed:
be242da4-ea30-4cb4-b30c-10dcbbf2f1e0 | signoff | AUTHORITY HOLDPOINT
f48a1da4-4917-43b4-8a46-cabac6187089 | checkpoint | 2.4 - CEMP
dab6a440-ec08-5acc-a23e-1e6d9a756095 | note | Frequency - Before the commencement of work
e3e6bbfe-f3a9-5268-b114-454e9a4fca7b | note | Acceptance Criteria - The Contractor must submit and finalise a Construction Environmental Management Plan (CEMP) in accordance with the requirements of the Contract.
3dbf197f-920a-5342-ae44-7fe14044b8f8 | note | Reference Documents - Vol1: 1404-1 HP
f38438e7-09e2-5cd4-ab1d-a2a99d6a8868 | note | Inspection/Test Method - Check
dd603cdc-b37e-57cb-9384-30d5b00d3963 | note | Record of conformity - Notification
a6ed602d-719a-5b5a-a42c-7750d3a9df1a | note | HP
3979b677-a578-54e3-885f-898950f48f0d | note | Responsibility - Quality Engineer
c280f9bb-2162-544e-9a57-aa99ee7abdfa | date | Date Completed:
c9e3ed87-6b3d-410d-98d0-791a75250df7 | signoff | AUTHORITY HOLDPOINT
a31ce71b-43b6-429c-86f5-bdd84faaca08 | checkpoint | 2.5 - Continuation of Works
feb63904-2179-58d5-b498-f3eea741d42f | note | Frequency - within five (5) working days after receipt of a notice for non- compliance.
a8bd7542-78f4-502a-8562-f6f996a38b0e | note | Acceptance Criteria - Submission of a written report to the Contract Administrator describing corrective actions required as a result of a non-compliance with the CEMP within five (5) working days after receipt of a notice for non-compliance.
82e8774e-4b14-5ba0-ab77-f13c0e233c53 | note | Reference Documents - Vol1: 1408-1 HP
45a75cf3-28ca-5484-9af5-b570f864679d | note | Inspection/Test Method - Check
768008f1-90fe-5fe1-ba99-e3505572b2cf | note | Record of conformity - Notification
ae958bb6-58f6-5d33-9acc-345cceb2b367 | note | HP
42912904-d880-5f82-b986-6252d40632bf | note | Responsibility - Quality Engineer
168142c2-734f-51ed-85e6-8c8b3c9ad6d9 | date | Date Completed:
f4e06a7c-286b-4668-861d-5e0c975c2674 | signoff | AUTHORITY HOLDPOINT
916b2337-1e2c-42a2-8426-9add3e693cf9 | checkpoint | 2.6 - Lot Closure
dc1c3bee-b3b2-59b5-bc34-182b0944d1aa | note | Frequency - Each Lot
630374a2-588a-5c76-99e7-fb45ccb88394 | note | Acceptance Criteria - Lot conforms to all required Technical Specifications. Any NCR's actioned and closed out and no further actions are required.
96329f10-cf81-589e-9d30-e6608a570601 | note | Reference Documents - Vol 1: 1300
50bcc07f-5cd5-509d-b22f-8a6095c51ddd | note | Inspection/Test Method - Verify
fffd1ddb-e3c2-5ecf-bc0d-e6cd10b72e03 | note | Record of conformity - ITP Sign Off
f1166447-8ca2-5156-82d8-a9e1f6d14795 | note | IP
9c62de04-f21a-5020-9e79-2ae113cb2e2e | note | Responsibility - Quality Engineer
517cc74a-ab63-5328-8132-10f862aea78f | date | Date Completed:
44cc34ec-aa33-42e6-9b9f-a32d7f18d0dd | checkpoint | Final Inspection
d9823b3c-e41f-517b-aaaf-aa6ec4aa07ed | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
c40eed90-56d7-5990-a07d-bda8c970ef5e | textbox | Print Name:
0da4dea0-baaf-5ed7-a6a1-abe3c73661e4 | textbox | Position:
e3a6bec8-1427-5e29-93c6-b19a812ccb89 | date | Work Completed On:
e7831767-5faa-5116-847d-965a26946e09 | date | Date:
6f5ac380-ba37-4785-a7b4-651b3379263e | checklist | FH-927-QU-ITP002 - Pavement Marking - Rev 0 | itp | ITP002 - Pavement Marking
9021e3bb-347a-4a4c-9b69-6a40f6e57b68 | section | 1 - Materials
5c0f7830-0aa8-4b52-8426-7945f4b6d820 | checkpoint | 1.1 - Supply of paints for pavement marking.
e1121e8e-bb46-5abc-9f99-cc140b7a08f9 | note | Frequency - Not less than 1 month prior to the commencement of pavement marking.
e34b338b-c944-576e-899b-4ced9362680c | note | Acceptance Criteria - Submission of conformance test reports for the proposed paints to the Contract Administrator which demonstrate compliance to Section 2 of this ITP.
9b3b5292-ff08-5a31-be09-36a88cd9b4bd | note | Reference Documents - Cl 7103(b), HP7103-1
407ede10-7cf2-54a0-93fb-5b5399a2fab6 | note | Inspection/Test Method - Document
7b4df792-1ee2-58f5-8c95-073ab19e5b33 | note | Record of conformity - Aconex Submission
f9e783a3-bc1a-5836-90bf-2a0c1a61560d | note | HP
a4506be2-225a-52b9-a51b-5a1a0b229268 | note | Responsibility - Site Engineer
3e82c557-21bd-5729-a028-43a33bbb71fe | date | Date Completed:
5afdf377-086d-4407-b81d-7814c5ae2c13 | signoff | AUTHORITY HOLDPOINT
ee507440-5527-4fbf-be79-4c000b656263 | section | 2 - Paint Properties
48c5af91-b240-4c26-a896-c3296cc67e1d | checkpoint | 2.1 - Runway marking paint and taxiway and apron marking paint type and packaging
d92c67d0-e904-56dd-a525-d3ab779fd59a | note | Frequency - Prior to the commencement of pavement marking works.
c63eb9eb-ffe6-5401-903d-f7b10e75f9c6 | note | Acceptance Criteria - Paint is pre-mixed acrylic co-polymer water-based paint, packaged in 20 L containers. Containers are of durable construction and labelled with manufacturer's name and a complete description of the contents. Paint is of a consistency suitable for application by brushing and spraying, and capable of being used as supplied or diluted with water.
9bb2477e-0dcb-528f-9be9-33a3ff2fdf39 | note | ○ Dilution information and coverage is stated by the manufacturer on the packaging.
3be5cd32-71a6-5842-82de-0f64d8511821 | note | Reference Documents - Cl 7103(a)(c)(d)(h)
2c98bfcf-7644-5406-a810-0b3a2f7c7089 | note | Inspection/Test Method - Inspection
faac731c-949d-5adb-b5dc-318cd8aeefb7 | note | Record of conformity - This ITP signed by Contractors Quality Representative
60e3dab6-76e2-5973-b5bd-21f16f88c3d8 | note | IP
724ec473-a627-572e-9d54-48eae7d0b6e0 | note | Responsibility - Site Engineer
755f33d9-1471-5aa7-a23e-4e461f3aa08b | date | Date Completed:
d233ca95-739d-4b21-95d4-3fb2bc55af06 | checkpoint | 2.2 - Condition upon delivery
9faef112-26e7-5c20-9d0c-e7f2a54c8277 | note | Frequency - Prior to the commencement of pavement marking works, at the time of delivery of paint.
c20b677c-51b3-57a2-8c80-28621ffacdd2 | note | Acceptance Criteria - Hand stirring of the paint readily produces a smooth uniform product.
3e786e2d-1bb9-5ea1-b565-1d0b5d60c09e | note | Reference Documents - Cl 7103(f)(g)(i)(j)(k)
de816b3b-fa7d-58fc-a0c9-497a44562b1d | note | Inspection/Test Method - Inspection
ef040c5f-de3d-56ec-88cf-4edc788de082 | note | Record of conformity - This ITP signed by Contractors Quality Representative
1274aaa2-f680-5f38-b2ce-2e330d79c5ee | note | IP
265058e5-47fc-5fb1-aa73-6ab802c5ecff | note | Responsibility - Site Engineer
9d210c0d-73b8-5903-8ce3-496a05e412cd | date | Date Completed:
3776d6c2-674f-468c-9084-08f14b41b474 | checkpoint | 2.3 - Paint Surface Finish
a2d2e530-ef5f-5b83-bfca-f05941eaa69d | note | Frequency - Prior to the commencement of pavement marking works.
d82ab70b-a118-5f99-a77a-759477a69b43 | note | Acceptance Criteria - The dried surface of painted areas on aircraft aprons is not slippery under foot. The surface finish of the dried film of paint is a non-gloss matte finish.
56ac6b53-5515-5103-9be6-194da6e17e6e | note | Reference Documents - Cl 7103(l)(m)
4dc3bc42-e8fb-51dd-a21f-51257e1c39ed | note | Inspection/Test Method - Inspection
4a45421c-c206-522c-9d3b-812d180881c4 | note | Record of conformity - This ITP signed by Contractors Quality Representative
d9b0375d-9dfc-5460-8ee0-0b818300c92e | note | IP
602fffad-afa7-5399-a4c0-d0f416cbf2ab | note | Responsibility - Site Engineer
f00cbd28-fdd0-5f48-9f4d-03c0977eac70 | date | Date Completed:
1566ffe2-ce47-40d3-8d24-5f6963940e75 | section | 3 - Trials
be6c6d5d-238c-4223-abe9-1a9078dc6a13 | checkpoint | 3.0 - Demonstration of process and equipment for removal of pavement paint markings.
7fd890f2-e66a-55d4-a4c8-ffc99991d8a8 | note | Frequency - Not less than 1 working day prior to the commencement of full-scale paint removal works. Prior notice (24 hours minimum) of trial to be given to Contract Administrator.
a65e6be2-e0a7-5bfc-bf75-256ffae03a13 | note | Acceptance Criteria - A trial conducted in an area agreed with the Contract Administrator of not less than 5 m2 demonstrates removal of pavement marking without chemical methods, without causing disintegration of the pavement surface and in compliance with the requirements of Section 4 of this ITP.
1ea04001-6641-54a3-bba9-9e9bce6ada87 | note | Reference Documents - Cl 7104(f), HP7104-1
140dc713-dd07-5825-afc0-1f533a173e22 | note | Inspection/Test Method - Inspection
67b74b49-b1d2-5ad1-b813-480e0e560d1f | note | Record of conformity - This ITP signed by Contract Administrator
cbf7587e-4a85-5ce6-a6a3-1e369a6689b6 | note | HP
21340322-efba-54c1-bb9c-0e8b4a75ad1d | note | Responsibility - Site Engineer
231def4b-093a-5505-a8c0-a3e80163ae19 | date | Date Completed:
2ea671f6-b46f-4e3f-b4b6-c24006ce8048 | signoff | AUTHORITY HOLDPOINT
a374aa73-66a6-48dd-aaaa-c4f5587642d1 | section | 4 - Removal of Pavement Paint Markings
f08ea855-23d4-4082-962a-5ef9938fed51 | checkpoint | 4.1 - Plant Performance Check
6fd6c66c-522c-521d-b43d-c555cb9ad7ae | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
aaec9f4e-f4fe-5a1e-a7ca-22d77206bd7d | note | Acceptance Criteria - All plant is in working order, free from leaks, and capable of removing all paint from the pavement surface without filling voids with debris, removing joint sealants or otherwise damaging the pavement surface.
8e2d74a6-3126-5406-800a-522ff9c5aaad | note | Reference Documents - Cl 7104(b)(c), WP7104- 1
2edb2795-aaf2-549c-a941-391b471f566e | note | Inspection/Test Method - Inspection
71436ee5-df44-5cb7-a6a4-8bae3057bd5e | note | Record of conformity - Daily Plant Verification Checklist / This ITP signed by Contract Administrator
6c2ed108-0918-511b-a2ef-9c3e0ddae5fd | note | WP
5527735a-e55b-5e58-9015-4ffa64cf3449 | note | Responsibility - Site Engineer
814d688b-95aa-5d76-94c7-85d7615c26af | date | Date Completed:
2a25c58b-53a4-4397-ac57-2a9b1993776e | checkpoint | 4.2 - Weather Conditions
e1ed1375-ef6d-5e08-9013-f3fec14f6c76 | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
3d7cab71-a4df-5d93-9e65-9570386346d5 | note | Acceptance Criteria - Pavement surface is free of snow, ice or slush, with a surface temperature of at least 5oC and rising at the beginning of operations (except for where shot- or sand- blasting is used for which a lower surface temperature may be accepted). Work is not occurring during a thunderstorm. Work is not occurring during rainfall, except for water-blasting and removal of previously applied chemicals.
d1526695-993b-5001-9ef0-bdab2471b4d0 | note | Reference Documents - Cl 7104(e)
a83c778e-7ff6-53f7-bda5-6d12e3ac57ca | note | Inspection/Test Method - Inspection
3a334b7a-56aa-520b-bd5f-bc4e3f735afc | note | Record of conformity - This ITP signed by Contractors Quality representative
de25f33f-5853-5bb4-8bf1-380ba0fae476 | note | IP
6415efe4-ed69-5407-bb31-3af986007cc3 | note | Responsibility - Site Engineer
22b31772-6cb9-595b-a9e0-a5c6eeeed00b | date | Date Completed:
f11e319b-72d9-4d3a-abc4-ab762f4c849d | checkpoint | 4.3 - Surface Texture
2f0194c1-3128-5167-bd97-36adff1f211f | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
5e41bf13-54a9-5e3a-9b90-de3811965c89 | note | Acceptance Criteria - The surface texture of the cleaned removal area is comparable to a standard area of pavement in the removal trial area selected by the Contract Administrator.
56bf7701-f19c-5304-a15b-99c9853bcd57 | note | Reference Documents - Cl 7104(f)
b2e27adc-f548-5230-b711-e04eda40f4ca | note | Inspection/Test Method - Inspection
054f5682-fd2d-5dd5-ad8f-f91ba33d131b | note | Record of conformity - This ITP signed by Contractors Quality representative
c008bf20-529a-5138-9af5-18e672383547 | note | IP
4356a79a-546d-52e8-961d-043e7de317bd | note | Responsibility - Site Engineer
87093b31-de11-5f72-9b01-95b4b26f61d6 | date | Date Completed:
3fc108c7-e383-4d01-94ef-2b70eed8b90b | checkpoint | 4.4 - Clean up and waste disposal
0fd64ea0-e430-5a1e-bc31-961d4e42e0fc | note | Frequency - At the completion of paint marking removal work in each work period.
ba192bf8-cdd5-5e5a-bfd6-681f3611e528 | note | Acceptance Criteria - Debris and waste materials have been collected, removed from site and disposed of at an appropriately licensed waste disposal site.
e4751505-1cdf-58e6-8c66-099ec13790e1 | note | Reference Documents - Cl 7104(f)
2c9df90a-79a7-55b8-a1bf-b3433f1c31c7 | note | Inspection/Test Method - Inspection
ca18c8fd-b938-54aa-b6a1-ca03d65ab327 | note | Record of conformity - This ITP signed by Contractors Quality representative
b01c8491-2ca6-5841-bde6-08f3e09010fc | note | IP
bfebdaeb-ee1b-5539-9b3e-202e508af1f2 | note | Responsibility - Site Engineer
64a8b768-86ad-5d2a-a972-4796306486e4 | date | Date Completed:
73d85883-11ee-48bd-bcea-c767287049a6 | section | 5 - Application of Pavement Markings
b66fc8fe-7573-4b47-9d74-7990595f75a2 | checkpoint | 5.1 - Setting out of pavement markings
1254e53c-72a1-5b31-896a-d86cc279ddb8 | note | Frequency - At the completion of setting out and prior to application of pavement markings. Prior notice (minimum 24 hours) of commencement of setting out is given to the Contract Administrator.
a628cc16-a9e4-59fc-8cb2-22c3b1c76a00 | note | Acceptance Criteria - Survey for setting out new pavement markings has been completed as shown on the Drawings by a suitably qualified surveyor, to a horizontal accuracy of ± 25 mm. Spotting indicates the location and extent of new markings in sufficient detail for the painting of the required markings to the tolerances specified.
68dbe0be-89da-56ed-9eb6-75015e92f3b0 | note | Reference Documents - Cl 7105, HP7105-1
d4ac2d27-d024-527c-b575-dbc0bd0eeb5f | note | Inspection/Test Method - Inspection / Statement of complianc e by contractor s PQR
e56b0ef2-edda-5317-a148-d5ea781099e4 | note | Record of conformity - This ITP Signed by Contract Administrator
9ead7e50-d16f-5ffb-b143-ac75e53f179f | note | HP
a5ce3d8f-2c8e-55cd-b42b-81d46d92b67f | note | Responsibility - Site Engineer
f9fc8204-cb29-5cdc-81c5-4dbb2f484466 | date | Date Completed:
07e7c35f-a625-43d5-890c-6076c55e6122 | signoff | AUTHORITY HOLDPOINT
b84672dc-9474-4f48-bb2e-2cb25787fd05 | checkpoint | 5.2 - Surface preparation
d38a937d-e1e6-58b8-93e4-efc2ff759c03 | note | Frequency - Prior to the commencement of pavement marking in each work period. Prior notice (minimum 24 hours) of the commencement of pavement marking is given to the Contract Administrator.
e6d8cfe4-0a42-5eae-b510-71e61d940f2e | note | Acceptance Criteria - The surface to be painted has been thoroughly cleaned using vacuum sweepers, hand brooming, and/or high pressure water jetting as required, and all existing paint not strongly adhering to the pavement has been removed.
ab83bab6-0e5b-59cc-91ed-92a2d16564f4 | note | Reference Documents - Cl 7106(b), HP7106-1
cf66a919-2d94-5213-8bb0-e5f5a227cfda | note | Inspection/Test Method - Inspection / Statement of Complianc e by Contractor s PQR
59440c99-f69a-5b62-b05d-134cc9a2c4a5 | note | Record of conformity - This ITP Signed by Contract Administrator
25abbe96-b4f0-5db7-8a02-7b758fd0614f | note | HP
9e872a1c-e60e-5d8e-8b6b-55bed65a3c5c | note | Responsibility - Site Engineer
c64c28eb-50d0-5ec5-8d86-d49d56efe697 | date | Date Completed:
85c5ca23-797e-428e-9a12-b1a9a62980f7 | signoff | AUTHORITY HOLDPOINT
07d7d1c7-696e-41c6-a424-b79cd80ff294 | checkpoint | 5.3 - Weather conditions
98d48d6d-9469-5bfc-bce8-b69b74273873 | note | Frequency - Prior to the commencement of pavement marking in each work period.
d98e2c34-c3e5-5650-bcf4-d0e9ce4a3078 | note | Acceptance Criteria - The pavement surface is not wet and wet weather conditions are unlikely during the work period, the air and pavement temperatures are not less than 15oC, the relative humidity is not greater than 85%, the wind speed is not greater than 20km/hr, and wind conditions are unlikely to affect the application of the paint.
3606e0a8-6793-5aba-843a-b29b6e464de5 | note | Reference Documents - Cl 7106(c)
78b5db06-e8b5-51f9-919c-dde7de37335b | note | Inspection/Test Method - Inspection
f1b4b365-c955-55a0-9c2e-3d79d6162ce9 | note | Record of conformity - This ITP Signed by Contract Administrator
45cb75b5-110f-593f-ad93-061d8a7883c8 | note | IP
66f900ed-a9e1-5ed0-8394-dcb7b0e0b801 | note | Responsibility - Site Engineer
76172c38-a55f-5237-abd3-130dfa12131b | date | Date Completed:
fdb94963-0f14-4a4b-9a0a-a58e9e3ab121 | checkpoint | 5.4 - Pavement marking adjacent to in- pavement light fittings
44d5b57e-6b9e-5cce-955d-80cce72f4e11 | note | Frequency - During pavement marking works.
c48f1128-f027-529f-aba7-fa5d91b5e4cf | note | Acceptance Criteria - Any in-pavement light fittings in the vicinity of pavement marking works have been protected to avoid contamination with paint. Markings in line with light fittings extend to the edge of the fitting but not on to the fitting. The gap between the end of painted line and edge of a light fitting is not more than 25 mm.
22d6b35e-2633-52e1-ae9f-a3a1aeb926c9 | note | Reference Documents - Cl 7106(d)
e1b1eb9e-6f61-5d1c-85ce-90fb4ff92404 | note | Inspection/Test Method - Inspection
8bd6f016-6523-54f6-acd8-55fdad63ec9f | note | Record of conformity - This ITP signed by Contractor Quality representative
ab65aae3-6cf8-5a2e-99e8-5b3910990556 | note | IP
837506d2-15df-5c39-b5f9-4cd464f38eed | note | Responsibility - Site Engineer
673a4202-d0c7-5147-85eb-522edcdd7fe0 | date | Date Completed:
d55ea4a7-70a6-46ad-aacf-70b47e76e6fe | checkpoint | 5.5 - Application of Paint
0a53e44e-2f2f-518f-9159-8a62ec02a034 | note | Frequency - During Pavement works.
1b33b657-51e4-5de5-b349-c6853960fd58 | note | Acceptance Criteria - Paint is applied by spraying, except for small markings, isolated repairs, and stencilling of letters and numerals where brushing is permitted. Paint is applied in 2 even coats to give a minimum total dry film thickness of 120 µm. The edges of markings are straight or smooth even curves, with crisp even lines without side spatter at the edges and ends of markings.
bee329f3-683a-5bcf-ad50-28096441abcd | note | Reference Documents - Cl 7106(d)
e81732cb-f019-533c-abca-4953b29dedbc | note | Inspection/Test Method - Inspection
297eb5cd-ff3e-5667-9fba-6108e17e21f7 | note | Record of conformity - This ITP signed by Contractor Quality representative
b7da4b94-a0d0-5f51-bd40-d1a8b2d45371 | note | IP
c7ea825e-1938-56ca-9e06-f7c951c97f72 | note | Responsibility - Site Engineer
02f2039e-512d-5728-b519-ddcd6c9ccff7 | date | Date Completed:
8e24ba86-5355-4bd7-a707-62b64ba42d46 | checkpoint | 5.6 - Application of glass beads
c7ba8d42-eb1f-5a6a-a837-753b05d9f3c8 | note | Frequency - During Pavement Works.
3c6dbdd0-e160-54f6-97b9-8cb18868ba30 | note | Acceptance Criteria - Glass beads are not used on any pavements with the exception of areas specified within standard MAS- CVL-002 for Pavement & Pavement Markings (Airside). Where glass beads are specified on taxiway pavement markings, the minimum application rate is 300 g/m2.
2cdfa2ab-7768-57fd-b8e0-a783632edb7f | note | Reference Documents - Cl 7106(d), SP7103(n)
2661031b-569b-53d6-987a-316e0291fb13 | note | Inspection/Test Method - Inspection
4b6d42da-dcef-5bf5-a23d-e2d86ed3a132 | note | Record of conformity - This ITP signed by Contractor Quality representative
0dca6233-46bd-5b37-b02b-6b4af0d41382 | note | IP
1775200c-f43c-5b00-aee9-7d2c1dedde69 | note | Responsibility - Site Engineer
a5a06d77-9a9e-5766-9fb9-b69dccfe2372 | date | Date Completed:
bcc87495-a0c1-427f-916e-2d9df6c753e5 | checkpoint | 5.7 - Paint Application
892f6c06-0c3e-5764-b5fe-5ddc0450c780 | note | Frequency - At the completion of paint marking removal work in each work period.
740bb1f7-04ca-5782-bcb4-2624c8b3c286 | note | Acceptance Criteria - Paint usage and area of coverage for each work period are recorded.
46842592-312d-529a-ad05-f247adbcedf9 | note | Reference Documents - Cl 7107
b2b43e49-f396-5fca-8c8d-3c70bb2cb050 | note | Inspection/Test Method - Inspection
e1b0f966-4a0d-5549-a0c2-4479bb5163ad | note | Record of conformity - Daily Shift Report.
08e5ddac-52f1-5a43-9b80-f29c2ba26e45 | note | IP
e0524375-a145-51b3-84a8-98736e315a99 | note | Responsibility - Site Engineer
dd277837-dbc9-5e7f-924c-a2df4eb577be | date | Date Completed:
49ce66af-c0da-476f-8b74-ad76be6ff393 | checkpoint | 5.8 - Daily records of Paint Usage and Area covered.
5281a257-049c-58a4-a9af-8be23b828124 | note | Frequency - Each shift
0246511f-fbe2-52f0-8e6e-1451d3a3c793 | note | Acceptance Criteria - Daily records of paint usage and the area covered must be maintained by the Contractor to ensure that the specified application rate of the paint is being achieved consistently.
97dde519-66ca-55bc-bc5a-b810b55ccba5 | note | Reference Documents - CL7107
366b2cf9-f859-519d-9a23-1c310b245ad7 | note | Inspection/Test Method - Review of Daily Records.
5ed82264-d2c9-5300-8d99-1d754c993246 | note | Record of conformity - This ITP Signed by Contractors Quality representative.
9b557ef3-8df3-5a4b-9214-afb3305b251c | note | IP
faf3b611-99e6-5923-95c5-6f545cc66575 | note | Responsibility - Site Engineer
acef21dd-eee1-568a-a0b6-16ce7a3adf46 | date | Date Completed:
3f1c8687-750b-45a8-989a-1b94264d5998 | checkpoint | 5.9 - Lot Submission for Pavement Marking
85b4e7a6-aa53-5192-b32f-93a61816e0b7 | note | Frequency - Per shift
b14a8bed-b3fa-5e7a-9bbd-95045d84a3ee | note | Acceptance Criteria - Submit detailed information for each shift. Details include location, test certificates etc.
2d346bf1-ee85-5523-beec-a2e8fe3b287a | note | Reference Documents - Method Statement
e9af6895-92a5-5468-8764-b6954faec8f6 | note | Inspection/Test Method - Review of Lot Submission details
eb3f6070-1b11-565a-bd42-886aeb29648a | note | Record of conformity - Lot Submission documents submitted to Contract Administrator
15cacba1-e0b6-5c52-8728-949f6eb2cd21 | note | WP
84e227d5-0d97-511a-9abd-d40f7b4f0d52 | note | Responsibility - Site Engineer
f27075c9-a846-5328-ac2c-d54890832947 | date | Date Completed:
193f4b85-49c0-4362-9706-fae894f3f0fa | checkpoint | 5.10 - Removal of Non-conforming Pavement markings
032938c2-65c2-5ddb-b451-10953afdd1ad | note | Frequency - As required
9e42e32d-1d5a-5d67-b394-eaeb8f55c885 | note | Acceptance Criteria - Any pavement markings that do not comply with the requirements of this Specification must be deemed non- conforming and must be removed by the contractor in accordance with the requirements of Clause 7104 and reinstated.
ecfc8239-2a26-52b2-b2c5-7f021660ca58 | note | Reference Documents - CL7108
b44d3554-a993-5d71-a494-64c90b19ca2c | note | Inspection/Test Method - Verification of Removal
1ca70729-c1c7-55ef-81de-d733eaeacaa6 | note | Record of conformity - This ITP Signed by Contract Administrat or
c578c4ba-4c8d-5c17-ab5d-1beeb4db9f16 | note | WP
7578c95d-81ba-5f05-b92f-72a93e675ac6 | note | Responsibility - Site Engineer
2061de2a-a666-5030-af2f-872ed12f776d | date | Date Completed:
8b27fdf6-c363-401d-a9a0-9c83b419f012 | checkpoint | Final Inspection
ce8831f9-27db-5240-a899-378274ffc904 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
b6cd69c6-7965-5549-9e22-79a58662cf5a | textbox | Print Name:
867e8be6-fd99-5b00-b4d0-a7b0598312b3 | textbox | Position:
07819e95-5fda-5719-ae78-26e7cab46833 | date | Work Completed On:
51297cef-58c2-5e95-a656-ccdcb037d33e | date | Date:
9ce03912-5c9a-4f30-b0b6-4f5e09733cdb | checklist | FH-927-QU-ITP003 - Surface Rejuvenation - Rev 0 | itp | ITP003 - Surface Rejuvenation
9705a555-f101-4905-9708-e94c264880e8 | section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
abcf9e9f-e27e-4d3f-adc4-b69adb2e6713 | checkpoint | 1.1 - Check for correct documentation
85d0a6f6-1c70-5a64-ae0d-bd49a9d0c191 | note | Frequency - Prior to commencing any activity
faeab320-3ee7-5388-ae03-adea86fe30d7 | note | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy.
50e37505-28f3-5228-912a-54368f0265c4 | note | ○ Current revision to be obtained via Aconex.
81d4d525-a335-5569-a632-e4f73752b815 | note | Reference Documents - Drawings and drawing registers on Aconex
18ecd4d5-7f84-5bd0-84ad-c4fc5545edf4 | note | Inspection/Test Method - Visual inspection
29315a2f-a074-59e1-96df-b6bffcc3431f | note | Record of conformity - This ITP signed by contractors Quality Representative.
7887bf89-0d56-5984-9c9d-ad5dd248cdbe | note | HP*
e3ad0633-181b-5597-abfd-e437b5600e48 | note | Responsibility - Project Engineer
c616fbe2-6551-53eb-91cd-1327cc2088c4 | date | Date Completed:
1b8e8999-d59e-4eb7-9eb8-e89df03f4460 | checkpoint | 1.2 - Implementation of all measures and controls
1e7348ef-8e80-5df6-bb26-1537a38c5657 | note | Frequency - Prior to commencing any activity
d2b4acef-2ad5-5a5a-ba3d-bbd211a2b1a6 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
f7e4f864-3c44-578d-b90f-eee188f8d8a8 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
3780820d-dde9-587d-8e88-12762e84f2ee | note | Inspection/Test Method - Visual Inspection
600cef63-e3be-59b5-95f1-873ac7bb12c8 | note | Record of conformity - This ITP signed by contractors Quality Representative.
45766f02-c446-5ce9-8d96-469ecd686914 | note | HP*
dca29e69-229b-5f51-a94c-abc1fce79851 | note | Responsibility - Project Engineer
d9e56ec1-5d79-5e7d-9cbe-43b7196d6e96 | date | Date Completed:
fac222ce-2189-4215-9146-961821e8434c | checkpoint | 1.3 - Definition of the work area
c8b3bfaa-cd51-5e32-9609-48fae847be9a | note | Frequency - Prior to commencing any activity
0f816db6-f26b-5090-97b3-2175236ab47a | note | Acceptance Criteria - Work area has been cleared and limits of works defined on site.
d0fbd8a1-6156-504a-a66f-0acf1de218eb | note | Reference Documents - Drawings
6c5c7773-bb65-5c62-913e-6e7388256be2 | note | Inspection/Test Method - Visual Inspection
d3deb857-ec54-5ff4-b372-2d1c7550a744 | note | Record of conformity - This ITP signed by contractors Quality Representative.
08445fb9-ac0e-5b98-acb5-ddee96bb3727 | note | HP*
dd55079d-9325-56c3-88a6-70af477d18fa | note | Responsibility - Project Engineer
de1b3b25-d65b-5a3e-8f1b-5f6f956bb766 | date | Date Completed:
2dbaa836-4882-42a3-8d69-56a60d3525f7 | section | 2.0 - Plant, Tools Equipment
2a54c27f-e103-4279-89a2-fb14750aa0d1 | checkpoint | 2.1 - Plant, Equipment and Tools
45fbe457-ad87-5aa5-9099-8bdcd77489ac | note | Frequency - Prior to commencement.
fab5695c-26e6-5e2e-b29d-21c9a61c85fb | note | Acceptance Criteria - List of all plant, equipment and tools to Contract Administrator prior to commencement of Works.
3a88df02-09e2-51b3-baaf-4c42caf72d4b | note | Reference Documents - Cl 5605-1, WP5605-1
6b6e16cb-fd45-50c8-9418-4fb3f8417481 | note | Inspection/Test Method - Visual Inspection.
081a18bc-d607-5f04-bb48-6c9c6f3bbe18 | note | Record of conformity - List of all plant equipment and tools to be submitted to Contract administrator.
b3168d70-a02e-5c22-92b5-28f20f0e4059 | note | WP
813df316-8e55-57f5-90fb-a5ed24c29c88 | note | Responsibility - Site Engineer
014ff7e0-debe-59c6-9d68-5fc611610a47 | date | Date Completed:
c7634c78-f084-4cc2-b29e-f28593d0911b | checkpoint | 2.2 - Stabilised Calibration and demonstration of spraying equipment
871d072a-33a2-59a9-b8d5-5933f17294af | note | Frequency - 7 days Prior to commencement.
007d38a4-1898-56f0-92be-9c614dcd49cc | note | Acceptance Criteria - The Contractor must demonstrate to the Contract Administrator prior to the commencement of work that the spraying equipment complies with the Specifications.
cc9c406c-d5ac-5ed3-8985-24b82e24398b | note | Reference Documents - Cl 5605-1, HP5605-1
8dbebdb4-435c-52f3-8bd7-14fec3da38a6 | note | Inspection/Test Method - Verify
96fd43bb-ac12-52fe-a399-2cd919b20b60 | note | Record of conformity - Aconex Submission/This ITP signed by Contract administrator.
de301d42-3389-5842-9a9a-90c684419786 | note | HP
1c06fd08-e845-551c-b93b-f10d554541e1 | note | Responsibility - Site Engineer
c94e6401-7a53-556f-a2f1-73cb3949f208 | date | Date Completed:
0fa59cfa-feec-4b27-9c7b-92803ce70e31 | signoff | AUTHORITY HOLDPOINT
1fbe42d1-ec5a-4721-996e-1522a8b235d7 | section | 3.0 - Weather Limitations
71284bcb-1e23-42ad-b51e-364a0e3453e1 | checkpoint | 3.1 - Intention to proceed with works
d72eeb4a-5bad-5417-8bbb-a70a2a47efc0 | note | Frequency - 24 hours prior to commencement of works
61a19d8a-e887-54ec-a5b0-da5cc05cca36 | note | Acceptance Criteria - Written intention to proceed with the Works and on what basis this decision has been made, at least 24 hours prior to commencement of works.
3cb4477d-72e4-5470-8856-56fb04d1d7d4 | note | ○ Application of the rejuvenation material must only proceed when the pavement temperature is above 15 °C and rising.
06259747-5e07-5ebc-80c2-bb700a2064be | note | Reference Documents - Cl 5606-1, WP5606-1
82d3dd21-e36a-54ca-a311-4fb50962674d | note | Inspection/Test Method - Notificatio n
ce0889e9-32cf-5fbc-b58c-a81754b2fb2b | note | Record of conformity - This ITP signed by contractors Quality Representative.
560b1b11-431b-5cf6-8a85-3277d8baac50 | note | WP
0375a004-1c19-523d-8b0b-6dd352d1ea68 | note | Responsibility - Site Engineer
8efe1e37-fb30-5976-bf29-9b0f590377b3 | date | Date Completed:
f4c8328c-3b16-4428-aa5e-40c19459ce3f | section | 4.0 - Preparation of Surface
27cd2ea9-f648-419e-a708-e7658bc1f841 | checkpoint | 4.1 - Inspection of Surface
490edd98-1b8c-53a8-a6a4-92fda5929517 | note | Frequency - 24hours notice prior to commencement of works
75ce3441-355f-5230-b0c4-eacaee5a75e2 | note | Acceptance Criteria - 24 hours’ notice to the Contract Administrator for inspection of the surface to be rejuvenated.
24ddd71c-4825-5978-bb90-76d47aeaee07 | note | ○ Prior to applying the Rejuvenating Material, the Contractor must prepare the pavements surface. This preparation may include but not be limited to:
c786cde6-dbe9-5d2c-b897-2ba45ad414cc | note | — Sweeping those areas of the surface contaminated with accumulations of soil, silt or other foreign and/or loose material.
70029f8d-5585-5b50-b53c-8c8aa1413c28 | note | — Protecting all airfield light fittings and other structures and abutting concrete by suitable means.
2a6fd62f-5b3a-5352-b9d9-01b6d42720be | note | — Protecting all pavement markings by suitable means unless stated otherwise on the drawings.
7e1a24a4-047a-5529-8423-dfb2bdf67d6d | note | Reference Documents - Cl 5607-1, WP5607-1
92a37058-bf3e-5a4a-805e-93b9cbb5d4fe | note | Inspection/Test Method - Verify
7dc2ab5d-a41d-50a0-9e75-56c2013c3620 | note | Record of conformity - This ITP signed by all parties present including contractors administrator
58fa861e-0958-57a8-8d0d-0ea108eb4315 | note | WP
8e1b42fa-ab4f-5528-87a9-5aea927e8310 | note | Responsibility - Site Engineer
2e710d58-b05c-5c03-b26c-440eb3d5140b | date | Date Completed:
35a1927d-2a7a-43b7-bb99-5b07ffa531de | section | 5.0 - Application of Rejuvenating Materials
acc9c28c-3b00-42e6-86a9-431ab8ec0275 | checkpoint | 5.1 - Transport and Storage of Rejuvenating material to site
e15ab493-190a-5717-824d-7cf844f04289 | note | Frequency - 7 days prior to transporting rejuvenating material to site
ecfd8145-b7bc-571a-8153-425a16290494 | note | Acceptance Criteria - During construction, the contractor must submit records on the transport and storage of the material on request by the Contract Administrator.
9ac75f65-37ec-55ae-b54f-95d2e45bad56 | note | Reference Documents - Cl 5608-1, HP5608-1
460d763b-91d0-584a-9f4e-0a5c99342244 | note | Inspection/Test Method - Check
17458c45-8faf-5a57-aa8c-298a9e50e09a | note | Record of conformity - This ITP signed by contractors administrator
e2e65d0b-059d-5c81-92b7-2e85f0e12468 | note | HP
6506edd1-ad3c-570a-9e5c-8814f8c26d75 | note | Responsibility - Site Engineer
5ba3cb1e-6eff-5ddb-a214-6eea772b8e4e | date | Date Completed:
e225fa32-a316-46bf-a7b0-bb99e5739d5b | signoff | AUTHORITY HOLDPOINT
54667830-26d7-43f6-930a-fd5b6b7ea60f | checkpoint | 5.2 - Application of Rejuvenating Material
b3483d85-4bb5-525f-a69c-feb7af5c9c5f | note | Frequency - 24hours notice prior to commencement of works
78437f0c-f0fb-539f-997b-ac487f3061c7 | note | Acceptance Criteria - The Rejuvenating Material must be applied only in the presence of the Contract Administrator. Rejuvenating Material must only be applied using a suitably calibrated sprayer/applicator.
c247450b-bee8-52ce-848c-99c11edb43b0 | note | ○ Before each run is applied, the Contractor must mark out the pavement with removable markings to guide the sprayer when applying the Rejuvenating Material to ensure correct application.
797df7bb-a507-5247-8ace-a11c8c2f8724 | note | Reference Documents - Cl 5608-1, WP5608-1
95685c65-b25b-5855-b3da-4b1785410410 | note | Inspection/Test Method - Verify
8e918f34-7585-5dd4-a110-fe69e254de1b | note | Record of conformity - This ITP signed by all parties present including contractors administrator
9a9f7a3a-a36b-545a-bbff-ac1b9c07a12e | note | WP
6e862f0d-d221-58aa-9346-52d7e24caf43 | note | Responsibility - Site Engineer
79b46588-f5a7-59cd-9da3-b3902c1f72f0 | date | Date Completed:
a3cd644c-52f7-4fbc-85f4-b3e75753ddc7 | checkpoint | 5.3 - Application rate
50b08a10-dc88-5044-96a7-2b39c0df17e4 | note | Frequency - During
3dd11fe5-9a01-5920-8f5f-87cde213da14 | note | Acceptance Criteria - The Rejuvenating Material must be applied at the application rates indicated as per the specification.
650a0efb-19a9-5f85-a6f7-f70300fe8ff7 | note | ○ Application rates will be included in daily record sheets.
18630409-8d68-5e05-9598-c52d6f1f66bf | note | Reference Documents - Cl 5608-1
005fe0ad-a8ca-5145-aae5-779eb42af6ce | note | Inspection/Test Method - Verify
283ea1ec-8458-568d-adbc-b9141dcb567b | note | Record of conformity - This ITP signed by Contract administrator / Daily Spray Record Sheets
bc2cf652-3b4c-5efc-a216-a4082ad83e2f | note | WP
1633ca06-aa21-5a13-9f80-198a61e5af67 | note | Responsibility - Site Engineer
1197930e-5d15-50c3-b2fd-11f4e91b3a55 | date | Date Completed:
b5a3b387-caea-43f8-acc1-b1b685831ab8 | section | 6.0 - Quality Control
8a6105ed-680f-487a-89ff-5c333614d3ab | checkpoint | 6.1 - Application of fuel resistant surface treatment
6bf96c2b-19af-53dd-9857-eae644ef9edf | note | Frequency - Prior to commencement of works
080250d6-6a3c-5179-bedc-b815c3027fb5 | note | Acceptance Criteria - Proposed production and process control testing programme.
2ddb3a1d-654e-540d-aef6-7cf08064181c | note | Reference Documents - Cl 5612-1, HP5612-1
8b19e1e0-97ad-5e45-89cc-4d28a1560b9a | note | Inspection/Test Method - Verify
5c9e1235-30f8-5065-b25b-1d58402b5ef6 | note | Record of conformity - Aconex Submission of PQP / This ITP signed by Contract administrator
8ac4a915-bb11-54b1-86be-b5bb71063066 | note | HP
5150a210-06c0-5234-beb7-5302c511266e | note | Responsibility - Quality Engineer/ Site Engineer
5572d6df-92ec-5bcd-a830-08a2ec89fcfd | date | Date Completed:
b54681f9-0fb6-47ae-a36c-8922e6d45dca | signoff | AUTHORITY HOLDPOINT
572b5d9c-c4ad-4db1-9860-0657808f608b | checkpoint | 6.2 - Test Certificates
3144d9e6-9e62-508b-be8e-8d54fce19566 | note | Frequency - During surface treatment works
43d6ead8-b143-5f1a-bf61-789d7fd09a27 | note | Acceptance Criteria - Reference samples, test certificates, MSDS and technical data as specified for component materials and previous usage of the Rejuvenating Material and sand
8101511f-9a60-5020-9e71-de21717f2a8c | note | Reference Documents - Cl 5612-2, HP5612-2
0d20e940-27f3-56dd-8a35-5c11095bc002 | note | Inspection/Test Method - Verify
d23651b8-1eee-553e-83e9-7cb5acf557f2 | note | Record of conformity - Test Certificate s / Reference Samples / This ITP signed by Contract administrator
14fa980b-7dda-50c1-be0e-91937069a982 | note | HP
476faf2d-5170-59ba-9d20-c2c2b3069f5c | note | Responsibility - Site Engineer
1e41c429-958a-5b5f-b9d6-cacd87e2c77d | date | Date Completed:
5a0d8e8b-52fd-4546-bbc1-641011fd6b0e | signoff | AUTHORITY HOLDPOINT
05c91fc0-2d4d-4a27-9be8-40585c2654fa | checkpoint | 6.3 - Work Method Statement
efa44936-8e93-55f0-955d-3ccc252a78b8 | note | Frequency - Prior to commencement of works
437e9942-2b4f-5d7a-acf5-2bf623790a66 | note | Acceptance Criteria - The Contractor’s work method statement for the processes to be used for the application of the Rejuvenating Material, including surface cleaning/preparation, priming (as required), number of coats to be applied and curing time must be submitted with the reference samples.
aef6b93b-5df6-5c1f-9325-623fc3ce1fbb | note | Reference Documents - Cl 5612-3, HP5612-3
bbd605b1-6ada-59c2-bb41-485d08e92a37 | note | Inspection/Test Method - Verify
e9065638-7be1-5f7d-95d0-c746aae3c93d | note | Record of conformity - Aconex Submission / Reference samples / This ITP signed by Contract administrator
9b32c4e4-bc69-5f3b-b38b-593580b89f85 | note | HP
754eb856-9edf-55ad-9320-8fc9b2315bbf | note | Responsibility - Site Engineer
7a9493a9-e4ba-591b-995c-7ae1229b9fc5 | date | Date Completed:
e0b835b4-38e9-4e0c-9441-bd3be308ffdf | signoff | AUTHORITY HOLDPOINT
8e4cb35b-251f-46dd-b8d9-58d726d6a39e | checkpoint | 6.4 - Lot Submission for Surface Rejuvenation
6a7b1959-b3c7-5bd5-b8a1-5261789408c6 | note | Frequency - Per shift
8c5b9fa4-df2f-5240-93dc-8494cf2c0a3c | note | Acceptance Criteria - Submit detailed information for each shift. Details include application rate, location, test certificates and daily spray records etc.
8af9f627-c199-5b18-b275-337155cd53b8 | note | Reference Documents - Method Statement
2df2e1e5-bafd-5d77-a483-5af42923851a | note | Inspection/Test Method - Review of Lot Submission details
d8a5985b-2913-5d1c-95fb-9d9baeb7d4e5 | note | Record of conformity - Lot Submission document s submitted to Contract administrator
78b593b0-98bb-51eb-870c-37d1a763ec28 | note | WP
dbe9fbf5-dedd-56dd-bad0-0d166985e244 | note | Responsibility - Site Engineer
3d09ab66-4549-5848-b6a9-d19eba69a461 | date | Date Completed:
04838dca-2600-41aa-b896-48edb497fdc9 | checkpoint | 6.5 - Rejected materials and work
c192ba66-14e3-5431-986b-55895ea7e547 | note | Frequency - As required
e3c40430-e3b5-56b2-b8f9-e37f3cdcef3a | note | Acceptance Criteria - Non-conforming materials or areas must be repaired or rectified by the contractor to comply fully with the specification.
85b732f6-30ad-59cd-8f98-57c9457849c5 | note | Reference Documents - Cl 5613
18738f00-41fe-5043-9966-05ddb5b9b50a | note | Inspection/Test Method - Review and verification
506f4256-881a-5759-8544-ed5788ef4157 | note | Record of conformity - This ITP signed by Contract administrator
963de4a7-c07b-59d6-a881-7ad177240d60 | note | HP
6f4725b0-33ae-5cd6-bbb2-b7a4a7938ba1 | note | Responsibility - Site Engineer
16fc5edf-f971-5c8d-92c1-90eddd56a35f | date | Date Completed:
283a4d62-8424-4e09-b5ea-2367ab50b088 | signoff | AUTHORITY HOLDPOINT
cf8d008f-2c8d-4a1b-991e-0136f670cd11 | checkpoint | Final Inspection
3d805f06-8133-54b2-9f12-65e0fcad152e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
649aae02-b8bf-5738-9e39-6657bcaa815c | textbox | Print Name:
ae8c5e26-50ed-5142-9437-79e22b0ed75d | textbox | Position:
86055197-3639-5950-8aad-748648a9633d | date | Work Completed On:
c98ef87d-a187-5e6e-814c-eef67a92d4f9 | date | Date: