## zres_siteapp_NEW
Type | Name | Values | Prompting Name | Postfix | Resource Id
checklist | FH-927-QU-ITP007 - AGL Removal of Luminaire, Installation of Shallow Cans and Luminaire Installation - Rev 0 | itp | ITP007 - AGL Removal of Luminaire, Installation of Shallow Cans and Luminaire Installation
section | 1.0 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents - IFC Drawings Appendix K - AGL Specification
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings
label | IP
label | Responsibility - Subcontractor Representative
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activities
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Material/Equipment Approvals and Certification
label | Frequency - Prior to Start
label | Acceptance Criteria - All materials shall be proven to meet contractual requirements prior to acceptance.
label | Reference Documents - GHD-DD-SPC- 002 Section 2.4, Section 2.5
label | Inspection/Test Method - Verify
label | Record of conformity - Datasheet/ Material Submission
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
section | 2.0 - Removal of AGL Luminaires and installation of Foundation (All light types)
checkpoint | 2.1 - Setting out of Airfield Luminaires
label | Frequency - Each Lot
label | Acceptance Criteria - Surveyor to confirm location of AGL with IFC drawings and confirm alignment of luminaires.
label | ○ Existing lights shall be reinstated following the overlay works in their existing location and at their existing orientation utilising the survey data captured prior to their removal before the overlay works commencing.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.1
label | Inspection/Test Method - Verify
label | Record of conformity - SCP
label | IP
label | Responsibility - Site Engineer / Surveyor
date | Date Completed:
checkpoint | 2.2 - Confirmation of pre- works
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure that the light to be removed corresponds to project drawings and documentation.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 2.3 - Light removal
label | Frequency - Each Lot
label | Acceptance Criteria - Remove existing light and AGL cables from conduits as per Sub-Contractor ITC for the Methods 1 and 2.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 Sub-Contractor ITC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 2.4 - Isolation of lights
label | Frequency - Each Lot
label | Acceptance Criteria - Prior to commencement of removal, the subcontractor shall ensure that the light has been isolated from power.
label | Reference Documents - APAM Electrical Isolation Standards
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 2.5 - Coring
label | Frequency - Each Lot
label | Acceptance Criteria - Core pavement to required depth as per subcontractor ITC for relevant Method.
label | ○ Remove base and clean void.
label | ○ Existing AGL secondary cables removed after coring.
label | Reference Documents - AGL Subcontractor ITC CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Subcontractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 2.6 - Blanking Plate
label | Frequency - Each Lot
label | Acceptance Criteria - As required, core holes and luminaires to be safeguarded to allow for placement of asphalt with a Blanking plate.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
label | Inspection/Test Method - Verify
label | Record of conformity - This Signed ITP & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 2.7 - Light storage
label | Frequency - Each Lot
label | Acceptance Criteria - After removal of the light, the subcontractor must ensure that the light number and position is recorded and stored accordingly for re-installation.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
section | 3.0 - Installation of Light Foundation
checkpoint | 3.1 - Setting out of Airfield Luminaires
label | Frequency - Each Lot
label | Acceptance Criteria - Existing lights shall be reinstated following the overlay works in their existing location and at their existing orientation utilising the survey data captured prior to their removal before the overlay works commencing.
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.1
label | Inspection/Test Method - Verify
label | Record of conformity - SCP
label | IP
label | Responsibility - Site Engineer / Surveyor
date | Date Completed:
checkpoint | 3.2 - Coring
label | Frequency - Each Lot
label | Acceptance Criteria - Core pavement to required depth as per subcontractor ITC for relevant Method and Section 3.19.3 of Specifications GHD-DD-SPC-002.
label | ○ Remove asphalt core and remove blanking plate.
label | Reference Documents - AGL Subcontractor ITC CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC- 002
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Subcontractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 3.3 - Installation of Light Base
label | Frequency - Each Lot
label | Acceptance Criteria - Method 1:
label | 1) Re-instated Light Location is to be picked up by survey as per Section 3.19.1 of Specifications GHD-DD-SPC-002
label | 2) Secondary cable and earthing are to be places in Slot cuts
label | 3) Reinstall existing light and reconnect secondary cable and terminate earth on light base as per Sections 3.12.4 and 3.19.3 of Specifications GHD-DD-SPC-002
label | Method 2:
label | 1) Re-instated Light Location is to be picked up by survey as per Section 3.19.1 of Specifications GHD-DD-SPC-002
label | 2) Reinstall existing light and reconnect the existing secondary cable and connector as per Sections 3.12.4 and 3.19.3 of Specifications GHD-DD-SPC-002
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 Sub-Contractor ITC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
section | 4.0 - Installation of AGL Luminaires
checkpoint | 4.1 - Installation of Inset light
label | Frequency - Each Lot
label | Acceptance Criteria - A jig must be used to install, locate and level the inset light unit base in position in the core hole and maintain the base in position during the curing of the epoxy grout.
label | ○ Ensure correct light is installed in correct position and rotation as per the IFC drawings, this ITP and ITC
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.6
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & Sub- contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 4.2 - Light Fitting Functional Check
label | Frequency - Each Lot
label | Acceptance Criteria - Light illuminates correctly (aiming, orientation, existing colour) as per existing photometric specs
label | Reference Documents - CP1024-GHD- AD-L00-DR- EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 GHD-DD-SPC-002 Section 3.19.6 MOS 139
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & Sub- contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | 4.3 - Cabling and Earth Bond Verification
label | Frequency - Each Lot
label | Acceptance Criteria - Termination as per IFC and testing requirements of AS/NZ 3000
label | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.6 AS/NZ 3000
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed & Sub-contractor ITC
label | IP
label | Responsibility - Site Engineer / Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: