## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| 19c4b6d1-863e-55c9-b037-36910b2389d0 | checklist | (Dental School) Add Pipework Pressure Test Sheet - Water/LPG |  | Pipework Pressure Test Sheet - |  | b8efc79d-673a-4fa1-9b2c-ebe442bca291
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2016-513
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| ea42bb29-f001-5a6e-8d35-77d90be2e691 | checkpoint | Testing
| ced3b0fd-cefc-4dea-aa31-0a2809e66ad5 | note | Required Test Pressure: 1500kpa (min)
| 90a413a2-d72b-4f60-b1d4-f20e3e794aa4 | note | Required Test Time: 15 min (min) (as per NZBC G12 and ASNZ 3500)
| 30ea53b8-0304-4ddd-81cf-6b655a96afc2 | textbox | Date:
| 8012a329-4fed-4aa3-a46f-02521fa3f6cb | textbox | Start Pressure: |  |  | (kPa)
| 86bdf576-e22e-4052-a8bc-cc1cfa5e5420 | textbox | Finish Pressure: |  |  | (kPa)
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| 2350e3b4-3f78-5bca-ae6a-c0c111b7723a | checklist | (Dental School) Add Sanitary drainage/Suction Test Sheet |  | Sanitary drainage/SuctionTest Sheet - |  | 6bb65c56-81ca-44c5-b3fb-5757957d7ef5
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2016-513
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| ea42bb29-f001-5a6e-8d35-77d90be2e691 | checkpoint | Testing
| ced3b0fd-cefc-4dea-aa31-0a2809e66ad5 | note | Required Test Pressure: Static Head
| 90a413a2-d72b-4f60-b1d4-f20e3e794aa4 | note | Required Test Time: 10 min (min) (as per NZBC G12 and ASNZ 3500)
| 30ea53b8-0304-4ddd-81cf-6b655a96afc2 | textbox | Date:
| 8012a329-4fed-4aa3-a46f-02521fa3f6cb | textbox | Water Level Check 1
| 86bdf576-e22e-4052-a8bc-cc1cfa5e5420 | textbox | Water Level Check 2 |  |  | (kPa)
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| 8647de54-4e35-478d-b46a-5427a7043898 | checklist | Add Demolition Fixtures Checklist |  | Room - |  | e0e6963c-d756-403f-a806-6a07e04ab5c7
| b939799e-cb32-552b-b0ae-f77ae972662b | checkpoint | Details Completed
| 704792d6-407f-47d2-a793-63b38e1bdebe | textbox | Location:
| 6cbb0c5b-c23b-4a7a-a2a6-970612c8c13a | textbox | Drawing:
| 30d3167a-bf9f-4480-867f-5dd2f3b6932c | textbox | Plumber:
| f97accd6-1d2a-4a66-9fcf-876e208de072 | note | What area within space that can be demoed
| a9ba95d7-60da-4917-823f-f850ad2794a4 | tickbox | Ceiling Space
| 7aaa24f1-6c50-48c6-9dbe-47dedbbc525e | tickbox | Room area
| 02834c41-a498-5875-add1-7009bb9c1e34 | checkpoint | Cold water services have been isolated and capped
| 767f9972-9b04-5664-8012-18e6945018db | checkpoint | Hot water services have been isolated and capped
| 3cade01f-7182-547f-ac43-44f420c2df0f | checkpoint | Trap's have been removed and desposed of
| 5f7e7b65-d7d1-585e-8b73-fc44ac496fdd | checkpoint | Waste pipes have been capped
| 20a0eb37-2e44-5be8-9ad0-9f5fd804fb28 | checkpoint | LPG services have been isolated, purged and capped
| edd26113-ad1d-55ac-80e4-354ef8dbb886 | checkpoint | Compressed Air services have been purged and isolated
| 96d70be9-4bd8-513d-85ca-68f9fa915b8b | checkpoint | All services have been isolated and all fixtures are now safe to be removed
| 2dcddb35-3292-5298-9ea9-6675195619af | checklist | Add Final Sign Off Slab Grids Checklist |  | Final Sign Off Slab Grids |  | 86bdf911-63e7-4773-b65f-ffdb7777b83d
| 949a58a0-3680-5acc-b1c2-53a133b591f2 | section | Slab Grids QA
| 007d08bc-fca4-51f2-a22b-35f79adf890c | checkpoint | Steel clips ready for mesh tie down
| 377684bf-d401-59c3-94b6-b10e2f461035 | checkpoint | Pipe penetrations lagged to slab height
| df5cb1e7-9edf-5bee-a26b-93793d7937fe | checkpoint | Checked for damage at slab level all ok
| cc880b24-6251-5bf9-9070-94a99d5b9216 | checkpoint | Water test holding
| 3ceadcd6-d779-5c97-8426-53dd865a89c4 | section | Sign Off
| 185aed6f-b8f8-5085-bfd5-ec90233da70d | checkpoint | Foleys Signoff
|  | checklist | Add Folder |  |  |  | 8509b27e-52e3-4407-8328-3805c8421ff0
| c4e34a4e-6c51-5c7e-9a16-ca5bb03add20 | checklist | Checklist - Backflow Preventer |  | Backflow Preventer |  | 2d984892-872f-4e83-8c96-289a2e5497d6
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 7c4b3bf8-122a-442a-87e3-fbfda2302f26 | textbox | Date
| 1ef10f31-7076-440e-80de-98dc66902059 | textbox | Valve Number
| 5653c384-3b33-4154-b70a-07fa20676a37 | textbox | Location
| 95fd21ee-e4f2-5865-b179-099684b6e41c | checkpoint | Result (confirm passed)
| 7adc7e80-f8d1-5c3b-aaa4-1a5143f5e0f5 | checkpoint | Service label attached to RPZ
| 889a62ec-0b43-5577-88d7-c4ead599220b | checkpoint | IQP certificate filed
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 8b8af21d-e886-5dc6-999e-dbe1a584f816 | checklist | Checklist - Demolition Fixtures |  | Room - |  | d5bd0a5c-837c-448f-bcb4-8f0cae443f54
| b939799e-cb32-552b-b0ae-f77ae972662b | checkpoint | Details Completed
| 704792d6-407f-47d2-a793-63b38e1bdebe | textbox | Location:
| 6cbb0c5b-c23b-4a7a-a2a6-970612c8c13a | textbox | Drawing:
| 30d3167a-bf9f-4480-867f-5dd2f3b6932c | textbox | Plumber:
| f97accd6-1d2a-4a66-9fcf-876e208de072 | note | What area within space that can be demoed
| a9ba95d7-60da-4917-823f-f850ad2794a4 | tickbox | Ceiling Space
| 7aaa24f1-6c50-48c6-9dbe-47dedbbc525e | tickbox | Room area
| 02834c41-a498-5875-add1-7009bb9c1e34 | checkpoint | Cold water services have been isolated and capped
| 767f9972-9b04-5664-8012-18e6945018db | checkpoint | Hot water services have been isolated and capped
| 3cade01f-7182-547f-ac43-44f420c2df0f | checkpoint | Trap's have been removed and desposed of
| 5f7e7b65-d7d1-585e-8b73-fc44ac496fdd | checkpoint | Waste pipes have been capped
| 20a0eb37-2e44-5be8-9ad0-9f5fd804fb28 | checkpoint | LPG services have been isolated, purged and capped
| edd26113-ad1d-55ac-80e4-354ef8dbb886 | checkpoint | Compressed Air services have been purged and isolated
| 96d70be9-4bd8-513d-85ca-68f9fa915b8b | checkpoint | All services have been isolated and all fixtures are now safe to be removed
| fe485388-3d3b-5064-940a-8384e8ec63fe | checklist | Checklist - Flushing Valves |  | Flushing Valves |  | 16cf727f-f1c5-4dfc-9473-4c9749121a69
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 94ea1db5-59f6-4afe-86a6-5829be154b8d | textbox | Date
| 04b3c509-2f01-4d48-8b52-b7b7c8465b42 | textbox | Item
| 4c9d4772-4980-437e-b23f-ef3f1aa1cf4b | textbox | Location
| 40838eeb-5710-5771-8805-98af28401f6c | checkpoint | Confirm Operation
| 97ce75f4-7a62-5aa2-8e18-1ce0b862a204 | checkpoint | GPF Flow Ring Installed (colour)
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 903e1a06-37df-5515-b4c1-3403b02ecf70 | checklist | Checklist - Hot Water Balancing Valves |  | Hot Water Balancing Valves |  | c85c1340-2f49-4e68-a162-fc3a4babb2fe
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| d1c44d88-cbcc-400e-b694-ae4407d2db04 | textbox | Date
| f3b96b47-47ee-4956-a2e1-f6bcf78b3c7e | textbox | Location
| ece9306b-2d7f-43cc-aef9-2f65aa6f9622 | textbox | Valve Number
| 1b3409fc-936d-5043-96ae-075feb516538 | checkpoint | Hot Water Circulating
| 4cb654f7-c6a2-5c0c-8ca7-0edccc544089 | checkpoint | Balanced Temperature
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 29ad2771-2684-5da0-bd48-f536d6b8e70d | checklist | Checklist - Hot Water Clorafiers |  | Hot Water Clorafiers |  | 77564cfd-69e0-4ec1-bfc1-fb74436dc73f
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| e53bc627-9d29-4a98-8407-6445b1104690 | textbox | Date
| 66ecfeae-26ed-473b-b64a-7a17082e9e09 | textbox | Item
| a66361cd-3411-42de-a738-8428919b1ac5 | textbox | Location
| 54bda19f-1a62-50bf-9e59-ad318322f48b | checkpoint | Temperature entering
Hidden property width:50 | 6a7ddd92-8564-4ec2-a127-59c87a0170c8 | textbox
| 73c292dd-cf4b-537d-83c6-e0401c61f786 | checkpoint | Temperature leaving
Hidden property width:50 | 94ac508f-54f7-46de-919f-4b35ecdd38c9 | textbox
| 39867aad-df21-4bbe-a4e8-b97ef0025ea4 | checkpoint-no-value
Hidden property width:75 | 4ed7598f-d1c7-4395-ba1b-e603125e82eb | textbox | Check time
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 370357fa-a2b9-5b1b-aa0c-14f5097c9342 | checklist | Checklist - Hot Water Return Pumps |  | Hot Water Return Pumps |  | 8e447c4e-47be-442a-bda2-68301e42e32c
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| d38a1928-e805-4a10-8e09-71b3a35ac7c2 | textbox | Date
| 6b6b9168-e219-451c-b08d-c89a8ec5f1f3 | textbox | Pump Number
| 8338c745-fcc8-47f5-86ff-995002c567a0 | textbox | Location
| 0aa43928-bc62-584c-8b14-5d64fb8a438c | checkpoint | Electrical Complete
| 0a756e34-8706-5d60-9a8e-956ff825a7dd | checkpoint | Water Heating operating
| f4ce927d-c3c3-5c7b-bb1b-1f3b17e67d30 | checkpoint | System Balanced
| bca3245d-b2b3-49af-9d27-2f91b4a9e38e | checkpoint-no-value
| ffe491ac-0468-43e7-8021-9a39b076531a | textbox | Pressure diffrence across pump
| 095d0a97-ccf1-47fc-bb43-0a53b80075fa | textbox | Final Flow Rate
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| ac160164-eda2-5fe6-a5d6-dfd2cfd4b061 | checklist | Checklist - LPG Meters |  | LPG Meters |  | 49f2a513-727b-4989-8283-44718709a4f7
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| b2db898f-3ad4-4183-a23d-d1cf9d676e05 | textbox | Date
| 6988f2d4-e160-4ceb-8c6a-e5c851216e34 | textbox | Item
| a10e58e4-0970-477f-a242-8c1e045eef73 | textbox | Location
| c3edb1e7-f13e-5a8a-8ec1-31f78155a98c | checkpoint | Confirm operation with BMS
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 4a4f1f1e-e397-55fd-b57f-e1aca5d14b8f | checklist | Checklist - LPG System |  | LPG system |  | 5e7e6873-f98f-4010-9f4d-33626a750f67
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 2ccd317b-51c9-47c1-b3fa-0cb3be22a613 | textbox | Date
| a98b401e-97db-4dc5-aa4e-6ebb97694239 | textbox | Location
| 4dc515b2-3e99-5467-8ea8-aa8cb4be1b0a | checkpoint | Test certificate filed
| 5893ad3d-f030-5601-a6dd-c1c5b34ba355 | checkpoint | Pressures set. Record below
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 3f31c55d-921e-5f3e-baf9-d58339eb2e09 | checklist | Checklist - Pressure Limiting Valves |  | Pressure Limiting Valves |  | cd27064b-3d5f-45b1-a6c0-dcb3122fd23a
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 9481867c-36ef-462d-8dd2-92be99740a46 | textbox | Date
| 7a04e321-7ee0-4c74-9923-d8faf96b6d14 | textbox | Valve Number
| c4fac3ad-4990-4218-92d5-551761bcfc23 | textbox | Location
| 993d85ea-b3e7-567b-a47a-1818a47c237b | checkpoint | Pressure Set
| 3fbd2dbb-534d-5664-a873-36c998908b3e | checkpoint | Set Pressure (KPA)
| 09886da9-5734-4192-983e-aa3f294a6d17 | textbox
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 22b496c3-f56a-5938-962d-a0489885d3c5 | checklist | Checklist - Sanitary Drainage |  | Sanitary Drainage Below Slab: |  | 2a04f69d-9afe-41b8-9643-1e6e26b63827
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2015 1137
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| 90992950-b9a2-5b5d-a4ef-a6c6a8aa61d7 | section | Water and Waste Pipe Work QA
| f202d5d8-b29e-53e0-b727-833610208474 | checkpoint | Area tidy and ready to start
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| b91069de-5051-5972-a08d-c5ad1597c7e1 | checkpoint | Confirm Pipe bedding at least 75mm compacted thickness
| a83131d3-2a94-5331-b783-2df0fecad343 | checkpoint | Confirm pipe bedding material AP20
| 921a0d67-3bd8-5ec2-99af-a89b1f0dd90e | checkpoint | Pipe work layed to invert and grades as per approved shop drawings.
| 7a20040e-734a-5d9c-82a8-186cc291fb95 | checkpoint | Check that risers are in the correct location and secure
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 33e18410-d447-53fc-a172-60cd19d016f5 | checkpoint | DCC inspection complete
| 4f22da70-9164-5b9d-b05a-03ec9ba1acc4 | checkpoint | Trenches backfilled and compacted AP65. Marking tape installed
| c5c6b592-7970-5140-aef2-d6e19b502566 | checkpoint | QA sheet completed and loaded in system
| 4b21b0ba-c9e4-5173-9293-e04749317963 | checklist | Checklist - Second Fit QA |  | Second Fit QA |  | 81d1dfad-4d59-4c78-a393-be0b3f24f995
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 0c8994cb-9886-4389-b6c7-62ed78acc830 | textbox | Date
| 7f01dc77-606b-4c31-ba70-73ae4f573818 | textbox | Item
| 875e7b71-d350-42d4-baf9-885dbec6c936 | textbox | Location
| 40838eeb-5710-5771-8805-98af28401f6c | checkpoint | Confirm Operation
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 2fa3674a-30c8-5db1-bdd3-7b7967930097 | checklist | Checklist - Thermal Mixing Valves |  | Thermal Mixing Valves |  | fb16baec-ce33-4be2-915d-76738b72f13b
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 1e08319f-91b0-4efc-8dff-ccfd505cc208 | textbox | Date
| 624ccebb-4905-4c0e-93b4-cc047057267f | textbox | Valve Number
| 18876f46-86c3-4f21-965e-2cdf5e5f12a7 | textbox | Location
| 8ca293e3-68bb-57c7-9a88-90fa35de8897 | checkpoint | Set Temperature. °C
| 70ccc2b6-63ef-5f12-a3c4-ce0b2650977a | checkpoint | Lock cap fitted
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 37739c50-3ff1-550c-a567-0295a00462c5 | checklist | Checklist - Trap Primer |  | Trap Primer |  | 47c7ef5a-1e74-4c35-bb27-725348b4b059
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| c0a8cf16-1060-4b78-b307-50f97a3399f4 | textbox | Date
| a3cfdb55-b353-4bae-8262-8e524f3d3ddb | textbox | Trap Primer Number
| 779a2d9d-c533-46cc-a6a7-d3aef030311b | textbox | Location
| 8849efbc-d538-52ef-8e46-5452db37f36b | checkpoint | Water system complete and charged
| 7e55d44b-fecb-5cab-86f1-2a1791ee0568 | checkpoint | Electrical supply commissioned
| a64ea136-883a-5ae4-9185-0d07b378165e | checkpoint | On/Off times set.(tick)
| 005de67d-e309-5473-a058-dc3cbaa095c3 | checkpoint | "Test button" Press confirm operation.
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 1f1920ae-eb41-5740-9dd5-1482e01b0dcd | checklist | Checklist - Water Meters |  | Water Meters |  | 997031c3-f399-4538-a5a8-25d97d12713e
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 6efe3c46-615d-4af3-8ea7-1451691f105f | textbox | Date
| 640f36e4-065d-4d60-bc00-8c8b9c77c500 | textbox | Item
| f201b4a1-a8ca-4a65-bf54-bcdef6003225 | textbox | Location
| c3edb1e7-f13e-5a8a-8ec1-31f78155a98c | checkpoint | Confirm operation with BMS
| 05d676bb-0ad1-58c0-933c-f87ec98fbf7c | checkpoint | QA complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 78ad97fe-ca33-501e-8061-5b709264fc82 | checklist | Checklist - Water Quality Testing |  | Water Quality Testing |  | 10091958-9aff-4d28-861d-5c80a3722149
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| 8c2bdc22-4410-48c6-9577-09ed51d2939d | textbox | Date
| dd61bf64-5dc4-4c05-880c-0e3755df3a44 | textbox | Test point Location
| 64f23426-52af-5f04-8649-8b6b2c8f8974 | checkpoint | Lab results confirmed and attached
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| 5df265e8-b720-5a49-bf93-8d8e6c96a7f3 | checklist | Checklist - Water Strainers |  | Water Strainers |  | 736b0fe7-6266-490f-aeba-1229403e8b89
| 7eed4801-00d6-5013-9e0b-26fd05193fff | checkpoint-no-value
| a6026c5c-7b5b-4356-88b5-8c2d47b01964 | textbox | Date
| 6e582f4c-d1bd-48e6-9457-5aa73b762b10 | textbox | Item
| b1d8b0e8-3c2e-41f6-a6e1-9b82e991cf4f | textbox | Location
| 2e985431-ad87-5a5b-983e-c25aca76e18b | checkpoint | Size (Micron's)
| e54b4f21-0731-5919-beeb-67a1d1d10efd | checkpoint | Strainer mesh replaced
| 63d61854-03c2-5c88-990f-4666be73a6e8 | checkpoint | QA Complete
| db0003e4-a6e3-5d0d-a476-c1a4ee70f817 | checkpoint | Final Sign Off
| c9b1dfc4-1b3d-573e-80be-dddc442788a9 | checklist | Civil Drainage - Stormwater & Foul |  | Civil Drainage - Stormwater & Foul |  | 871dac65-1674-4f98-bfb2-6ea90f6438d8
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 9ee348e0-665f-5599-8a6b-a88299a23181 | checkpoint | Plans checked against what has been supplied for pipe types & size
| c2f1e4a2-7b2e-5009-8d87-fa0b7cea0124 | checkpoint | Trench shoring in place or benched if required.
| 721075d6-1043-5574-bf29-0f8cb8b030e2 | checkpoint | Trench bedding material (AP20 or dust) compacted
| c9eee1f4-ed5d-5bf1-919c-fe977fb25b86 | checkpoint | Sumps & manholes checked and confirmed for correct position
| fcbec304-a781-5a56-a9ba-1fd56702feb4 | checkpoint | Manholes have corbels in place and manhole benched
| 5771426d-59c1-56c1-afb9-4c7b76d652a0 | checkpoint | Drop structures complete
| a63ccc33-7c71-5722-828d-b9755b5345cb | checkpoint | Pipe laid to correct grade
| 58dc6359-8208-5bb6-9b45-38f409197c68 | checkpoint | Pressure test complete
| 33e18410-d447-53fc-a172-60cd19d016f5 | checkpoint | DCC inspection complete
| b95797e2-587d-5b09-ba3a-3c2ac083563b | checkpoint | Trench backfilled and compacted
| 21a2db44-cb2b-597e-a2c1-8f1a82649d22 | checkpoint | Commissioning signoff
| 37087507-b232-504b-b134-af6d129f1d21 | signoff
| 7b5780f4-0a89-5a03-b19e-df42236e88b9 | checklist | Gas Pipe Line Checklist |  | Gas Pipe Line Test Sheet |  | 0228c9cf-96da-4179-8fdd-9ffeaa986625
| 27eadc21-2652-56d1-8c55-3230e4fab2c7 | section | Job Details
| c5bc628f-94bf-50e8-857f-b56d2f35b9eb | checkpoint | Job details complete
| 6a61566f-4088-4336-8cb3-8bf88ea4df6f | textbox | Job:
| a5086cbe-7a94-425b-8abd-2a7e92dfd773 | textbox | Gasfitter:
| 9459eb1b-6b6e-4de1-bdfe-4d31a01d48da | textbox | Date:
| 9cf41410-8df0-4e71-bd5e-40db2a2701f1 | textbox | Site Address:
| 46648c72-7435-463e-920e-c4e9ef61bacf | dropdown | Gas Installation "Safe To Use" | No,Yes
| 3d0d85fe-8fd8-481f-8113-7be63b8ce174 | textbox | Risk Classification
| 8ce21f85-17a4-441f-ad35-4d69fcf94ee0 | textbox | Part/Whole Installation
| 0141838e-9b91-4ba6-b54b-c5717c653d50 | textbox | Gas Type
| e947eb6d-ccb2-40c1-8044-5952f5c2bd65 | textbox | Certifying Gasfitter
| 279109bf-d1af-412d-b91c-83a32cef5491 | dropdown | Work done in accordance with means of compliance (AS/NZS 5601.1:2010 part 1) | No,Yes
| f55ddf02-3d74-52ee-8f5f-e2943a7b9b19 | section | Test Details
Data not allowed on checkpoint-group. | f8e02dd4-6dea-4011-9679-ee7024ae6ec2 | textbox | Work undertaken:
Data not allowed on checkpoint-group. | 250dd824-129a-463c-8234-290c7991522d | textbox | Test location:
| 4e976180-88af-56ed-95f2-0fd64ea67afe | checkpoint | Test procedure AS/NZS 5601.1:2010 Appendix E
| 739b743d-1327-40a7-adfe-a5a318f487fa | textbox | Date:
| 391fea7e-3f43-5213-a3b7-0f999fb912aa | checkpoint | Leakage test of Existing installation E6
| db884bd4-6acd-4c57-ac0f-fde8db51d296 | textbox | Test Pressure: |  |  | kPa
| 35ba7837-70c7-46cf-8936-d360daf59514 | textbox | Duration:
| e3053feb-6ff9-4e67-9fde-3dcce1c1501c | textbox | Drop/raise
| 29c05a28-c524-5849-85ea-5656c615ce15 | checkpoint | Final Connection Test E7
| 6159a8fe-0eac-42c0-a3d4-c852d040bff3 | textbox | Test Pressure: |  |  | kPa
| 8b2bde2f-adb0-4e97-bc5f-87acbcfe74c2 | textbox | Duration:
| 8babf722-b069-4ad7-b268-62738d8d0cc5 | textbox | Drop/raise
| 9167430f-7348-4d57-b6af-3b196167c242 | textbox | Working Pressure |  |  | kPa
| 441f6a03-f68e-503a-8982-e3e8a39f3cf9 | checklist | Programmed Maintenance Checklist |  | Programmed Maintenance Checklist |  | 1dacc987-363b-40c5-af15-694d6af17279
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
| 9db6b777-1a53-4553-9ec8-eedda209f514 | textbox | Maintenance Number:
| 2244ab15-2d6d-4a86-8bec-93fa47e44f0a | button |  | Area - CSB,Walsh
| f5f73253-6296-556f-99b1-494247e60e82 | checkpoint | Having recieved approval to carry out the maintenance, ask the department heads if there have been any problems with the plumbing systems
| ceb8ef29-10b9-5de0-ac3a-410e2657879e | checkpoint | coordinate with the electrical trade to carry out the maintenance at the same time
| cf26d2cd-7299-593c-bbb9-d4aab980f325 | checkpoint | Inspect the integrity of the portaboe hot and cold pipework
| 26df7b16-8ed8-5e91-b14f-08462895310e | checkpoint | Inspect the integrity of the waste water pipe work
| 4b243434-38d9-51d9-b3b7-2af3e9730dd8 | checkpoint | Inspect the integrity of the HWC for leaks
| f5e9fc6d-aeb7-5e51-b58a-091503a21a13 | checkpoint | Inspect the integrity of the HWC valves
| 04ab8ee5-7908-548b-9200-687a632e03cf | checkpoint | Inspect the integrity of the TWC temperatures
| 1b8b92d3-c5a8-5c80-81e8-07eb60057b61 | checkpoint | Inspect the integrity of the toilet flush
| 7f1b02be-4492-579c-bf5e-b814b5d944d8 | checkpoint | Inspect the integrity of the pumps
| 6ad683a0-0429-5c86-826d-0a9a2b42cba0 | checkpoint | Inspect the integrity of the trap primers
| 4b1ebcb1-e366-50e8-86c3-f0115424f7d2 | checkpoint | Inspect the integrity of the suction pipework
| c9ca8bad-5a67-5c23-9e83-9a57c33e8e2a | checkpoint | Inspect the integrity of the LPG pipework and valving
| eb32e170-f180-5fa4-a4b6-4c47e5d8e988 | checkpoint | Inspect the integrity of the basins and sinks
| 0a894c35-0af5-5a05-9a59-2fb9044c8f49 | checkpoint | Inspect the integrity of the suction pipe work
| 9706fbca-ae94-50ce-ac1a-bba206645410 | checkpoint | Inspect the integrity of the plaster traps
| 2049ea79-e8fc-50c8-bf5e-2032a2044d2f | checkpoint | Inspect the integrity of the foul sewer and water systems
| c7b0adf7-d0d5-5a97-910f-bed7c972c142 | checklist | Pump Station |  | Pump Station |  | 9059accd-da0f-4c5a-ac12-ae79f32928f2
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 03d7361b-6abd-5c16-a08f-256f42c005c1 | checkpoint | Check ground conditions for correct installation
| 859b6df1-c943-521d-a827-5e405cf3b678 | checkpoint | Backfilled with appropriate fill
| c0af717a-361f-533a-9157-face87e7140c | checkpoint | Check floats and controls clear of any obstructions in pump chamber
| 7b43d28c-d9a7-5e98-80ac-1bb05ebce108 | checkpoint | Check correct electrical connection has been made
| f143187c-62be-5182-8e69-3e2222c6ad68 | checkpoint | Fill tank with water to float level and check operation of pump
| eeca8b2b-4cc9-5853-bf63-0d6646bb3e19 | checkpoint | Check high level float alarm
| 21a2db44-cb2b-597e-a2c1-8f1a82649d22 | checkpoint | Commissioning signoff
| 37087507-b232-504b-b134-af6d129f1d21 | signoff
| e20ac077-07df-481f-9d20-842d42f729a6 | checklist | QA Sheet - 1st Fix - LPG |  | 1st Fix - LPG |  | ab28d90e-07e8-4593-b55a-07ada6fd85dd
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| ea261aed-0bb2-5bd7-8b00-8c203bd022b7 | checkpoint | Check that the correct pipe sizing is complete to each fixture
| 7b666a7d-86f3-5c0b-b61f-fd16bf716cce | checkpoint | Check that the wingbatts are installed at the correct height
| e4cf5f04-86fd-5229-b034-6d188dc2559e | checkpoint | Check that seismic restraints are installed
| 3a49ad16-5679-523a-b1bc-fa0dc62b58c8 | checkpoint | Check that the fixing's are installed at correct height
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 596f756c-59f9-521a-8058-04c12f3e8e6b | checkpoint | Check the pipe labels are on
| 048ec5c4-fd8a-43f2-ada2-634e6f5cd723 | checklist | QA Sheet - 1st Fix - RO Water pipe work |  | 1st Fix - RO Water pipe work |  | 5a89a564-26e3-48fc-ae40-0664da136e10
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| 483b5a1f-8c9b-5b84-a075-472dd1b5ca9f | checkpoint | Check that the correct water and pipe sizing is complete to each fixture
| 7b666a7d-86f3-5c0b-b61f-fd16bf716cce | checkpoint | Check that the wingbatts are installed at the correct height
| e4cf5f04-86fd-5229-b034-6d188dc2559e | checkpoint | Check that seismic restraints are installed
| 61ec0166-8a7d-5947-bf1b-31c580ba1fed | checkpoint | Check that the waste pipe is the correct location
| 3a49ad16-5679-523a-b1bc-fa0dc62b58c8 | checkpoint | Check that the fixing's are installed at correct height
| 1c97c775-b8c9-5f4f-9a79-dc8a21f71e22 | checkpoint | Check that the pipe insulation is installed
| f66ee80a-c1e0-5816-b7d1-246f88c41452 | checkpoint | Check that the acoustic insulation is installed
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 42aad14d-baca-511f-ac04-a1638eb15c3c | checkpoint | Council inspection complete
| 596f756c-59f9-521a-8058-04c12f3e8e6b | checkpoint | Check the pipe labels are on
| c0a6e78d-ca7b-4629-9fd0-6a7f41280039 | checklist | QA Sheet - 1st Fix - water pipe work |  | 1st Fix - Water pipe work |  | fa7ea125-6a62-499e-a6c0-48dce6c76ee2
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| 483b5a1f-8c9b-5b84-a075-472dd1b5ca9f | checkpoint | Check that the correct water and pipe sizing is complete to each fixture
| 7b666a7d-86f3-5c0b-b61f-fd16bf716cce | checkpoint | Check that the wingbatts are installed at the correct height
| e4cf5f04-86fd-5229-b034-6d188dc2559e | checkpoint | Check that seismic restraints are installed
| 61ec0166-8a7d-5947-bf1b-31c580ba1fed | checkpoint | Check that the waste pipe is the correct location
| 3a49ad16-5679-523a-b1bc-fa0dc62b58c8 | checkpoint | Check that the fixing's are installed at correct height
| 1c97c775-b8c9-5f4f-9a79-dc8a21f71e22 | checkpoint | Check that the pipe insulation is installed
| f66ee80a-c1e0-5816-b7d1-246f88c41452 | checkpoint | Check that the acoustic insulation is installed
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 42aad14d-baca-511f-ac04-a1638eb15c3c | checkpoint | Council inspection complete
| 596f756c-59f9-521a-8058-04c12f3e8e6b | checkpoint | Check the pipe labels are on
| d9248abf-8c4e-4925-8064-eac0772da445 | checklist | QA Sheet - Sanitary drainage - waste pipe work |  | Sanitary drainage - waste pipe work |  | ce6fd15a-540e-440a-94d9-0445f910b60a
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| a0f8479e-7f3f-5641-802d-8f22d7bc026c | checkpoint | Check pipe brackets conform to PS1 design
| dc4afba6-47c7-5187-a142-83cc46bb1eee | checkpoint | Check maximum spacing of brackets not exceded. Ref Aurecon 6.4.8.3
| 86730634-50ff-5356-8f5a-07ad5dacd466 | checkpoint | Drains installed at correct grades/fall ratios
| 7a20040e-734a-5d9c-82a8-186cc291fb95 | checkpoint | Check that risers are in the correct location and secure
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 42aad14d-baca-511f-ac04-a1638eb15c3c | checkpoint | Council inspection complete
| 33e18410-d447-53fc-a172-60cd19d016f5 | checkpoint | DCC inspection complete
| 173a6c45-12aa-4df3-8f25-b8833eeec2d5 | checklist | QA Sheet - Sanitary drainage below slab - water and waste pipe work |  | Sanitary drainage below slab - water and waste pipe work |  | 6d389d02-3611-4956-ad05-d076516d8183
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| a0f8479e-7f3f-5641-802d-8f22d7bc026c | checkpoint | Check pipe brackets conform to PS1 design
| dc4afba6-47c7-5187-a142-83cc46bb1eee | checkpoint | Check maximum spacing of brackets not exceded. Ref Aurecon 6.4.8.3
| 86730634-50ff-5356-8f5a-07ad5dacd466 | checkpoint | Drains installed at correct grades/fall ratios
| 7a20040e-734a-5d9c-82a8-186cc291fb95 | checkpoint | Check that risers are in the correct location and secure
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 42aad14d-baca-511f-ac04-a1638eb15c3c | checkpoint | Council inspection complete
| 33e18410-d447-53fc-a172-60cd19d016f5 | checkpoint | DCC inspection complete
| 41b6fe5d-2486-5210-8595-d8342975ad61 | checklist | Safety Shower Operation & Flow test |  | Safety Shower Operation & Flow test |  | d4bc4c65-ced3-4536-8e17-d909a1b9e868
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 1aaa531e-83c4-5862-aaf6-a1bf88811211 | checkpoint | Water supply delivers required flow when shower and eye wash are operated
| c041e62a-355f-5f9a-999b-682f1b57fb35 | checkpoint | Hands free valve operating correctly
| 761cfb2d-57b3-5148-a740-ac700642f920 | checkpoint | Shower delivers required 75.7 litres per minute
| 69e7d969-f25e-5138-a294-147adfa36258 | checkpoint | Eye wash delivers 11.4 litres per minute
| 30a95e9b-b14b-5413-a531-42ba64628949 | checkpoint | Tempering valve set to correct temperature
| 21a2db44-cb2b-597e-a2c1-8f1a82649d22 | checkpoint | Commissioning signoff
| 37087507-b232-504b-b134-af6d129f1d21 | signoff
| 51e58fff-1857-4401-b23a-861dc8ac4ed8 | checklist | Sanitary drainage - waste pipe work QA Sheet |  | Sanitary drainage - waste pipe work |  | f24a4b05-6e5d-4545-95f3-d6c3650b7192
| 18f9d207-bd0f-5065-aab9-fca72d2b0c16 | checkpoint | Check pipework is installed as per listed drawings
| a0f8479e-7f3f-5641-802d-8f22d7bc026c | checkpoint | Check pipe brackets conform to PS1 design
| dc4afba6-47c7-5187-a142-83cc46bb1eee | checkpoint | Check maximum spacing of brackets not exceded. Ref Aurecon 6.4.8.3
| 86730634-50ff-5356-8f5a-07ad5dacd466 | checkpoint | Drains installed at correct grades/fall ratios
| 7a20040e-734a-5d9c-82a8-186cc291fb95 | checkpoint | Check that risers are in the correct location and secure
| d0561c0a-8f10-511d-b2ce-e84eaf96d383 | checkpoint | Check that the pressure test is complete
| 27f5c9eb-a9ca-5458-b69d-21a80dcd6c0b | checkpoint | Check that the test sheet is filled out
| 42aad14d-baca-511f-ac04-a1638eb15c3c | checkpoint | Council inspection complete
| 33e18410-d447-53fc-a172-60cd19d016f5 | checkpoint | DCC inspection complete
| 117bffe4-a5e2-593a-9208-cb6b1b00e634 | checklist | Test Sheet - Pipework Pressure - Water |  | Pipework Pressure Test Sheet - Water: |  | 10156f40-5f6e-4bd2-a2d9-be6e49eee604
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2015 1137
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| ea42bb29-f001-5a6e-8d35-77d90be2e691 | checkpoint | Testing
| ced3b0fd-cefc-4dea-aa31-0a2809e66ad5 | note | Required Test Pressure: Static Water Test
| 90a413a2-d72b-4f60-b1d4-f20e3e794aa4 | note | Required Test Time: 1/2 hour (as per NZBC and ASNZ 3500)
| 30ea53b8-0304-4ddd-81cf-6b655a96afc2 | textbox | Date:
| 8012a329-4fed-4aa3-a46f-02521fa3f6cb | textbox | Start Pressure: |  |  | (kPa)
| 86bdf576-e22e-4052-a8bc-cc1cfa5e5420 | textbox | Finish Pressure: |  |  | (kPa)
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| d7d21a75-054c-4c2c-864a-e73d9ce812c5 | checklist | Test Sheet - Pipework Pressure - Water/LPG |  | Pipework Pressure Test Sheet - |  | e9a281d5-44fb-4f65-a4d3-fb85b22813e3
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2016-513
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| ea42bb29-f001-5a6e-8d35-77d90be2e691 | checkpoint | Testing
| ced3b0fd-cefc-4dea-aa31-0a2809e66ad5 | note | Required Test Pressure: 1500kpa (min)
| 90a413a2-d72b-4f60-b1d4-f20e3e794aa4 | note | Required Test Time: 15 min (min) (as per NZBC G12 and ASNZ 3500)
| 30ea53b8-0304-4ddd-81cf-6b655a96afc2 | textbox | Date:
| 8012a329-4fed-4aa3-a46f-02521fa3f6cb | textbox | Start Pressure: |  |  | (kPa)
| 86bdf576-e22e-4052-a8bc-cc1cfa5e5420 | textbox | Finish Pressure: |  |  | (kPa)
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| 4312c063-d41e-4676-962e-0266607a7d88 | checklist | Test Sheet - Sanitary drainage/Suction |  | Sanitary drainage/SuctionTest Sheet - |  | d51c1d2d-5b14-4fb3-bc30-ce245ac726af
| 3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
| 25e741cf-f7f4-45ab-b864-5ca34dd41538 | note | Consent Number: ABA 2016-513
| f7244314-1608-4d09-8dcb-f175826e98ad | textbox | Location:
| 983cd07f-9335-45af-9269-f758e47c7aa5 | textbox | Drawing:
| 5044b75f-1ed9-4ff5-affe-24dce170f3b7 | textbox | Plumber:
| 70b8ef99-3faf-4478-86e4-a2a971730f79 | textbox | Date:
| ea42bb29-f001-5a6e-8d35-77d90be2e691 | checkpoint | Testing
| ced3b0fd-cefc-4dea-aa31-0a2809e66ad5 | note | Required Test Pressure: Static Head
| 90a413a2-d72b-4f60-b1d4-f20e3e794aa4 | note | Required Test Time: 10 min (min) (as per NZBC G12 and ASNZ 3500)
| 30ea53b8-0304-4ddd-81cf-6b655a96afc2 | textbox | Date:
| 8012a329-4fed-4aa3-a46f-02521fa3f6cb | textbox | Water Level Check 1
| 86bdf576-e22e-4052-a8bc-cc1cfa5e5420 | textbox | Water Level Check 2 |  |  | (kPa)
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff