## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
396c2cda-bb58-4656-ab28-0c4dd0a29569 | checklist | Checklist - Backflow Preventer |  | Backflow Preventer
ba9910c2-a219-4b11-8cb5-d27a814614c9 | checkpoint | Details Complete
e2f704b9-dfe6-5f78-bac1-aab64c957aaa | textbox | Date
d6071612-99a4-5bcf-8c20-f04efbdd3207 | textbox | Valve Number
c6db67ca-c82f-5214-841d-819fc3fdff83 | textbox | Location
b83bc80c-73de-4df7-a1fb-ada78bffb427 | checkpoint | Result (confirm passed)
b28ed8d8-37b3-4669-83dc-8dab266b4d66 | checkpoint | Service label attached to RPZ
f829bfd4-e755-46b7-9a02-c748cf760ea6 | checkpoint | IQP certificate filed
2331a370-7a65-49ec-9b80-d0e195947b62 | checkpoint | Final Sign Off
14dddd56-a166-42f5-8559-a3fcea55d727 | checklist | Checklist - Demolition Fixtures |  | Room -
9d10d0f4-ced7-4a44-8f3a-f6fb8d9c46f5 | checkpoint | Details Completed
fa327d06-bfe6-51f0-8ff1-3fc2fdac4625 | textbox | Location:
b5f26294-44ac-58ab-9d65-ca6feb54238d | textbox | Drawing:
680ea3b1-f88a-5f45-a136-f9d926f5c179 | textbox | Plumber:
1f96de99-f97d-5604-a0c1-80f77be97cf7 | note | What area within space that can be demoed
0e96b2db-a83c-58be-ad80-b5919fcb87b2 | tickbox | Ceiling Space
eb153d4a-74a4-58b9-b0e3-41008d6e2fc7 | tickbox | Room area
69e117b5-5a17-47ed-addc-99f4b2c6c4a3 | checkpoint | Cold water services have been isolated and capped
78a2a28b-4a5a-4a0e-8e42-294ff93e8a14 | checkpoint | Hot water services have been isolated and capped
c11d667c-f9dd-4ac4-839e-954a5b9bde44 | checkpoint | Trap's have been removed and desposed of
77d9cd5c-350f-4542-859e-753f96a4ef04 | checkpoint | Waste pipes have been capped
d46be65f-e919-424b-9b82-18a119029dca | checkpoint | LPG services have been isolated, purged and capped
79c7b274-afba-486d-98e9-cada8237a237 | checkpoint | Compressed Air services have been purged and isolated
58031e20-195d-4f6d-9d41-7ac319febdeb | checkpoint | All services have been isolated and all fixtures are now safe to be removed
740b4d80-932f-4295-9448-a78b9b7d6372 | checklist | Checklist - Flushing Valves |  | Flushing Valves
56f681bc-2b9e-44a3-9d80-b8e63f220936 | checkpoint | Details Complete
5a8c78cf-e60b-5056-95fd-c1a3a716c59c | textbox | Date
802f70cb-b4b3-5a24-a53a-fa828eda8691 | textbox | Item
41199d1a-56e7-5b31-8c41-3c989603e348 | textbox | Location
6a59e67f-f9a8-421f-bd6e-1d0fbfe3d182 | checkpoint | Confirm Operation
ce6eb5a4-3cbb-4783-94ce-b423610508e1 | checkpoint | GPF Flow Ring Installed (colour)
b42afaef-f73d-4e85-a83d-f392936f273e | checkpoint | QA complete
4c1f24ca-d5d7-4ff2-b3a9-6971d4bb5fad | checkpoint | Final Sign Off
c5f3d679-0ea3-4801-8046-c657209e79f7 | checklist | Checklist - Hot Water Balancing Valves |  | Hot Water Balancing Valves
e0f1e9d4-009c-4f10-8cc6-c01e1fd0e2c4 | checkpoint | Details Complete
39c4a257-a0ba-55ca-a224-dc9c076b68b0 | textbox | Date
e8c9d0de-0074-59e9-b18b-cfed53f31388 | textbox | Location
a17d8490-9c63-5b2b-aeab-acf27edaa846 | textbox | Valve Number
d04a0b91-99b2-4b64-a9b7-f93f10ad5838 | checkpoint | Hot Water Circulating
e781b3f3-671a-4fbb-ba62-f5487d1638b3 | checkpoint | Balanced Temperature
ea0ed3a9-a2d1-4703-bcb3-1d60855def18 | checkpoint | QA Complete
65fc7c3f-0f6d-4328-ad35-eb5b6d5b5e06 | checkpoint | Final Sign Off
309a580c-256b-4a2c-86dc-eef13f6dab27 | checklist | Checklist - Hot Water Return Pumps |  | Hot Water Return Pumps
be87ea85-7553-4654-8861-02136e33929a | checkpoint | Details Complete
a820d338-8ff3-56aa-8dbd-222df2e239ba | textbox | Date
ac9cb354-659d-5183-87d6-31c63b8768b1 | textbox | Pump Number
332372f1-bba3-5635-a029-37afc5013f13 | textbox | Location
71a2bd14-8ebc-40ba-af6f-05cdc121671e | checkpoint | Electrical Complete
1a8ad27e-d0f0-4589-8cb1-6b84e3ae539f | checkpoint | Water Heating operating
8ec5a90c-8133-44dc-a01e-0ee63e6d2ed0 | checkpoint | System Balanced
c49de5b4-71ae-4262-a96d-af5549156b84 | checkpoint | Details entered
66e48cf2-746f-5c4f-abd0-13083e77e1c4 | textbox | Pressure difference across pump
753f3779-7894-56ba-9b64-c95b670f78bd | textbox | Final Flow Rate
f261e841-13ce-4042-b192-5fd30cf6cbb0 | checkpoint | QA Complete
3d36aa0d-90c4-49ee-aefb-5f8803599f39 | checkpoint | Final Sign Off
246c9e99-0ab7-41d2-96ec-f2ad7cd7f7a3 | checklist | Checklist - LPG Meters |  | LPG Meters
144a3623-2891-4275-a4b9-e4e3d3dbe5fa | checkpoint | Details Complete
7fbfacba-5e4d-5072-8073-83e1f8b2d538 | textbox | Date
5a110151-4bf5-5065-a4cb-485a974ff6f2 | textbox | Item
4511826b-9efb-5ae0-80e6-9a08699dc94e | textbox | Location
f358f4fa-1180-488f-bdf1-911fc8e95445 | checkpoint | Confirm operation with BMS
bcb55416-c9ad-4716-8c4b-243fc74572aa | checkpoint | QA complete
6ebdc796-aa5d-4169-abec-7a7866e32c0a | checkpoint | Final Sign Off
8c435d84-6510-4387-939a-aa1f3577f387 | checklist | Checklist - LPG System |  | LPG system
d7e713c8-28a0-4b7e-b2d1-04ac664f722b | checkpoint | Details Complete
21a3e0bb-131c-58ca-8e18-fa85536ed883 | textbox | Date
44e1575a-3320-5f09-921e-302a4bee83b1 | textbox | Location
a8e53947-7153-4298-b476-6d0029ff4ee8 | checkpoint | Test certificate filed
c2c45201-a01c-4937-8272-5beec7557737 | checkpoint | Pressures set. Record below
507bb9e3-bc25-43c0-8af2-7cc6f7b99c4e | checkpoint | QA complete
c4ec15a0-13e4-4a14-a992-8fe8dc2d22d8 | checkpoint | Final Sign Off
a0e2ca75-ed58-4f79-81c6-eea070bd7805 | checklist | Checklist - Pressure Limiting Valves |  | Pressure Limiting Valves
7a7d4fd4-9a05-4a39-bd94-112339babc3b | checkpoint | Details Complete
eada7fab-1c6a-5d24-8f4b-c1eda0b106b0 | textbox | Date
69b22e59-3b60-5fec-81db-26ae563340c5 | textbox | Valve Number
9a3ec182-0ba8-5f61-97f4-2226e96fc34a | textbox | Location
cc20d9a1-5ca0-4943-bffb-6db65adc180c | checkpoint | Pressure Set
d3c635e3-2176-56dc-b903-420166d3e1f0 | textbox | Set Pressure (KPA)
b1b8a112-878b-4d1f-b864-76d27e2b0a42 | checkpoint | QA Complete
7567ebc7-b4df-4c82-a92b-0c5f44ed5fed | checkpoint | Final Sign Off
ea7fa487-77a5-4623-ab97-01cba2f88c76 | checklist | Checklist - Programmed Maintenance |  | Programmed Maintenance Checklist
b40945c5-5e01-4af5-8b10-05f074beb0cc | checkpoint | Details
84d7e2f0-0b31-5273-b1ab-5eabb1ef5047 | textbox | Maintenance Number:
55b48851-df5a-5b86-a3c7-d107b2b55295 | textbox | Area
ad1e94ee-4bbd-4585-be13-454b6d435436 | checkpoint | Having recieved approval to carry out the maintenance, ask the department heads if there have been any problems with the plumbing systems
c49b12ca-3dd9-4bbd-a318-4a04caf1f127 | checkpoint | coordinate with the electrical trade to carry out the maintenance at the same time
5e546f56-2dcf-4591-abec-75455437e69e | checkpoint | Inspect the integrity of the portaboe hot and cold pipework
5c9a04f6-bd9f-4ccb-87e9-751e34d4eed3 | checkpoint | Inspect the integrity of the waste water pipe work
27000d6a-23c8-46f8-9cbe-b5e5716a80c6 | checkpoint | Inspect the integrity of the HWC for leaks
0bb8c982-534c-4501-9f73-944de929aa4c | checkpoint | Inspect the integrity of the HWC valves
6533144b-a7e7-4efe-9f9e-985ab105ca21 | checkpoint | Inspect the integrity of the TWC temperatures
13772c0b-3e54-471e-9510-e013f0f64224 | checkpoint | Inspect the integrity of the toilet flush
4ee1c7eb-cf05-4123-815b-e00afbdce9a0 | checkpoint | Inspect the integrity of the pumps
6489d81c-0fab-4a20-a26f-e7e7cdea5ceb | checkpoint | Inspect the integrity of the trap primers
fd534447-f3f0-48bf-ac03-73af8d7ca5cf | checkpoint | Inspect the integrity of the suction pipework
37f4855c-09eb-4a34-8d59-ed14a448aba9 | checkpoint | Inspect the integrity of the LPG pipework and valving
a9ee206e-aa2e-4359-acfb-a2963399551a | checkpoint | Inspect the integrity of the basins and sinks
536c439c-a257-4a7e-bda7-e6475d712310 | checkpoint | Inspect the integrity of the suction pipe work
e1ea6d73-6a26-499f-af08-c5a6edb7bb28 | checkpoint | Inspect the integrity of the plaster traps
0da8173f-d40f-47f9-9dd8-4b3665bfe7c1 | checkpoint | Inspect the integrity of the foul sewer and water systems
ba1b098e-2d28-487e-bba6-1b71ae45c1a0 | checklist | Checklist - Sanitary Drainage |  | Sanitary Drainage Below Slab:
341ac49e-b7b8-421f-93a6-8ab93c373b0a | section | Details
8729899b-c1e8-49fe-9ee6-a95393c4ace5 | checkpoint | Details Complete
e72b4d5c-74ec-5612-b7af-d3db65462b71 | note | Consent Number: ABA 2015 1137
b60b6d56-2739-530f-94e1-ab5a8084014f | textbox | Location:
90591743-205d-5968-b74c-95ff94e335ae | textbox | Drawing:
7af2d8cc-dc25-5f0d-992a-8bdb208cb97e | textbox | Plumber:
445cf570-59dc-5f9c-ae19-764c41d5429b | textbox | Date:
a0d4a3e1-6fcb-43cc-920c-1fd0d850c429 | section | Water and Waste Pipe Work QA
2e5773b0-e911-430f-aaf1-f2a83e0960aa | checkpoint | Area tidy and ready to start
617750d4-d9f1-40dd-a5f2-7642fec477da | checkpoint | Check pipework is installed as per listed drawings
ea6d7f22-41e7-41fc-8a41-f7e748136787 | checkpoint | Confirm Pipe bedding at least 75mm compacted thickness
aff25519-8192-4e6c-aa8c-0e4644770223 | checkpoint | Confirm pipe bedding material AP20
265bd59f-0588-47f8-a02d-2dae87d3382d | checkpoint | Pipe work layed to invert and grades as per approved shop drawings.
17ac843e-e570-40b8-a409-bc387bce65bd | checkpoint | Check that risers are in the correct location and secure
f15ae87b-ed79-47d5-b063-6a8ea146b7dd | checkpoint | Check that the pressure test is complete
2cf591e7-5a0f-4526-82c5-39389df579ff | checkpoint | Check that the test sheet is filled out
6a8f0210-a3d7-4007-8299-d7987ffd9c8b | checkpoint | DCC inspection complete
013c89ba-29f5-476e-905c-baec75a1b352 | checkpoint | Trenches backfilled and compacted AP65. Marking tape installed
ff145778-cec8-4cb9-bd1d-9baec163aade | checkpoint | QA sheet completed and loaded in system
3fb53e8a-2657-4834-85a5-3b7b0b54b886 | checklist | Checklist - Second Fit QA |  | Basin Sensor Taps
e2bd4f7e-2e94-432b-9383-619039ad4dbf | checkpoint | Details Complete
ce71e635-7c2b-5e43-b740-b740f0bc4844 | textbox | Date
e868f369-a75a-56ec-aeee-8788281b2158 | textbox | Item
2c3398c9-8b0d-5c5b-b487-9f1b693aeca9 | textbox | Location
c60e48af-0a41-486e-8e13-5b202105d3e4 | checkpoint | Confirm Operation
d21ec6d2-1b68-41e3-991f-d01eb3980d62 | checkpoint | QA complete
9a356663-e0e5-47a0-a2df-05595b03bd48 | checkpoint | Final Sign Off
196ddb4a-6b6a-4ff5-b4f9-3d563e136b15 | checklist | Checklist - Thermal Mixing Valves |  | Thermal Mixing Valves
f3303fd6-52dc-437c-970f-46f53d03fd8d | checkpoint | Details Complete
908f3eec-e171-5b91-84a0-7c97f4314a76 | textbox | Date
65e5bd9b-ec7f-5bef-b592-cae66b71b940 | textbox | Valve Number
4e98e756-2ca3-58c3-80a3-de2f0706a998 | textbox | Location
640f19c7-f2d9-43d6-94e0-e751c0d3c474 | checkpoint | Set Temperature. ∞C
313d351a-5c07-4f17-98e5-a43b35a766d0 | checkpoint | Lock cap fitted
a0d4be0d-9ae9-49c7-9646-bc277079ba66 | checkpoint | QA complete
baa215fc-2d49-4144-a6eb-60e5a38a6537 | checkpoint | Final Sign Off
9501fd5b-8974-4616-8cfa-22eceebc48b9 | checklist | Checklist - Trap Primer |  | Trap Primer
04ed104a-b126-4f73-8acc-ba8ff5ace112 | checkpoint | Details Complete
21405401-f6c6-5064-b756-a859b1543ed4 | textbox | Date
feb6e15d-c649-50ea-8a6a-a0122066bc5d | textbox | Trap Primer Number
51a3be19-2d1b-58df-bc63-ae128042f765 | textbox | Location
73d3e33a-be2b-44b1-b412-97ce11cc50c2 | checkpoint | Water system complete and charged
18c3bd3b-b3c7-4ca9-9447-926c207e90d8 | checkpoint | Electrical supply commissioned
2cd34c18-6d5f-4b71-9eec-576794515d2b | checkpoint | On/Off times set.(tick)
5ad4e03a-315d-458b-8ebc-dd5b8797749e | checkpoint | "Test button" Press confirm operation.
a51f121e-e9c6-4c90-9785-0ec89fdc7d7f | checkpoint | QA Complete
08063d9d-a893-4e74-9644-3a8e0deb7ec2 | checkpoint | Final Sign Off
a3405f41-e17e-4d07-be82-36cc33a775e4 | checklist | Checklist - Water Meters |  | Water Meters
39eaa295-3f05-40ee-9103-f282ee0b9414 | checkpoint | Details Complete
d0ed398e-4d74-564b-a28c-59a69c4491f5 | textbox | Date
face3b38-83cb-5fea-98dd-0941d2b86eb3 | textbox | Item
34a5b97c-9dec-57a5-8a74-3bacdcc28fc1 | textbox | Location
070943e4-5994-4057-921e-e849d7e54d87 | checkpoint | Confirm operation with BMS
5d46b4ef-2de0-4edb-bbac-3236cfcdc2e6 | checkpoint | QA complete
f909c252-4a43-47c4-8895-a928a1b4dc08 | checkpoint | Final Sign Off
9da48b2c-49e7-4d06-91ed-faa45547cf77 | checklist | Checklist - Water Quality Testing |  | Water Quality Testing
9e48acba-7c26-47ab-b62e-d8e99e376121 | checkpoint | Details Complete
206f80e9-bc10-584f-87c9-96b8614fb1a2 | textbox | Date
1f3ec462-cdb3-50e0-84e2-e69ccdbf7163 | textbox | Test point Location
4291cbaa-482a-4c8b-a26c-47652226e996 | checkpoint | Lab results confirmed and attached
dfad02db-78ec-4fd3-9946-5f845f0a9fdb | checkpoint | QA Complete
b9287713-6a1d-490a-8d95-e5cbbd0f25ee | checkpoint | Final Sign Off
d720574e-b2ca-43f0-9c20-3d3680b7b53f | checklist | Checklist - Water Strainers |  | Water Strainers
04addd2d-4e51-4c93-b4fb-d1b8c184c1e6 | checkpoint | Details Complete
bc70a077-fccc-5383-bc0e-4c94e5343a8a | textbox | Date
ab2e550b-7edc-5617-be4c-efcc384c6c86 | textbox | Item
1a7407b9-bc26-5a93-8847-4d204da806b1 | textbox | Location
44a53c2c-b22e-41c7-8f6a-a69b2d6d17fa | checkpoint | Size (Micron's)
2ed94522-e46e-473b-84b2-9dbf3543d005 | checkpoint | Strainer mesh replaced
c833b1cc-3e4e-4d14-bb00-e08d176d25b6 | checkpoint | QA Complete
12a1620f-426f-47b3-9861-4b94082176f5 | checkpoint | Final Sign Off
617bd59d-d10c-48ed-acac-669bd318891d | checklist | Civil Drainage - Stormwater & Foul |  | Civil Drainage - Stormwater & Foul
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3a729f23-e534-4a84-81c4-44188eaeec10 | checkpoint | Plans checked against what has been supplied for pipe types & size
6793dc7d-338e-49b8-8c85-1a73cc0617cb | checkpoint | Trench shoring in place or benched if required.
daa3268b-54a3-4a14-b556-4304213e7d20 | checkpoint | Trench bedding material (AP20 or dust) compacted
b9d23bcf-4a7b-458c-baa5-f13d68208dff | checkpoint | Sumps & manholes checked and confirmed for correct position
43a8db8f-0ac8-4dce-ad68-c254128a71d4 | checkpoint | Manholes have corbels in place and manhole benched
6d9eebf3-e4fa-4434-91e1-75e0e37e07c5 | checkpoint | Drop structures complete
0d8dcf2c-e85f-41d1-86bf-bb001c14c169 | checkpoint | Pipe laid to correct grade
8a17278d-5915-49ad-b7f5-55908b710eb6 | checkpoint | Pressure test complete
be2949d7-08a9-4ee6-a96b-040e674a4a6c | checkpoint | DCC inspection complete
e4e49edd-d9d2-4781-9f3b-4aa54a1bd3fe | checkpoint | Trench backfilled and compacted
10465d1c-aef1-4a52-aec4-e20e107b85cc | checkpoint | Commissioning signoff
93f5b0cd-8a07-4b22-a93e-b4e54c643ff5 | signoff
d3befa2b-93a1-4525-9cb5-cc12339fcb49 | checklist | Design Certificate - Gas Installation |  | Gas Installation Design Certificate
c040e991-8ab2-40c4-b8dc-ff5840ee3492 | checkpoint | Gas Installation Design Certificate Details added below
4ed8f6fc-70ea-526f-b5ba-d2c19d73e041 | textbox | Job
22cb1d00-f6b9-5b46-b810-bca84b456433 | textbox | Date
4faa242a-a573-5c06-87ca-204c549645e1 | textbox | Gasfitter
d9e52976-337d-555c-a99a-206832968ec9 | textbox | Gas Type
c0450db1-20cb-4b45-830a-392cd6a4225c | checkpoint | Pipe Size AS/NZS 5601.1:2013 Appendix F
d02cc167-3d93-513e-8135-2a4fae2d4914 | textbox | Pipe Size
f02a6040-46eb-56c5-9ee8-d719697228bf | textbox | Pipe Branch Line Size
0e2c66be-deb7-5adf-ab76-1896778ff7b9 | textbox | Pipe Material
39bc4276-9653-5be8-b664-6af90ca05eac | textbox | Pipe Length
75ded741-b8aa-4213-b79f-87740c3dd20b | checkpoint | Test procedure AS/NZS 5601.1:2013 Appendix E
f7e3748a-b560-47aa-a7c0-8c835fb86484 | checkpoint | Pipework test E4
ecea9785-f406-58a1-9481-a2aba1aea0d8 | textbox | Test Pressure kPa
5e6291c0-905e-551f-9215-857e0143b26f | textbox | Duration
ff520114-1177-5261-9260-474b849c3993 | textbox | Drop/raise
f7ac9ec1-5ba1-4ea0-ba9c-38bd0c25382f | checkpoint | Installation Test E5
cde8c50b-2e53-5dce-90ee-1309d5dbdb0c | textbox | Test Pressure kPa
345081b9-f092-5b15-b299-7af2a932bd67 | textbox | Duration
c9638f0f-384e-5352-bdd3-eef014640332 | textbox | Drop/raise
014b8b7a-60b4-45e5-b73f-bf981f567b61 | checkpoint | Final Connection Test E7
e12cfb9a-9589-5784-98e5-9e0d63b2a13e | textbox | Test Pressure kPa
cec46b67-eca5-5bd5-a3c3-a012fd758977 | textbox | Duration
30fdecd2-e10b-559d-b54c-a40c74f4a165 | textbox | Drop/raise
a8825473-ad0a-5b95-be92-71db3f2f6871 | textbox | Working Pressure kPa
2fbbdb15-aae5-4a53-86ed-9a50ea8e56cf | checklist | Pump Station |  | Pump Station
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c6c7cb79-fb8f-4023-81c4-646e51c0ff38 | checkpoint | Check ground conditions for correct installation
d917f4fa-8bb5-4d18-bf11-cda7f43e0f91 | checkpoint | Backfilled with appropriate fill
e7b514b0-a2ea-4502-a896-327e3e0343bd | checkpoint | Check floats and controls clear of any obstructions in pump chamber
7363fc64-72d1-4378-bd1f-3edc5c8938f8 | checkpoint | Check correct electrical connection has been made
8aa4ecaf-e30a-4b10-8224-47ccf544d072 | checkpoint | Fill tank with water to float level and check operation of pump
d627bb84-d391-4563-85e9-085c9d02c703 | checkpoint | Check high level float alarm
e11fc530-4257-4424-845e-de5f3caf5547 | checkpoint | Commissioning signoff
3aaa7180-1ca3-4af2-a3fa-c20cb98808ab | signoff
c096f6f2-daa0-4368-aca2-f6145742ee49 | checklist | QA Sheet - 1st Fix - LPG |  | 1st Fix - LPG
7d947e12-4a1f-4f28-8445-4eb0eae7012d | checkpoint | Check pipework is installed as per listed drawings
be64bcfc-12e7-4bab-b576-531501a2cb7a | checkpoint | Check that the correct pipe sizing is complete to each fixture
7764fa83-7006-4320-87cf-d11bf72c2123 | checkpoint | Check that the wingbatts are installed at the correct height
a3e32c9f-b672-4b48-823a-c136a0de37bc | checkpoint | Check that seismic restraints are installed
78d8c72c-4803-446c-9de8-f53547f4652a | checkpoint | Check that the fixing's are installed at correct height
5356bc1f-c1ff-4ac1-b86a-d8f3024008d0 | checkpoint | Check that the pressure test is complete
d05a3274-4c48-4c76-adae-36ba7aff9d2d | checkpoint | Check that the test sheet is filled out
c8e5e002-dbeb-4969-92e3-4164cce91e2f | checkpoint | Check the pipe labels are on
a41e5877-9e99-4a11-add1-d131cee1c32a | checklist | QA Sheet - 1st Fix - RO Water pipe work |  | 1st Fix - RO Water pipe work
8a16b7a6-f92c-4807-9d6d-7f69881fa900 | checkpoint | Check pipework is installed as per listed drawings
913a81c4-11ca-4623-9a5b-9b8ff6452764 | checkpoint | Check that the correct water and pipe sizing is complete to each fixture
b81bf4dc-efc0-4f2b-9c53-b034dc1bbd49 | checkpoint | Check that the wingbatts are installed at the correct height
9971f2fe-9811-494a-9fc1-6e7565b12556 | checkpoint | Check that seismic restraints are installed
5a24534f-5fb0-45d6-8943-c0231bb4d453 | checkpoint | Check that the waste pipe is the correct location
48c0da9f-42bb-47d7-af4e-653cbcb58a7f | checkpoint | Check that the fixing's are installed at correct height
e89eac64-4670-440e-b29b-6ec824fcfb14 | checkpoint | Check that the pipe insulation is installed
31ea73c5-a068-44fc-9e9a-a7fdf9ef177e | checkpoint | Check that the acoustic insulation is installed
c6fedb47-51be-40c3-a2ee-56abe015db4f | checkpoint | Check that the pressure test is complete
1ff5f84c-f2a8-4fe8-b42c-c5987275d772 | checkpoint | Check that the test sheet is filled out
2e1b273e-9277-4e41-bf87-ca81d518364c | checkpoint | Council inspection complete
d492d6fb-4d68-41e3-88f5-68328fdb8fec | checkpoint | Check the pipe labels are on
779cbcbd-d0ec-4527-afc3-6df88f91da29 | checklist | QA Sheet - 1st Fix - water pipe work |  | 1st Fix - Water pipe work
ab60e3d0-bbc6-4948-ad40-7841ae6b2d54 | checkpoint | Check pipework is installed as per listed drawings
88cbe3a6-5fa2-4c4f-bcbc-f6b57478060e | checkpoint | Check that the correct water and pipe sizing is complete to each fixture
1c268886-eb1f-408f-bc21-fbb94f03cc9d | checkpoint | Check that the wingbatts are installed at the correct height
a1beaed3-825d-409f-aa9e-cd162416b304 | checkpoint | Check that seismic restraints are installed
2b4488a0-5f85-482f-9ffa-3479e209dabc | checkpoint | Check that the waste pipe is the correct location
43e3cfd1-dcaf-4fea-ae8c-e033f530ebf5 | checkpoint | Check that the fixing's are installed at correct height
115e667f-e0b4-40ca-bd5b-517e4d68e7bd | checkpoint | Check that the pipe insulation is installed
e336e765-99bf-403b-92c0-28d286c2b8fd | checkpoint | Check that the acoustic insulation is installed
f602c502-7236-40d6-9fd6-5378c5fe9ed4 | checkpoint | Check that the pressure test is complete
46f522a3-b78d-4aba-9dcc-a60a26552149 | checkpoint | Check that the test sheet is filled out
bf5bfec4-ec51-470b-8f4b-afe0177c3220 | checkpoint | Council inspection complete
9efdefae-6fa9-4ec3-8fed-fc9c1950f05b | checkpoint | Check the pipe labels are on
42cd68f7-7801-4327-b62e-13e427c63c3a | checklist | QA Sheet - Sanitary drainage - waste pipe work |  | Sanitary drainage - waste pipe work
5aa45f7a-594e-47a8-96d8-d025ad3077c8 | checkpoint | Check pipework is installed as per listed drawings
f0855ae9-8c1e-4e0a-9dc9-973268d954d2 | checkpoint | Check pipe brackets conform to PS1 design
af518736-3021-48e6-8699-f01a013790b9 | checkpoint | Check maximum spacing of brackets not exceded. Ref Aurecon 6.4.8.3
aa69c5e5-a12c-466a-9ad1-607650308d1f | checkpoint | Drains installed at correct grades/fall ratios
f5d0b323-f603-4e63-a9bf-72c6f712af01 | checkpoint | Check that risers are in the correct location and secure
76a34096-8da6-4d19-9337-3a72a50244df | checkpoint | Check that the pressure test is complete
91d652a2-047f-4d77-878a-086c874b347e | checkpoint | Check that the test sheet is filled out
ba46877b-d95e-43bc-9073-167f26bc13a7 | checkpoint | Council inspection complete
902ed489-55b3-432c-a359-6abf260f60c5 | checkpoint | DCC inspection complete
0649deef-5cc0-469b-b2bf-e4abb12feb91 | checklist | QA Sheet - Sanitary drainage below slab - water and waste pipe work |  | Sanitary drainage below slab - water and waste pipe work
f83b4ee6-bcd9-414a-ba6e-1bf4931c49d6 | checkpoint | Check pipework is installed as per listed drawings
6d4c515c-1e86-40c2-a1f9-06898cc4b2bd | checkpoint | Check pipe brackets conform to PS1 design
cd6e3517-753b-4647-978f-5aa2f3b91f9d | checkpoint | Check maximum spacing of brackets not exceded. Ref Aurecon 6.4.8.3
a9ca88dd-3feb-4f35-b762-9ba385179e59 | checkpoint | Drains installed at correct grades/fall ratios
85fe5a50-2b32-4b3f-a3a5-238c37514936 | checkpoint | Check that risers are in the correct location and secure
0b9bf7ed-a6fc-45c2-a730-b046b6df5c11 | checkpoint | Check that the pressure test is complete
5dfdf5d1-3ec0-4ea2-8685-f35081945647 | checkpoint | Check that the test sheet is filled out
17ae6a4f-d644-46cb-b5bb-26a61db9ead3 | checkpoint | Council inspection complete
a3f1eb85-3ac4-4c39-9b37-28f628955ee7 | checkpoint | DCC inspection complete
b424b23e-2756-4d94-afc6-a00ffa07feeb | checklist | Safety Shower Operation & Flow test |  | Safety Shower Operation & Flow test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2fd831ac-08f1-47d3-be86-d2f9e38ba1f6 | checkpoint | Water supply delivers required flow when shower and eye wash are operated
93ae4dc3-eac0-4b3b-8fa6-fca090951ca5 | checkpoint | Hands free valve operating correctly
999270af-28b3-48ae-96e4-773fd4357bb3 | checkpoint | Shower delivers required 75.7 litres per minute
41ef8c5b-7489-42c6-8a4a-07eb5b17a86a | checkpoint | Eye wash delivers 11.4 litres per minute
c0ec5b85-6041-43f0-9236-bbabd79d333c | checkpoint | Tempering valve set to correct temperature
04faf5a3-79ed-4cfc-a8ac-78ab53f37e9a | checkpoint | Commissioning signoff
c0cb000b-6316-412c-90a2-1c29921718b8 | signoff
db21b27e-de43-4092-9e7d-975abd1b1663 | checklist | Test Sheet - Gas Pipe Line |  | Gas Pipe Line Test Sheet
8af732cc-2c31-410b-8b16-c9affa87c9c9 | section | Job Details
bee5333d-6f2a-4665-bcbf-52f9919b786f | checkpoint | Job details complete
af367181-0358-56d6-9293-a24f89ac9d30 | textbox | Job:
10f9e384-b872-58d5-bd8d-ecbf8f45645a | textbox | Gasfitter:
13def8f5-1847-5f47-ace0-e4d8ce85e0c2 | textbox | Date:
63692698-4fa8-59fc-8b42-0a0bac4813a1 | textbox | Site Address:
3238f544-289a-592c-b06c-f3a5b8afa718 | dropdown | Gas Installation "Safe To Use" | No,Yes
905d805e-627c-58bd-a023-67008578d2a5 | textbox | Risk Classification
067f6483-fd56-5950-bf0c-afb27ab57b8a | textbox | Part/Whole Installation
c400b2e3-81af-51fa-8bf5-dec0ea0e42e6 | textbox | Gas Type
6fd1a065-3d72-5b39-85d4-2c7057c1868e | textbox | Certifying Gasfitter
0bf98ca5-3b56-5e62-ba22-5d9cf2235471 | dropdown | Work done in accordance with means of compliance (AS/NZS 5601.1:2010 part 1) | No,Yes
72b24930-23ba-4d94-9f27-f41e733fd3da | section | Test Details
5d7595fd-fae9-493f-b39c-29f5ec60b8d5 | checkpoint | Test Details:
846912bf-9cf6-5bab-bb40-8ea693aaee9b | textbox | Work undertaken:
c05dfd01-a50c-573c-a2a0-2b25b3ba7a59 | textbox | Test location:
469c798d-ba74-47e0-8db0-994b1ac5e74c | checkpoint | Test procedure AS/NZS 5601.1:2010 Appendix E
f3476c18-df90-5111-90f2-4c08f2dc46c0 | textbox | Date:
10ccb851-315a-5980-a535-9ae73885a026 | textbox | Test Pressure: |  |  | kPa
8576dfd7-e0ad-50aa-8659-1dd907fc4dfe | textbox | Duration:
9ef9d5ac-e23e-58fd-b356-29da286a976c | textbox | Drop/raise:
0777e1cd-7ae4-411d-930e-859a57c46e3f | checkpoint | Leakage test of Existing installation E6
bde49c1f-cf0c-55fc-8b67-8c9e1b3f6af6 | textbox | Test Pressure: |  |  | kPa
cbd63c2a-cb58-57c6-932e-16e2651fc34b | textbox | Duration:
226a256c-95ba-5162-9866-79d4aef1c9e9 | textbox | Drop/raise
b1f5eef1-ef69-413b-babc-aeaa8aa26a24 | checkpoint | Final Connection Test E7
deb7c05b-d9e1-55e1-8803-1fe2952f031d | textbox | Test Pressure: |  |  | kPa
6c68d066-5117-5f17-b84c-56f7421da5a1 | textbox | Duration:
099870dd-9d2b-5903-9d21-89a0f00659cb | textbox | Drop/raise
c1a8b348-7349-5a99-93b9-abb9bec260ee | textbox | Working Pressure |  |  | kPa
a789c215-0c28-442f-af1f-35ddaf423c6a | checklist | Test Sheet - Pipework Pressure - Water |  | Pipework Pressure Test Sheet - Water:
368ff4aa-8e5e-4030-b677-2b8f9f69e5b3 | checkpoint | Details Complete
ad187e91-b0f3-5040-ad56-73eede307463 | note | Consent Number: ABA 2015 1137
e838d214-7ed2-5def-b524-ac3573aec750 | textbox | Location:
2374f045-976f-55d7-97b2-10856452827f | textbox | Drawing:
421903c9-6e38-5a37-b313-fac759a9ac0e | textbox | Plumber:
3bb48199-990c-5384-b7a7-9e914f9f3d5f | textbox | Date:
dcee89e1-0bc8-4325-bf89-ecffea01061d | checkpoint | Testing
0a375ad7-36b4-5ba0-840b-045b444e5b9a | note | Required Test Pressure: Static Water Test
c7e9dd98-4ec1-5a7a-a16a-7c2e56a838ae | note | Required Test Time: 1/2 hour (as per NZBC and ASNZ 3500)
cac7c4e7-869f-51ef-bba1-b1dc7666d22e | textbox | Date:
52281352-b825-5b1f-a88b-6d73f9237be0 | textbox | Start Pressure: |  |  | (kPa)
c4497956-c2b0-5bd1-a697-24fcb9e0d81f | textbox | Finish Pressure: |  |  | (kPa)
903b8f2f-e5fe-47cb-9ec9-bb010d9c26ec | checkpoint | Signoff
b43329e4-ccbb-4263-9e55-00b967bd7cce | checklist | Test Sheet - Pipework Pressure - Water/LPG |  | Pipework Pressure Test Sheet -
daafb953-6926-4e97-a707-24adefea7059 | checkpoint | Details Complete
21312430-21ac-500d-9c9d-a9e09ebf89ae | note | Consent Number: ABA 2016-513
dbb587a5-8ce8-5686-a38e-7ccc576d6d77 | textbox | Location:
cf8eac64-1df5-5039-b216-6221cea7c410 | textbox | Drawing:
f82506cc-3bce-5004-9016-a86b839694e5 | textbox | Plumber:
048928ea-d910-5e9b-9bf4-52f3e2a9397b | textbox | Date:
f4643749-3bcb-4585-af37-b3a16f95c918 | checkpoint | Testing
bfcfb761-2266-5064-8856-86863214697e | note | Required Test Pressure: 1500kpa (min)
dbaea371-c278-5ec1-a16f-0ab16cac92f1 | note | Required Test Time: 15 min (min) (as per NZBC G12 and ASNZ 3500)
511d90c2-9f71-5c4f-b7e5-7669c8e409da | textbox | Date:
de3f0998-3808-564b-a3bd-b52eb83c9f99 | textbox | Start Pressure: |  |  | (kPa)
c7acd757-d477-5b9f-89b1-c9991ea6b32b | textbox | Finish Pressure: |  |  | (kPa)
cf371209-2c99-4408-91c1-769369bb989d | checkpoint | Signoff
ff5866ec-399d-42dd-bc9b-33a167ab9077 | checklist | Test Sheet - Sanitary drainage/Suction |  | Sanitary drainage/SuctionTest Sheet -
a70dd09a-797d-47c8-bf58-c4cbef37b5fb | checkpoint | Details Complete
6964cb48-ea27-583a-965d-dd5bac2f1799 | note | Consent Number: ABA 2016-513
40362419-c1da-5a9a-b2b0-5045a8a0b21a | textbox | Location:
23d08d9d-43f3-51bb-81d0-a639169db808 | textbox | Drawing:
60fee6b9-4fbb-52a1-bac3-59a45f8ed7dd | textbox | Plumber:
c393724c-05ff-5e8f-af0d-a56956908984 | textbox | Date:
e20f856d-09df-4884-b3c5-6442337133f5 | checkpoint | Testing
26d1b478-353e-54e9-b18e-442dc6cc95b3 | note | Required Test Pressure: Static Head
4e6982f6-3b79-5b7f-b627-3b24fc8bfbc4 | note | Required Test Time: 10 min (min) (as per NZBC G12 and ASNZ 3500)
740a62a3-8058-5c7f-bca0-f73b91629e46 | textbox | Date:
b57a7f63-fccd-52fd-8688-68e2145dc8ea | textbox | Water Level Check 1
4bb7a50a-8c4d-528e-92a4-d5dbff2b1427 | textbox | Water Level Check 2 |  |  | (kPa)
da9a7cb2-08da-4a25-9b76-c3ded156fe39 | checkpoint | Signoff