## MFU-FH-ITP-0009
|  |  | Inspection and Test Plan - Granular Pavements - Cement Stabilisation | [7 empty] | Document # ITP-002
Client: | DTP - Vic Roads |  | Construction Process: | Subgrade Stabilisation |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  | Specifications: | VicRoads Specifications Section 307 |  | Name | James Gardiner | Name: | Syeed Abu |  | Name: | Simon Jaworski
Contract No: |  |  | Structure / Component: | Earthworks/Civil
|  |  | Location: |  |  | Date: |  | Date: |  |  | Date:
Lot No: |  |  | Lot Title: |  | Location CH: |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Mix Design |  | Prior to start | Mix design to be selected based on pavement material investigation. Binder application rates to be confirmed with client prior to start. | VR 307.05 | Record | Record | HP* | Project Engineer | N/A
2 | Preliminary level confirmation |  | Prior to start | The surface level of the area to be stabilised shall be confirmed to be within level tolerances prior to commencement of stabilisation. Unless otherwise specified, +15/-25mm. | VR 307.03(a) | Visual | Visual | IP | Project Engineer | N/A
3 | Binder Supply |  | Each production day | Quicklime & Hydrated Lime to meet requirements of AS1672. Cement supply to comply with AS 3972. ALI shown on delivery dockets. | VR 307.04 | Test Report | Test Report | IP | Project Engineer | N/A
4 | Spreading of stabilising agent |  | Each Lot | Binder shall be spread at the specified rate. In passes not exceeding 15kg/m2. No traffic to be allowed after spreading other than construction traffic. Matt test & load cell outputs recorded for QA purposes. | VR 307.14 | QA Report | QA Report | IP | Project Engineer | N/A
5 | Slaking of Lime |  | Each Run | If quicklime is used it shall be slaked with sufficient water to allow full slaking to take place prior to mixing. Full slaking will be deemed to have been achieved when all quicklime that has been spread has changed from a cream coloured granulate to a fine white powder and there is a cessation of rising vapours. | VR 307.08 (c) | Visual | Visual | IP | Project Engineer | N/A
6 | Mixing of stabilising agent |  | Each Run | Mixing shall commence as soon as practical after spreading of the cementitious binder. Water to be added as required to achieve and maintain close to optimum moisture content. Mixing depth to be physically checked. | VR 307.08(e) | Visual/ QA report | Visual/ QA report | IP | Project Engineer | N/A
7 | Compaction |  | Each Run | Compaction of the stabilised layer shall commence immediately after mixing. All compaction shall be completed within the times specified in Table VR 307.052 after addition of the cementitious binder. | VR 307.08(f) | Visual | Visual | TP | Project Engineer | N/A
8 | Trimming |  | Each Lot | On completion of initial rolling, the stabilised material shall be trimmed to the specified surface tolerances. Water may be applied during this operation to replace evaporated moisture. | VR 307.08(g) | Visual | Visual | IP | Project Engineer | N/A
9 | Test Rolling |  | Each Lot | Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer. | VR 307.10 | Visual | Visual | HP WP | Project Engineer / DTP |  | Date / Comments:
10 | Compaction Testing |  | Each Lot | If required, density testing to be undertaken as per table 307.151 or otherwise specified | VR 307.15 | Test Report | Test Report | TP | Project Engineer | N/A
11 | Maintenance of Stabilised layer |  | Each Lot | Surface shall be kept moist and protected from damage by traffic and construction activities until further pavement layer is applied. | VR 307.11 | Visual | Visual | IP | Project Engineer | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: James Gardiner |  | Position: Project Engineer |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent