## Structure Acceptance
Date:
Doc: | QA Checklist: Structure Acceptance | Project Details:
Number:
Loc/Area |  | Site Manager:
Level: |  |  | Signed:
Elevation: |  | Site Foreman:
Grids: |  |  | Signed:
Symonite drawing/detail referenced for construction:
Product Install manuals:
Nb. | Performance criteria |  | Symonite sign off
|  |  | Status | (√) if PASS (X) if N/A | Initial | Date
1 | Formal Handover Received
1.1 | Has the Main Contractor provided a Formal Handover? |  | Pass
Notes:
2 | Structure Opening Checks- Maun Contractor to Symonite
2.1 | Grid-lines provided by MC? |  | Pass
2.2 | RLs provided by MC? |  | Pass
2.3 | Sill Structure completed? |  | Pass
2.4 | Jamb Structure completed? |  | Pass
2.5 | Head Structure completed? |  | Pass
2.6 | Sill waterproofing completed and acceptable? |  | Pass
2.7 | Jamb waterproofing completed and acceptable? |  | Pass
2.8 | Head waterproofing completed and acceptable? |  | Pass
2.9 | Floor slab in tolerance? |  | Pass
2.1 | Clear opening/ structure in tolerance? |  | Pass
Notes:
3 | Structure Inspection Sign off
3.1 | Is the above area ready to commence installation? |  | Pass
3.2 | Client agreement and sign off |  | Pass
4 | Completion
4.1 | Confirm work area clean and tidy. Note: photo area |  | Pass

## Alucolux - Hook and Pin
Date:
Doc: | QA Checklist: Alucolux Hook and Pin System | Project Details:
Number:
Loc/Area |  | Site Manager:
Level: |  |  | Signed:
Elevation: |  | Site Foreman:
Grids: |  |  | Signed:
Symonite drawing/detail referenced for construction:
Product Install manuals:
Nb. | Performance criteria |  | Symonite sign off
|  |  | Status | (√) if PASS (X) if N/A | Initial | Date
1 | Pre-start. Checks to be by both Symonite and main contractor.
1.1 | Siderise QA has been completed. |  | Pass
1.2 | Wrap QA has been completed. |  | Pass
1.3 | Check framing layout provides adequate fixing points to be able to meet the required fixing centres. |  | Pass
1.4 | Check all window, door and corner flashings are completed |  | Pass
1.5 | Joinery and TPO protection in place |  | Pass
Notes:
2 | Alum Support Angle INSTALLATION. Initial checks to be by Symonite Installer.
2.1 | Size, Location and centres are in accordance to set out drawing. |  | Pass
2.2 | Apply Vaproshim or vaprotape to all screw pentrations. |  | Pass
2.3 | Correct screws used as per drawings for timber and concrete |  | Pass
Notes:
3 | Vertical Rail Support INSTALLATION. Initial checks to be by Symonite Installer.
3.1 | Plumbed and straight.Check alignment and cavity is as per shop drawings and set out drawings. |  | Pass
3.2 | Apply Vaproshim and/or vaprotape to all screw pentrations. |  | Pass
3.3 | Ensure SPAX screws are straight with the rubber washer in tact |  | Pass
3.4 | Ensure fixing at 800crs is achieved |  | Pass
3.5 | Final check of alignment with straight edge |  | Pass
Notes:
4 | Alucolux Panels INSTALLATION. Initial checks to be by Symonite Installer.
4.1 | Check panel numbers match insdtall plan for the location |  | Pass
4.2 | Check the Alucolux Panel is seating perfectly onto the pins. Plumb and straight with correct space |  | Pass
4.3 | Panel secured properly as per shop drawing details. |  | Pass
4.4 | Internal corner angle installed and sealed. |  | Pass
4.5 | Install interstorey flashings as per shop drawings. |  | Pass
Notes:
6 | Downpipe Shrouds and Flashings by Symonite
6.1 | Soffit flashings installed straight with correct fixings & Sealant |  | Pass
6.2 | Install shroud and check alignment with full height stringlines |  | Pass
6.3 | All panel plastic and sealant tapes removed. |  | Pass
Notes:
7 | CLEAN UP. Initial checks to be by Symonite Installer. If necessary give details on separate sheet.
7.1 | Remove all rubbish from work area and dispose of as per site instructions. |  | Pass
7.2 | Ensure all plastic removed from panels and free from defects
7.3 | All unused materials moved to next work area or returned to ground level |  | Pass
Notes:
8 | Completion
8.1 | Confirm work area clean, tidy and all quality assurance issues resolved in this area. Note: photo area |  | Pass