## Table 1
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  | KEY |  | Date | Approved | Date
Perform (P)
ITP 1 - SITE ESTABLISHMENT |  | 7050 - DONALD ROAD CATCHMENT - WASTEWATER PIPELINE |  |  |  | Review (R)
Witness (W)
Hold (H)
TASK | SPECIFICATION REFERENCE | ACTIVITY/TASK | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | FNDC | COMMENTS
ESTABLISHMENT
Pre-Start/Site Establishment | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Visual inspection of site establishment. | FNDC | Prior to commencing works on site. | Acceptance by Engineer's Representative. | H | H
Site Clearance - Inspection of Defined Limits and Vegetation Removal | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Visual inspection of defined limits and vegetation removal. | FNDC |  | Acceptance by Engineer's Representative. | H | H
Survey Setout | Donald Road Catchment - Wastewater Pipeline Specification, page 19 | Set out the work to conform with the drawings. | UCCL | Prior to commencing each stage of work. | Acceptance by Engineer's Representative. | H | H
Service Location | Project Specification, page 24, clause 1.16 | Locate and protect existing services. Arrange with external network utility operators as required. | UCCL | Prior to commencing each stage of work. | Record of services location. Photos. | P
Aggregate | FNDC Engineering Standards 2023, Page 121, Clause 3.3 | Aggregate testing to comply with FNDC Engineering Standards. | FNDC | Test certificates to be provided to Engineer for approval prior to using aggregate on site. | Acceptance by Engineer's Representative. Material test certificates. | H | H