## Table 1
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  | KEY |  | Date | Approved | Date
Perform (P)
ITP 3 - SP528 TO SP529 (BRIDGE CROSSING) |  | 7050 - DONALD ROAD CATCHMENT - WASTEWATER PIPELINE |  |  |  | Review (R)
Witness (W)
Hold (H)
TASK | SPECIFICATION REFERENCE | ACTIVITY/TASK | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | FNDC | COMMENTS
BRIDGE CROSSING
Materials Quality | FNDC Approved Material List | Visual check for approved materials, quality and condition. | UCCL | On arrival to site, prior to using materials. | Delivery dockets, photos. | W | R
PE Butt Welding | FNDC Engineering Standards 2023, Page 237, Clause 5.3.5.3 | Butt welds completed successfully. Visual check. | UCCL | On completion of each butt weld. | UCCL butt welding checklist completed. Data log for welds recorded. | P | R
Pipe Brackets | Donald Road Catchment - Wastewater Pipeline Drawing 0019-004-0WW-C-0008-T1 | Visual inspection to confirm brackets are fabricated and installed as per approved design. | UCCL | On completion of the bridge crossing installation. | Photos. | P | R
Bridge Crossing - Pipeline | Donald Road Catchment - Wastewater Pipeline Drawings | Pipeline installed to correct invert levels and grade. | UCCL | On completion of installation of pipeline. | As-builts drawings. Completed pipeline installation checklist, photos. | P | R