## Table 1
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  | KEY |  | Date | Approved | Date
Perform (P)
ITP 6 - TANK AND WET WELL INSTALLATION |  | 7050 - DONALD ROAD CATCHMENT - WASTEWATER PIPELINE |  |  |  | Review (R)
Witness (W)
Hold (H)
TASK | SPECIFICATION REFERENCE | ACTIVITY/TASK | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | FNDC | COMMENTS
WASTEWATER TANK
Aggregate | As per Tank Design. | Aggregate certificates to comply with tank design. | UCCL | Prior to using as hardfill/backfill. | Approval by tank designer. Acceptance by Engineer's Representative. Material certificates. | H | H
Excavation to Top of Sheetpiles |  | Visual check of excavation, levels, position. | UCCL | On completion of excavation. | Photos. | P | W
Sheetpile Installation |  | Sheetpiles installed as per temporary works design. As-built taken of sheet- piles to use for periodic checks throughout construction. | UCCL | On completion of sheet piling, prior to excavtion. | Photos. | P | W
Excavation and Subgrade inside Sheetpiles | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control. | FNDC | On completion of excavation, prior to placing hardfill. | Acceptance by Engeineer's Representative. | H | H
Hardfill Layer | As per Tank Design. | Visual check of hardfill layer. Hardfill layer meets specification. | UCCL |  | Confirmation from tank design Engineer. Photos. | P | W
Deadman Beams | As per Tank Design. | Deadman beams placed as per specification. | UCCL | On completion of installation of deadman beams, prior to backfilling. | As-built drawings. Photos. | P | W
Tank Installation | As per Tank Design. | Tank installed as per specification. | UCCL | On completion of installation of tank, prior to backfilling. | As-built drawings. Photos. | P | W
Tank Backfill | As per Tank Design. | Tank backfill as per specification. | UCCL | On completion of backfill. | Record of 'Vertical Diamter Measurements'. Photos. | P | W
WET WELL INSTALLATION
Pumps and Mechanical Equipment | Donald Road Catchment - Wastewater Pipeline Specification, page 19. | Engineer to approve specification prior to contractor placing supplier order. | FNDC | Prior to ordering pumps and mechanical equipment. | Acceptance by Engineer's Representative. Specifications for pumps and mechanical equipment. | R | R
Excavation and Subgrade inside Sheetpiles | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control. | FNDC | On completion of excavation, prior to placing hardfill. | Acceptance by Engeineer's Representative. | H | H
Pumps and Mechanical Equipment | Donald Road Catchment - Wastewater Pipeline Specification, page 19. | Engineer to review certification and inspect installation. | FNDC | On completion of installation of pumps and mechanical equipment. | Acceptance by Engineer's Representative. | H | H
Hydrostatic Testing | Donald Road Catchment - Wastewater Pipeline Specification, page 19 | Testing done by manufacturer/supplier. Certificate to be provided with tank. | FNDC | On acceptance of tank on site. | Acceptance by Engineer's Representative. Supplier documentation. | H | H
Testing of Pumps | Donald Road Catchment - Wastewater Pipeline Specification, page 19 | Witness draw-down testing of pumps. | FNDC | During commissioning of pumps. | Acceptance by Engineer's Representative. Commissioning checklist. | H | H
Electrical and SCADA | Donald Road Catchment - Wastewater Pipeline Specification, page 19 | Review switchboard test certification and inspect the installation. | FNDC | On completion of installation of the wet well. | Acceptance by Engineer's Representative. | H | H