## Table 1
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  | KEY |  | Date | Approved | Date
Perform (P)
ITP 7 - PAVEMENTS |  | 7050 - DONALD ROAD CATCHMENT - WASTEWATER PIPELINE |  |  |  | Review (R)
Witness (W)
Hold (H)
TASK | SPECIFICATION REFERENCE | TEST/TASK REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | FNDC | COMMENTS
PAVEMENT
Aggregate | FNDC Engineering Standards 2023, Page 121, Clause 3.3 | Aggregate testing to comply with FNDC Engineering Standards. | FNDC | Test certificates to be provided to Engineer for approval prior to using aggregate on site. | Acceptance by Engineer's Representative. Material test certificates. | H | H
Compaction - Reinstate Pavement Layers | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31. | FNDC | On completion of compacted pavement layers. | Acceptance by Enginner's Representative. Compaction records. Photos. | H | H
Road Re-Surfacing | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Pre-seal inspection. | FNDC | Prior to final road resurfacing. | Acceptance by Engineer's Representative. Supplier documentation. Photos. | H | H
Kerb and Channel/Footpaths | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Pre-pour inspection, inspect foundations. | FNDC | Prior to placing concrete. | Acceptance by Engineer's Represetative. Photos. | H | H