## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Site Establishment | itp |  |  |  |  | ITP 1 - Site Establishment
section | ESTABLISHMENT
checkpoint | Pre-Start/Site Establishment
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Visual inspection of site establishment.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing works on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Site Clearance - Inspection of Defined Limits and Vegetation Removal
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Visual inspection of defined limits and vegetation removal.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Survey Setout
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19
label | ACTIVITY/TASK - Set out the work to conform with the drawings.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing each stage of work.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Service Location
label | SPECIFICATION REFERENCE - Project Specification, page 24, clause 1.16
label | ACTIVITY/TASK - Locate and protect existing services. Arrange with external network utility operators as required.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing each stage of work.
label | ACCEPTANCE CRITERIA - Record of services location. Photos.
label | UCCL - P
label | FNDC -
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3
label | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checklist | SP529 to SP567 (Manholes and Pipeline - Trenched) | itp |  |  |  |  | ITP 2 - SP529 to SP567 (Manholes and Pipeline - Trenched)
section | MANHOLE/PIPELINE INSTALLATION (TRENCHED)
checkpoint | Manhole Excavation and Bedding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Visual check of excavation. Subgrade meets specification. Hardfill layer constructed as per project drawings.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to installing each manhole.
label | ACCEPTANCE CRITERIA - Subgrade meets minimum CBR of 5 (1.5 blows/50mm). Miniumum 150mm layer of GAP65, minimum CIV of 25.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Materials Quality
label | SPECIFICATION REFERENCE - FNDC Approved Material List
label | ACTIVITY/TASK - Visual check for approved materials, quality and condition.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On arrival to site, prior to using materials.
label | ACCEPTANCE CRITERIA - Delivery dockets, photos.
label | UCCL - W
label | FNDC - R
checkpoint | Manhole Installation
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Manhole installed in correct position and to correct level as per Project Drawings and FNDC EES.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of each manhole.
label | ACCEPTANCE CRITERIA - Completed manhole installation checklist, photos.
label | UCCL - P
label | FNDC - R
checkpoint | Pipeline Excavation and Bedding
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19. FNDC Engineering Standards 2023, Sheets 31-37
label | ACTIVITY/TASK - Visual check of excavation. Lower bedding layer constructed as per project drawings.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to laying pipe.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Pipeline Installation
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Pipeline installed to correct invert levels and grade.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each pipeline (manhole-to-mahole) prior to backfilling.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. As-builts drawings. Completed pipeline installation checklist, photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Testing of Manholes and Pipelines
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Engineer's Representative to witness testing of manholes and pipelines.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During testing of manholes and pipelines.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Testing checklists.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Sewer Connections (Household)
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 37
label | ACTIVITY/TASK - Visual check of connection.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each connection.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - R
checkpoint | Sewer Connection (to Existing Wastewater System)
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Inspection prior to connection into exisitng wastewater system.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to connecting to existing wastewater system.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checklist | SP528 to SP529 (Bridge Crossing) | itp |  |  |  |  | ITP 3 - SP528 to SP529 (Bridge Crossing)
section | BRIDGE CROSSING
checkpoint | Materials Quality
label | SPECIFICATION REFERENCE - FNDC Approved Material List
label | ACTIVITY/TASK - Visual check for approved materials, quality and condition.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On arrival to site, prior to using materials.
label | ACCEPTANCE CRITERIA - Delivery dockets, photos.
label | UCCL - W
label | FNDC - R
checkpoint | PE Butt Welding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 237, Clause 5.3.5.3
label | ACTIVITY/TASK - Butt welds completed successfully. Visual check.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each butt weld.
label | ACCEPTANCE CRITERIA - UCCL butt welding checklist completed. Data log for welds recorded.
label | UCCL - P
label | FNDC - R
checkpoint | Pipe Brackets
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Drawing 0019-004-0WW-C-0008-T1
label | ACTIVITY/TASK - Visual inspection to confirm brackets are fabricated and installed as per approved design.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of the bridge crossing installation.
label | ACCEPTANCE CRITERIA - Photos.
label | UCCL - P
label | FNDC - R
checkpoint | Bridge Crossing - Pipeline
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Drawings
label | ACTIVITY/TASK - Pipeline installed to correct invert levels and grade.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of pipeline.
label | ACCEPTANCE CRITERIA - As-builts drawings. Completed pipeline installation checklist, photos.
label | UCCL - P
label | FNDC - R
checklist | SP204 to SP528 (Manholes and Pipeline - Trenched) | itp |  |  |  |  | ITP 4 - SP204 to SP528 (Manholes and Pipeline - Trenched)
section | MANHOLE/PIPELINE INSTALLATION (TRENCHED)
checkpoint | Manhole Excavation and Bedding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Visual check of excavation. Subgrade meets specification. Hardfill layer constructed as per project drawings.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to installing each manhole.
label | ACCEPTANCE CRITERIA - Subgrade meets minimum CBR of 5 (1.5 blows/50mm). Miniumum 150mm layer of GAP65, minimum CIV of 25.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Materials Quality
label | SPECIFICATION REFERENCE - FNDC Approved Material List
label | ACTIVITY/TASK - Visual check for approved materials, quality and condition.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On arrival to site, prior to using materials.
label | ACCEPTANCE CRITERIA - Delivery dockets, photos.
label | UCCL - W
label | FNDC - R
checkpoint | Manhole Installation
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Manhole installed in correct position and to correct level as per Project Drawings and FNDC EES.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of each manhole.
label | ACCEPTANCE CRITERIA - Completed manhole installation checklist, photos.
label | UCCL - P
label | FNDC - R
checkpoint | Pipeline Excavation and Bedding
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19. FNDC Engineering Standards 2023, Sheets 31-37
label | ACTIVITY/TASK - Visual check of excavation. Lower bedding layer constructed as per project drawings.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to laying pipe.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Pipeline Installation
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Pipeline installed to correct invert levels and grade.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each pipeline (manhole-to-mahole) prior to backfilling.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. As-builts drawings. Completed pipeline installation checklist, photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Testing of Manholes and Pipelines
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Engineer's Representative to witness testing of manholes and pipelines.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During testing of manholes and pipelines.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Testing checklists.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Sewer Connections (Household)
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 37
label | ACTIVITY/TASK - Visual check of connection.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each connection.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - R
checkpoint | Sewer Connection (to Existing Wastewater System)
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Inspection prior to connection into exisitng wastewater system.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to connecting to existing wastewater system.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checklist | SP204-SP533 (Thrusted) | itp |  |  |  |  | ITP 5 - SP204-SP533 (Thrusted)
section | MANHOLE/PIPELINE INSTALLATION (THRUSTED)
checkpoint | Manhole Excavation and Bedding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Visual check of excavation. Subgrade meets specification. Hardfill layer constructed as per project drawings.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Subgrade meets minimum CBR of 5 (1.5 blows/50mm). Minimum 150mm layer of GAP65, minimum CIV of 25.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Materials Quality
label | SPECIFICATION REFERENCE - FNDC Approved Material List
label | ACTIVITY/TASK - Visual check for approved materials, quality and condition.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On arrival to site, prior to using materials.
label | ACCEPTANCE CRITERIA - Delivery dockets, photos.
label | UCCL - W
label | FNDC - R
checkpoint | Manhole Installation
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Manhole installed in correct position and to correct level as per Project Drawings and FNDC EES.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of each manhole.
label | ACCEPTANCE CRITERIA - Completed manhole installation checklist, photos.
label | UCCL - P
label | FNDC - W
checkpoint | PE Butt Welding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 237, Clause 5.3.5.3
label | ACTIVITY/TASK - Butt welds completed successfully. Visual check.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each butt weld.
label | ACCEPTANCE CRITERIA - UCCL butt welding checklist completed. Data log for welds recorded.
label | UCCL - P
label | FNDC - R
checkpoint | PE Electrofusion Welding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 237, Clause 5.3.5.3
label | ACTIVITY/TASK - EF welds completed successfully. Visual check.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each EF weld.
label | ACCEPTANCE CRITERIA - UCCL EF weld checklist completed. Data log for welds recorded.
label | UCCL - P
label | FNDC - R
checkpoint | PE Thrusted Pipeline Installation
label | SPECIFICATION REFERENCE -
label | ACTIVITY/TASK - Pipeline installed to correct invert levels and grade.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each length of pipe installed (i.e. manhole- to-manhole).
label | ACCEPTANCE CRITERIA - As-builts drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Testing of Manholes and Pipelines
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Engineer's Representative to witness testing of manholes and pipelines.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During testing of manholes and pipelines.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Testing checklists.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Sewer Connections (Household)
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 37
label | ACTIVITY/TASK - Visual check of connection.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each connection.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Sewer Connection (to Existing Wastewater System)
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Inspection prior to connection into exisitng wastewater system.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to connecting to existing wastewater system.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checklist | Tank and Wet Well | itp |  |  |  |  | ITP 6 - Tank and Wet Well
section | WASTEWATER TANK
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Aggregate certificates to comply with tank design.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to using as hardfill/backfill.
label | ACCEPTANCE CRITERIA - Approval by tank designer. Acceptance by Engineer's Representative. Material certificates.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Excavation to Top of Sheetpiles
label | SPECIFICATION REFERENCE -
label | ACTIVITY/TASK - Visual check of excavation, levels, position.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation.
label | ACCEPTANCE CRITERIA - Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Sheetpile Installation
label | SPECIFICATION REFERENCE -
label | ACTIVITY/TASK - Sheetpiles installed as per temporary works design. As-built taken of sheet- piles to use for periodic checks throughout construction.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of sheet piling, prior to excavtion.
label | ACCEPTANCE CRITERIA - Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Excavation and Subgrade inside Sheetpiles
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation, prior to placing hardfill.
label | ACCEPTANCE CRITERIA - Acceptance by Engeineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Hardfill Layer
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Visual check of hardfill layer. Hardfill layer meets specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Confirmation from tank design Engineer. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Deadman Beams
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Deadman beams placed as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of deadman beams, prior to backfilling.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Tank Installation
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Tank installed as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of tank, prior to backfilling.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Tank Backfill
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Tank backfill as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of backfill.
label | ACCEPTANCE CRITERIA - Record of 'Vertical Diamter Measurements'. Photos.
label | UCCL - P
label | FNDC - W
section | WET WELL INSTALLATION
checkpoint | Pumps and Mechanical Equipment
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Engineer to approve specification prior to contractor placing supplier order.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to ordering pumps and mechanical equipment.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Specifications for pumps and mechanical equipment.
label | UCCL - R
label | FNDC - R
checkpoint | Excavation and Subgrade inside Sheetpiles
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation, prior to placing hardfill.
label | ACCEPTANCE CRITERIA - Acceptance by Engeineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Pumps and Mechanical Equipment
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19.
label | ACTIVITY/TASK - Engineer to review certification and inspect installation.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of pumps and mechanical equipment.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Hydrostatic Testing
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19
label | ACTIVITY/TASK - Testing done by manufacturer/supplier. Certificate to be provided with tank.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On acceptance of tank on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Testing of Pumps
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19
label | ACTIVITY/TASK - Witness draw-down testing of pumps.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During commissioning of pumps.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Commissioning checklist.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Electrical and SCADA
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 19
label | ACTIVITY/TASK - Review switchboard test certification and inspect the installation.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of the wet well.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checklist | Pavements | itp |  |  |  |  | ITP 7 - Pavements
section | PAVEMENT
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3
label | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Compaction - Reinstate Pavement Layers
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of compacted pavement layers.
label | ACCEPTANCE CRITERIA - Acceptance by Enginner's Representative. Compaction records. Photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Road Re-Surfacing
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Pre-seal inspection.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to final road resurfacing.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation. Photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT
checkpoint | Kerb and Channel/Footpaths
label | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
label | ACTIVITY/TASK - Pre-pour inspection, inspect foundations.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to placing concrete.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Represetative. Photos.
label | UCCL - H
label | FNDC - H
holdpoint | HOLD POINT