## Sheet1
1 | Subgrade (Existing Brown Rock Surface) | Civil Works Specification Section 2, Clause 14.1 | Proof Roll Witnessed by Principal's Representative. | UCCL/MEL | Prior to commencing with the AP65 subbase layer. | Acceptance of subgrade by Principal's Representative. | H | H | 1 - Subgrade (Existing Brown Rock Surface) | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.1 | ACTIVITY/TASK - Proof Roll Witnessed by Principal's Representative. | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Prior to commencing with the AP65 subbase layer. | ACCEPTANCE CRITERIA - Acceptance of subgrade by Principal's Representative. | UCCL - H | CLIENT - H | 1 - Subgrade (Existing Brown Rock Surface)
2 | Subbase Course Material Testing | Civil Works Specification Section 2, Clause 14.4.2 | Material Test Certificates | UCCL/MEL | Prior to placing AP65 subbase layer on site. | Material meets specification. Material acceptance by Principal's Representative. | S | A | 2 - Subbase Course Material Testing | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.4.2 | ACTIVITY/TASK - Material Test Certificates | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Prior to placing AP65 subbase layer on site. | ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative. | UCCL - S | CLIENT - A | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.1
3 | Subbase Compaction (Under Containers) | MELNZ-CI-000133 | Clegg Testing - Minimum Clegg Impact Value (CIV) of 25. | UCCL | Prior to placing Fibre Concrete under containers. Minimum 2 tests under each container. | Minimum CIV 25 achieved. Acceptance by Principal's Representative. | W | W | 3 - Subbase Compaction (Under Containers) | SPECIFICATION REFERENCE - MELNZ-CI-000133 | ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25. | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - Prior to placing Fibre Concrete under containers. Minimum 2 tests under each container. | ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative. | UCCL - W | CLIENT - W | ACTIVITY/TASK - Proof Roll Witnessed by Principal's Representative.
4 | Subbase Compaction (Inner Zone Between Containers) | MELNZ-CI-000133 | Clegg Testing - Minimum Clegg Impact Value (CIV) of 25. | UCCL | Prior to placing Basecourse layer. | Minimum CIV 25 achieved. Acceptance by Principal's Representative. | W | W | 4 - Subbase Compaction (Inner Zone Between Containers) | SPECIFICATION REFERENCE - MELNZ-CI-000133 | ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25. | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - Prior to placing Basecourse layer. | ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative. | UCCL - W | CLIENT - W | INSPECTION BY - UCCL/MEL
5 | Subbase Compaction (Site Roads Outside of PCS's and Containers) | Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 7.6 | NDM Testing | UCCL/MEL | Minimum 5 No. NDM Tests per area. Compaction to achieve average > 95% MDD with minimum value > 92%. | Compaction achieves average > 95% MDD achieved with minimum value > 92%. | H | H | 5 - Subbase Compaction (Site Roads Outside of PCS's and Containers) | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 7.6 | ACTIVITY/TASK - NDM Testing | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 95% MDD with minimum value > 92%. | ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%. | UCCL - H | CLIENT - H | TASK TIMING OR TASK FREQUENCY - Prior to commencing with the AP65 subbase layer.
6 | Subbase Tolerances | Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1 | Strings. Survey setout/as-builts | UCCL | On completion of Subbase layer prior to placing Basecourse layer. | Line and level within tolerances. | S | A | 6 - Subbase Tolerances | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1 | ACTIVITY/TASK - Strings. Survey setout/as-builts | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of Subbase layer prior to placing Basecourse layer. | ACCEPTANCE CRITERIA - Line and level within tolerances. | UCCL - S | CLIENT - A | ACCEPTANCE CRITERIA - Acceptance of subgrade by Principal's Representative.
7 | Kerb and Channel |  | Kerb and channel installation | UCCL | On completion of kerb and channel installation. | Kerb and channel meets specification. | W | W | 7 - Kerb and Channel | SPECIFICATION REFERENCE - | ACTIVITY/TASK - Kerb and channel installation | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of kerb and channel installation. | ACCEPTANCE CRITERIA - Kerb and channel meets specification. | UCCL - W | CLIENT - W | UCCL - H
8 | Basecourse Material Testing | Civil Works Specification Section 2 Clause 14.5. | Material Test Certificates | UCCL/MEL | Prior to placing AP40 Basecourse layer on site. | Material meets specification. Material acceptance by Principal's Representative. | S | A | 8 - Basecourse Material Testing | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5. | ACTIVITY/TASK - Material Test Certificates | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Prior to placing AP40 Basecourse layer on site. | ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative. | UCCL - S | CLIENT - A | CLIENT - H
9 | Basecourse Compaction Compaction (Inner Container Zones) |  | NDM Testing | UCCL | NDM Testnig each area. Compaction to achieve average > 95% MDD with minimum value > 92%. | Compaction achieves average > 95% MDD achieved with minimum value > 92%. | W | W | 9 - Basecourse Compaction Compaction (Inner Container Zones) | SPECIFICATION REFERENCE - | ACTIVITY/TASK - NDM Testing | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - NDM Testnig each area. Compaction to achieve average > 95% MDD with minimum value > 92%. | ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%. | UCCL - W | CLIENT - W | 2 - Subbase Course Material Testing
10 | Basecourse Compaction (Site Roads Outside of PCS's and Containers) | Civil Works Specification Section 2 Clause 14.5. TNZ B/02 Clause 7.6. | NDM Testing | UCCL/MEL | Minimum 5 No. NDM Tests per area. Compaction to achieve average > 98% MDD with minimum value > 95%. | Compaction achieves average > 98% MDD achieved with minimum value > 95%. | H | H | 10 - Basecourse Compaction (Site Roads Outside of PCS's and Containers) | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5. TNZ B/02 Clause 7.6. | ACTIVITY/TASK - NDM Testing | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 98% MDD with minimum value > 95%. | ACCEPTANCE CRITERIA - Compaction achieves average > 98% MDD achieved with minimum value > 95%. | UCCL - H | CLIENT - H | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.4.2
11 | Basecourse Tolerances | Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1. | Strings. Survey setout/as-builts. | UCCL | On completion of Basecourse layer prior to placing Basecourse layer. | Line and level within tolerances. | W | W | 11 - Basecourse Tolerances | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1. | ACTIVITY/TASK - Strings. Survey setout/as-builts. | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of Basecourse layer prior to placing Basecourse layer. | ACCEPTANCE CRITERIA - Line and level within tolerances. | UCCL - W | CLIENT - W | ACTIVITY/TASK - Material Test Certificates
12 | AC Material Specification |  | Specification as agreed between Principal and Contractor. | UCCL/MEL | Prior to using the material on site | Specification as agreed between Principal and Contractor prior to works commencing. | H | H | 12 - AC Material Specification | SPECIFICATION REFERENCE - | ACTIVITY/TASK - Specification as agreed between Principal and Contractor. | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - Prior to using the material on site | ACCEPTANCE CRITERIA - Specification as agreed between Principal and Contractor prior to works commencing. | UCCL - H | CLIENT - H | INSPECTION BY - UCCL/MEL
13 | AC Pavement Testing |  | Testing as agreed between Principal and Contractor. | UCCL/MEL | On completion of AC pavement layer. | Testing as agreed between Principal and Contractor prior to works commencing. | H | H | 13 - AC Pavement Testing | SPECIFICATION REFERENCE - | ACTIVITY/TASK - Testing as agreed between Principal and Contractor. | INSPECTION BY - UCCL/MEL | TASK TIMING OR TASK FREQUENCY - On completion of AC pavement layer. | ACCEPTANCE CRITERIA - Testing as agreed between Principal and Contractor prior to works commencing. | UCCL - H | CLIENT - H | TASK TIMING OR TASK FREQUENCY - Prior to placing AP65 subbase layer on site.
ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative.
UCCL - S
CLIENT - A
3 - Subbase Compaction (Under Containers)
SPECIFICATION REFERENCE - MELNZ-CI-000133
ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25.
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - Prior to placing Fibre Concrete under containers. Minimum 2 tests under each container.
ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative.
UCCL - W
CLIENT - W
4 - Subbase Compaction (Inner Zone Between Containers)
SPECIFICATION REFERENCE - MELNZ-CI-000133
ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25.
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - Prior to placing Basecourse layer.
ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative.
UCCL - W
CLIENT - W
5 - Subbase Compaction (Site Roads Outside of PCS's and Containers)
SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 7.6
ACTIVITY/TASK - NDM Testing
INSPECTION BY - UCCL/MEL
TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 95% MDD with minimum value > 92%.
ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%.
UCCL - H
CLIENT - H
6 - Subbase Tolerances
SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1
ACTIVITY/TASK - Strings. Survey setout/as-builts
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of Subbase layer prior to placing Basecourse layer.
ACCEPTANCE CRITERIA - Line and level within tolerances.
UCCL - S
CLIENT - A
7 - Kerb and Channel
SPECIFICATION REFERENCE -
ACTIVITY/TASK - Kerb and channel installation
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of kerb and channel installation.
ACCEPTANCE CRITERIA - Kerb and channel meets specification.
UCCL - W
CLIENT - W
8 - Basecourse Material Testing
SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5.
ACTIVITY/TASK - Material Test Certificates
INSPECTION BY - UCCL/MEL
TASK TIMING OR TASK FREQUENCY - Prior to placing AP40 Basecourse layer on site.
ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative.
UCCL - S
CLIENT - A
9 - Basecourse Compaction Compaction (Inner Container Zones)
SPECIFICATION REFERENCE -
ACTIVITY/TASK - NDM Testing
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - NDM Testnig each area. Compaction to achieve average > 95% MDD with minimum value > 92%.
ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%.
UCCL - W
CLIENT - W
10 - Basecourse Compaction (Site Roads Outside of PCS's and Containers)
SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5. TNZ B/02 Clause 7.6.
ACTIVITY/TASK - NDM Testing
INSPECTION BY - UCCL/MEL
TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 98% MDD with minimum value > 95%.
ACCEPTANCE CRITERIA - Compaction achieves average > 98% MDD achieved with minimum value > 95%.
UCCL - H
CLIENT - H
11 - Basecourse Tolerances
SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1.
ACTIVITY/TASK - Strings. Survey setout/as-builts.
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of Basecourse layer prior to placing Basecourse layer.
ACCEPTANCE CRITERIA - Line and level within tolerances.
UCCL - W
CLIENT - W
12 - AC Material Specification
SPECIFICATION REFERENCE -
ACTIVITY/TASK - Specification as agreed between Principal and Contractor.
INSPECTION BY - UCCL/MEL
TASK TIMING OR TASK FREQUENCY - Prior to using the material on site
ACCEPTANCE CRITERIA - Specification as agreed between Principal and Contractor prior to works commencing.
UCCL - H
CLIENT - H
13 - AC Pavement Testing
SPECIFICATION REFERENCE -
ACTIVITY/TASK - Testing as agreed between Principal and Contractor.
INSPECTION BY - UCCL/MEL
TASK TIMING OR TASK FREQUENCY - On completion of AC pavement layer.
ACCEPTANCE CRITERIA - Testing as agreed between Principal and Contractor prior to works commencing.
UCCL - H
CLIENT - H