## Sheet1
Aggregate | FNDC Engineering Standards 2023, Page 121, Clause 3.3 | Aggregate testing to comply with FNDC Engineering Standards. | FNDC | Test certificates to be provided to Engineer for approval prior to using aggregate on site. | Acceptance by Engineer's Representative. Material test certificates. | H | H | Aggregate | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3 | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards. | INSPECTION BY - FNDC | TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site. | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates. | UCCL - H | FNDC - H | Aggregate
Compaction - Reinstate Pavement Layers | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31. | FNDC | On completion of compacted pavement layers. | Acceptance by Enginner's Representative. Compaction records. Photos. | H | H | Compaction - Reinstate Pavement Layers | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18 | ACTIVITY/TASK - Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31. | INSPECTION BY - FNDC | TASK TIMING OR TASK FREQUENCY - On completion of compacted pavement layers. | ACCEPTANCE CRITERIA - Acceptance by Enginner's Representative. Compaction records. Photos. | UCCL - H | FNDC - H | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3
Road Re-Surfacing | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Pre-seal inspection. | FNDC | Prior to final road resurfacing. | Acceptance by Engineer's Representative. Supplier documentation. Photos. | H | H | Road Re-Surfacing | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18 | ACTIVITY/TASK - Pre-seal inspection. | INSPECTION BY - FNDC | TASK TIMING OR TASK FREQUENCY - Prior to final road resurfacing. | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation. Photos. | UCCL - H | FNDC - H | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards.
Kerb and Channel/Footpaths | Donald Road Catchment - Wastewater Pipeline Specification, page 18 | Pre-pour inspection, inspect foundations. | FNDC | Prior to placing concrete. | Acceptance by Engineer's Represetative. Photos. | H | H | Kerb and Channel/Footpaths | SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18 | ACTIVITY/TASK - Pre-pour inspection, inspect foundations. | INSPECTION BY - FNDC | TASK TIMING OR TASK FREQUENCY - Prior to placing concrete. | ACCEPTANCE CRITERIA - Acceptance by Engineer's Represetative. Photos. | UCCL - H | FNDC - H | INSPECTION BY - FNDC
TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site.
ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates.
UCCL - H
FNDC - H
Compaction - Reinstate Pavement Layers
SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
ACTIVITY/TASK - Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31.
INSPECTION BY - FNDC
TASK TIMING OR TASK FREQUENCY - On completion of compacted pavement layers.
ACCEPTANCE CRITERIA - Acceptance by Enginner's Representative. Compaction records. Photos.
UCCL - H
FNDC - H
Road Re-Surfacing
SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
ACTIVITY/TASK - Pre-seal inspection.
INSPECTION BY - FNDC
TASK TIMING OR TASK FREQUENCY - Prior to final road resurfacing.
ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation. Photos.
UCCL - H
FNDC - H
Kerb and Channel/Footpaths
SPECIFICATION REFERENCE - Donald Road Catchment - Wastewater Pipeline Specification, page 18
ACTIVITY/TASK - Pre-pour inspection, inspect foundations.
INSPECTION BY - FNDC
TASK TIMING OR TASK FREQUENCY - Prior to placing concrete.
ACCEPTANCE CRITERIA - Acceptance by Engineer's Represetative. Photos.
UCCL - H
FNDC - H