## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fix 1 |  |  |  |  | Yes | Fix 1 | 79c92495-fb47-40fc-97c5-defd101dd49b
checkpoint-status |  |  | checkpoint | Sanitary noggins installed
checkpoint-status |  |  | checkpoint | Cavity slider installed plumb + level + square
checkpoint-status |  |  | checkpoint | Internal door timber studs installed
checkpoint-status |  |  | checkpoint | Final Sign Off
checklist-flat |  |  | checklist | Corridor A checklist |  |  |  |  | Yes | Corridor A checklist | cde59f84-a0d1-47ac-9423-270c8d771c4c
checkpoint-status |  |  | checkpoint | Skirting internally and externally tight
checkpoint-status |  |  | checkpoint | Cupboard doors installed with 3mm quirk
checkpoint-status |  |  | checkpoint | Bottom of cupboard doors installed with 5-10mm gap
checkpoint-status |  |  | checkpoint | Hardware installed and operational
checklist-flat |  |  | checklist | Fix 2 |  |  |  |  | Yes | Fix 2 | f2c157db-edb9-4e71-ab78-bf8960be04a9
checkpoint-status |  |  | checkpoint | Sanitary fixtures installed as per drawings
checkpoint-status |  |  | checkpoint | Skirting installed
boolean | e528eb46-0611-55c4-94a7-0f49b518e3c0 |  | tickbox | Internally and externally tight
boolean | c4df70be-d362-5bc4-81f7-885ace5bdd09 |  | tickbox | Caulking done if required
checkpoint-status |  |  | checkpoint | Cavity slider installed
boolean | a0b1a076-8b4e-5ffa-b069-32bfa3c7a18f |  | tickbox | Door closing into Jamb correctly
boolean | 7ec50cf8-aa4b-5704-97bd-2fe781663634 |  | tickbox | Hardware installed and operational
boolean | f9a440f3-7d53-51ff-93f3-43386dd05e34 |  | tickbox | Rollers adjusted correctly
checkpoint-status |  |  | checkpoint | Split jamb installed
boolean | 91aab41e-06f9-5ac0-b5d0-ee098e2bee7e |  | tickbox | Installed plumb + level + square
boolean | 7d3589d0-67a0-5193-8fe9-2ffbb0cf3934 |  | tickbox | Hardware installed and operational
checkpoint-status |  |  | checkpoint | Entry Door installed
boolean | 33b57dee-9688-5b0c-a671-275a89bda765 |  | tickbox | Installed with 3mm quirk
boolean | 01d68321-6f08-54e7-b9e4-918b2051db9d |  | tickbox | Bottom of door installed with 5 - 10mm gap
boolean | f37d5a05-346f-5276-9c5b-be8f492abce2 |  | tickbox | Hardware installed and operational
checkpoint-status |  |  | checkpoint | Final Sign Off