## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Pre Sheet Sign off | [5 empty] | Pre-Sheet wall Sign-Off
checkpoint | Electrical - Apps Electrical - Pass once below is completed
button | Rough-in Complete | Yes,No,N/A
button | Cutouts Marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | FR GPO boxes installed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Hydraulics - Planet Plumbing - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
button | Access panel / Valve box locations framed as marked | Yes,No,N/A
button | Lagging complete | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Mechanical - DE-ELLIS - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
button | Access panel locations framed as marked | Yes,No,N/A
button | Lagging complete | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Medical Gas - DE-ELLIS -Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Access panel / Valve box locations framed as marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Pneumatic Piping - DE-ELLIS -Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Wet Fire - Contract Fire -Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked (Fire extinguishers) | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Dry Fire - Jaycon -Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Security- Honeywell - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Fire rated boxes installed | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Data - SKS - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Fire rated boxes installed | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Nurse Call - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Fire rated boxes installed | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | AV - SKS - Pass once below is completed
button | Rough-in complete | Yes,No,N/A
button | Pressure boxes installed | Yes,No,N/A
button | Pressure box rough-in sealed | Yes,No,N/A
button | Fire rated boxes installed | Yes,No,N/A
button | Cut outs marked | Yes,No,N/A
button | Noggins installed as marked / TV support | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Joinery - GOSA/Jacaranda -Pass once below is completed
button | Noggins installed as marked | Yes,No,N/A
button | Cut outs framed as marked (mental health) | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Sanitary Hardware - Casello - Pass once below is completed
button | Cut outs framed as marked (mental health) | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Plaster - Expo / Express - Pass once below is completed
button | All rough-in complete | Yes,No,N/A
button | Studs installed @ correct centres (max 600mm) and framing noggins as per wall type | Yes,No,N/A
button | Wall cavity clean / no waste / vacuumed | Yes,No,N/A
button | No screws in head track | Yes,No,N/A
button | Secondary steel (walls) as marked - (drug safe / drop down rails / gun safes etc) | Yes,No,N/A
button | Door frames installed and filled when in fire rated wall | Yes,No,N/A
button | Special door openings framing and noggins for autoclosers etc | Yes,No,N/A
button | Insulation installed | Yes,No,N/A
button | Noggins installed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | MPX FINAL SIGN-OFF
button | All services signed off | Yes,No,N/A
button | Wall cavity clean and free of any rubbish / dust | Yes,No,N/A
button | Photos taken of all walls prior to sheeting | Yes,No,N/A
holdpoint | MPX sign-off
checklist-flat | Pre Grid Sign off | [5 empty] | Pre grid install Ceilings
checkpoint | Electrical - Apps Electrical - Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | Access Panel / ceiling set out location marked | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Hydraulics - Planet Plumbing - Pass once below is completed
button | Rough in complete including lagging to drains and pipes | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Access Panel locations marked and isolation valves accessible | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Mechanical - DE-ELLIS - Pass once below is completed
button | Rough in complete including lagging to drains and pipes | Yes,No,N/A
button | All penetrations through fire rated / smoke /pressurized walls are all sealed | Yes,No,N/A
button | Fire dampers installed correctly and sealed and labeled | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Access Panel / ceiling set out location marked | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Medical Gas - DE-ELLIS -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Pneumatic Piping - DE-ELLIS -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Wet Fire - Contract Fire -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Ceiling set out marked | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | In ceiling sprinklers / detectors have been fitted off / spray pattern unobstructed | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Dry Fire - Jaycon -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Ceiling set out marked | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Security- Honeywell -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Data - SKS -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Service separation to power verified | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Nurse Call - APPS Electrical-Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | AV - SKS -Pass once below is completed
button | Rough in complete | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | TV support poles installed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Patient lifters- -Pass once below is completed
button | Patient lifter track / hanger system installed | Yes,No,N/A
button | Patient lifter track / hanger system load test completed and passed | Yes,No,N/A
button | Power supply correctly located | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Equipment pendants - Device technologies -Pass once below is completed
button | Pendant supports installed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Plaster - Express / Expo - Pass once below is completed
button | All penetrations through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | All walls caulked to slab and soffitt / joints and screws stopped | Yes,No,N/A
button | No screws in top track | Yes,No,N/A
button | Screws installed to correct centers as per specification to walls | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | MPX FINAL SIGN-OFF
button | All subcontractors signed off | Yes,No,N/A
button | Building Surveyor Fire Wall inspection complete | Yes,No,N/A
button | No Fixings to Head Track or Between Stud & Top Track | Yes,No,N/A
button | Photos taken of all walls prior to sheeting | Yes,No,N/A
holdpoint | MPX sign-off
checklist-flat | Pre Ceiling Sign off | [5 empty] | Pre sheet install Ceilings
checkpoint | Electrical - Apps Electrical - Pass once below is completed
button | Ceiling fitting / rough-in complete and correctly located | Yes,No,N/A
button | Access Panel Openings Constructed and equipment is accessible | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Ceiling noggins installed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Hydraulics - Planet Plumbing - Pass once below is completed
button | All pipes connected | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Access Panel openings constructed and isolation valves accessible | Yes,No,N/A
button | Lagging complete to pipes and drains | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Mechanical - DE-ELLIS - Pass once below is completed
button | In ceiling fit off complete | Yes,No,N/A
button | All penetrations through fire rated / smoke /pressurized walls are all sealed | Yes,No,N/A
button | Fire dampers installed correctly and sealed and labeled | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Access Panel Openings Constructed and equipment is accessible for servicing | Yes,No,N/A
button | Lagging complete to pipes | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Medical Gas - DE-ELLIS -Pass once below is completed
button | In ceiling fit off complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Pneumatic Piping - DE-ELLIS -Pass once below is completed
button | In ceiling fit off complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Wet Fire - Contract Fire -Pass once below is completed
button | In ceiling sprinklers / detectors have been fitted off / spray pattern unobstructed | Yes,No,N/A
button | Fit off to ceiling grid complete | Yes,No,N/A
button | All pipes through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
button | Pressure test completed and passed | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Dry Fire - Jaycon -Pass once below is completed
button | In ceiling rough in complete and cables correctly located | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Security- Honeywell -Pass once below is completed
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Data - SKS -Pass once below is completed
button | In ceiling rough in complete and cables correctly located | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Nurse Call -Pass once below is completed
button | In ceiling rough in complete and cables correctly located | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | AV - SKS -Pass once below is completed
button | In ceiling rough in complete and cables correctly located | Yes,No,N/A
button | All cables through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | TV support poles / noggins installed | Yes,No,N/A
button | Fire rated penetrations have stickers, and photos taken | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Patient lifters- -Pass once below is completed
button | Patient lifter track / hanger system installed | Yes,No,N/A
button | Patient lifter track / hanger system load test completed and passed | Yes,No,N/A
button | Power supply correctly located | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Equipment pendants - Device Technologies -Pass once below is completed
button | Pendant supports clear of ceiling grid and level correct | Yes,No,N/A
button | Pendant services rough in complete (Power and Medical gas) | Yes,No,N/A
button | Framed opening in ceiling installed as per detail | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | Plaster - Express / Expo - Pass once below is completed
button | All penetrations through fire rated / smoke / pressurized walls are all sealed | Yes,No,N/A
button | All walls caulked to slab and soffitt / joints and screws stopped | Yes,No,N/A
button | Ceiling grid installed as per design | Yes,No,N/A
button | Thermal and acoustic insulation installed | Yes,No,N/A
button | Ceiling Grid frame is clear from Ceiling Services | Yes,No,N/A
button | Access Panel Openings Constructed as marked | Yes,No,N/A
holdpoint | Subcontractor presheet works complete (S/C to sign)
checkpoint | MPX FINAL SIGN-OFF
button | All subcontractors signed off | Yes,No,N/A
button | Photos taken of all ceiling system / services prior to sheeting | Yes,No,N/A
holdpoint | MPX sign-off