## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QA - Teal Call Solutions Ltd |  |  |  |  | Yes | QA - Teal Call Solutions Ltd | 031cad63-81d1-4f3d-8355-081998de7bdf
checkpoint-status |  |  | checkpoint | Installation completed
checkpoint-status |  |  | checkpoint | Testing completed
checkpoint-status |  |  | checkpoint | Acoustic treatment completed
holdpoint |  |  | signoff | Sign Off if required
checklist-flat |  |  | checklist | QA - Healthcare Fireproofers Ltd |  |  |  |  | Yes | QA - Healthcare Fireproofers Ltd | 14e9530a-daa6-4b39-80eb-768b3ec18e20
checkpoint-status |  |  | checkpoint | Fire Penetrations sealed
checkpoint-status |  |  | checkpoint | Any other jobs required
holdpoint |  |  | signoff | Sign Off if required
checklist-flat |  |  | checklist | Check List 5 |  |  |  |  | Yes | Check List 5 | 329484ac-42fb-4a93-9b99-ec142dd27381
checkpoint-status |  |  | checkpoint | Inspection & test Plan uploaded
checkpoint-status |  |  | checkpoint | As-Builts
checkpoint-status |  |  | checkpoint | Commissioning Reports
checklist-flat |  |  | checklist | QA - Contract Builders Ltd |  |  |  |  | Yes | QA - Contract Builders Ltd | 35b8aa51-2fc8-4f61-b119-bb933baebe87
checkpoint-status |  |  | checkpoint | Description of job
text | 3ea3038e-b78f-5572-8b9e-d23ac3cfce3e |  | textbox
checkpoint-status |  |  | checkpoint | All jobs completed to specifications
holdpoint |  |  | signoff | Sign Off if required
checklist-sectioned |  |  | checklist | Check List 2 |  |  |  |  | Yes | Check List 2 | 518e8512-1f01-4116-b895-cdc33f51ec3b
checkpoint-group |  |  | section | Pre-wire
checkpoint-status |  |  | checkpoint | Cable through fire box into area. (Attach Photos)
checkpoint-status |  |  | checkpoint | Existing Cable re-used
checkpoint-group |  |  | section | Fit-off
checkpoint-status |  |  | checkpoint | Nurse call installed
checkpoint-status |  |  | checkpoint | Data/TV points
checkpoint-status |  |  | checkpoint | Access control installed.
checkpoint-status |  |  | checkpoint | CCTV Installed
checkpoint-status |  |  | checkpoint | Intercom Installed
checkpoint-group |  |  | section | Testing & Commissioning
checkpoint-status |  |  | checkpoint | Nurse call tested to pagers and Displays
checkpoint-status |  |  | checkpoint | Data points tested
checkpoint-status |  |  | checkpoint | MATV tested
checkpoint-status |  |  | checkpoint | Access control programmed & tested
checkpoint-status |  |  | checkpoint | CCTV Programmed & tested
checkpoint-status |  |  | checkpoint | Intercom Programmed & tested
checklist-flat |  |  | checklist | QA - Rainbow Painters Ltd |  |  |  |  | Yes | QA - Rainbow Painters Ltd | 824541a8-ff23-46e6-84bb-25784af216c4
checkpoint-status |  |  | checkpoint | Area completed
checkpoint-status |  |  | checkpoint | Patching and painting up to specifications
checkpoint-status |  |  | checkpoint | Any other jobs required
holdpoint |  |  | signoff | Sign Off if required
checklist-flat |  |  | checklist | Check List 3 |  |  |  |  | Yes | Check List 3 | cab9cc39-461f-49d8-86e4-d03c4d6f5f70
checkpoint-status |  |  | checkpoint | Speakers Installed
checkpoint-status |  |  | checkpoint | Speakers Tested
checklist-flat |  |  | checklist | Ryman Overarching Checks |  |  |  |  | Yes | Ryman Overarching Checks | cfbbe830-3836-4899-a716-7c18eed009d5
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets Ryman requirements
checkpoint-status |  |  | checkpoint | Finishing completed and meets required standards
checkpoint-status |  |  | checkpoint | Upload any Ryman-related documents
checklist-flat |  |  | checklist | Check List 4 |  |  |  |  | Yes | Check List 4 | dc03069f-4bc4-49e3-a3a4-e6306bfd7cfe
checkpoint-status |  |  | checkpoint | Patch Panels terminated (Attach rear photos of patch panels)
checkpoint-status |  |  | checkpoint | UPS Installed and connected to network
checkpoint-status |  |  | checkpoint | Power Supply's installed and batteries connected.
checkpoint-status |  |  | checkpoint | Nurse call coordinator installed
checkpoint-status |  |  | checkpoint | Cabinet Labelled
checkpoint-status |  |  | checkpoint | Access control cabinet
checklist-sectioned |  |  | checklist | Check List 1 |  |  |  |  | Yes | Check List 1 | e02a7871-344d-48dd-97e5-976e0b72afb9
checkpoint-group |  |  | section | Pre-wire
checkpoint-status |  |  | checkpoint | Cables through fire box at Apartment point of entry. (Attach Photos)
checkpoint-status |  |  | checkpoint | Existing Cable re-used
checkpoint-group |  |  | section | Fit-off
checkpoint-status |  |  | checkpoint | Distribution box (Attach Photos)
checkpoint-status |  |  | checkpoint | Nurse call points
checkpoint-status |  |  | checkpoint | Data/TV points
checkpoint-group |  |  | section | Testing & Commissioning
checkpoint-status |  |  | checkpoint | Nurse call tested to pagers and Displays
checkpoint-status |  |  | checkpoint | Data points tested
checkpoint-status |  |  | checkpoint | MATV tested