## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island | itp |  |  |  |  | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-083-CIV-PSDS-Footpath-Industrial crossover-Traffic island
label | ITP Description: PSDS-Footpath-Industrial crossover-Traffic island
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 083-CIV
label | Revision Number: 0
label | Revision Date: 21/02/2024
label | ITP created by: Abhi Patil
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 304 August 2013
label | 1.2 Non Dependent
label | Reference: VicRoads Section 703 April 2019
label | 1.3 Non Dependent
label | Reference: Council CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 1.4 Non Dependent
label | Reference: AS 1379-2007
label | 1.5 Non Dependent
label | Reference: VicRoads Section 812 July 2016
label | 1.6 Non Dependent
label | Reference: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
section | Preliminaries - Materials
checkpoint | 2.1 Bedding Material Placement & Compaction
label | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 812.04, 703.21
label | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Concrete Mix
label | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.05 (a), 703.07
label | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | Footpaths (Pavement Type 7):
label | – Concrete Strength: 25Mpa
label | – N25 with eMesh (Macro Synthetic) Fibres Applied at 5.6kg/m3
label | – Min 30% SCM
label | Industrial Vehicle Crossings (Pavement Type 8):
label | – Concrete Strength: 25MPa
label | – Min 30% SCM
label | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
label | – Concrete Strength: 25MPa
label | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Reinforcement
label | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.16
label | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
label | Footpaths (Pavement Type 7):
label | – eMESH Fibres Applied at 5.6kg/m3
label | Industrial Vehicle Crossings (Pavement Type 8):
label | – SL82 Mesh (Centrally Placed)
label | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
label | – SL72 Mesh (Centrally Placed)
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Evaporative Retardant
label | REFERENCE: 703.09, 610.17 (f)
label | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.5 Curing Compound
label | REFERENCE: 703.10 (a), 610.23 (d)
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Documents
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.17
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ The Nominated Authority will review and confirm the set out.
label | Attach: Survey Report
label | METHOD: Document Review, Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Lot Map
label | REFERENCE: MRPA Lot Management Plan
label | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
label | Attach: Lot Map
label | METHOD: Document
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Attached Lot Map
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Site Clearing & Grubbing
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | METHOD: Visual
label | FREQUENCY: Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Excavation
label | REFERENCE: 703.20 IFC Drawings
label | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
label | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Bedding Material Placement & Compaction
label | REFERENCE: 703.21 IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
label | Footpath (Pavement Type 7) / Industrial Vehicle Crossing (Pavement Type 8):
label | – 20mm Class 3 Crushed Rock or Crushed Concrete
label | – Bedding shall be 50 mm compacted thickness
label | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4):
label | – Remnant pavement in SGH or minimum 100mm Class 3 Crushed Rock or Crushed Concrete)
label | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | Attach: Bedding Material Delivery Dockets
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Compaction Testing
label | REFERENCE: 703.21, 304.08 (a) & (b), 304.11 (a)
label | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
label | ○ Scale of Surface Level Measurement = Scale C
label | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
label | Attach: Moisture Content Test Results
label | Attach: Mean Value of Density Ratio
label | METHOD: Document Review, Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Formwork Construction & Placement
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.12
label | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Construction Joints & Matching Existing Surfaces
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.24
label | ○ Relevant Council Standard DrawingsRelevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | i. Concrete cutting of a shear-key
label | ii. Surface roughening
label | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | iv. Cutting a groove for sealant
label | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Isolation Joints
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (c)
label | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | ii. at any location marked on the drawings
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Expansion Joints
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (a) (ii) & (b) (i)
label | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | i. on either side of vehicle crossings
label | ii. at junctions with existing footpaths and shared use paths
label | iii. at junctions with bridges
label | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Reinforcement Placement
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.13
label | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | Footpaths (Pavement Type 7):
label | – eMESH (Macro Synthetic) Fibres Applied at 5.6kg/m3
label | Industrial Vehicle Crossings (Pavement Type 8)::
label | – SL82 Mesh (Centrally Placed)
label | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Pre-pour Survey
label | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
label | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork and base layer within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from alignment = ±10mm
label | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | ○ Irregularities in alignment = 5mm in 3m
label | ○ Section dimensions = ±5mm
label | ○ Section dimensions (less than 25mm) = ±3mm
label | ○ Width of pavement = -5mm, +15mm
label | Attach: Survey Report
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Pre-pour Inspection
label | REFERENCE: Section 703.09, Section 703.21 Section 610.17a), b) & c)
label | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Weather Conditions & Evaporation Limits
label | REFERENCE: 703.09, 610.17 (a - f) Table 610.171
label | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | Record: Required information on the Concrete Pour Record.
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.13 Concrete Testing - Sampling Frequencies, Footpath, Industrial Driveway, Traffic Island
label | REFERENCE: 703.11, 610.16 (b) AS 1379-2007 Cluse 6.2
label | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | ○ Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.14 Concrete Testing - Slump
label | REFERENCE: 703.11, 610.16 (c)
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each sample
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.15 Placement & Compaction
label | REFERENCE: 703.08
label | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | Record: Required information on the Concrete Pour Record.
label | Attach: Concrete Pour Record
label | Attach: Concrete Dockets
label | METHOD: Visual
label | FREQUENCY: Each load
label | CATEGORY: SP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
date | Date Completed:
checkpoint | 5.16 Surface Finishes
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.25
label | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.17 Crack-control Joints / Weaken Plane Joints
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
label | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.18 Curing
label | REFERENCE: 703.10
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Crack-control Joints / Weaken Plane Joints
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
label | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | <20°C = within 24 hours of finishing operations
label | ≥20°C - 35°C = within 4 hours of finishing operations
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Protection of Newly Poured Concrete
label | REFERENCE: 703.27
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Stripping Formwork
label | REFERENCE: 703.12 AS3610 Table C2
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | i. 2 days for vertical formwork on external surfaces; and
label | ii. 1 day for vertical forms on permanently hidden surfaces
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Backfilling & Pavement Restoration
label | REFERENCE: 703.29
label | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.5 Surface Inspection - Cracks
label | REFERENCE: 703.3
label | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 Surface Inspection - Surface Finish
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B 703.25, 703.10 (a) AS3610 Clause 3.2
label | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | Class of finish:
label | – Permanently hidden surfaces = Class 4
label | – All other surfaces = Class 3
label | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.7 Compressive Strength Test Results
label | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ○ Relevant Council Drawings 703.11 Table 703.111
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Attach: Compressive Strength Test Results
label | METHOD: Document Review
label | FREQUENCY: Each cylinder
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.8 As-built Survey
label | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from alignment = ±10mm
label | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | ○ Irregularities in alignment = 5mm in 3m
label | ○ Section dimensions = ±5mm
label | ○ Section dimensions (less than 25mm) = ±3mm
label | ○ Width of pavement = -5mm, +15mm
label | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | Attach: Survey As-builts / Survey Report
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP