## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | E3001A - SH05 - SIP-Site 1 |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guardrail & Wire Rope Barriers |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dharminder Singh
Lot No: E3001A |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH 05 300m South to 700m North of Marshalls bridge
Chainage:RP249/4.22 to RP 249/5.130
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Design Check | M | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | OFI or NTD/NTC | Site Engineer
2 | Survey Setout | W | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer
3 | Material Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer | CPS
4 | Material Compliance | M | All materials to be sourced from registered suppliers | Prior to commencement | Document Review | Registered suppliers | Materials register | Site Engineer
5 | Material Compliance | H | Proposed galvanising repair methodology to be approved by Engineer | Prior to commencement | Document Review | Best practice | Approved / Signature | Site Engineer | CPS
6 | Guardrail Installation | M | Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers | On Procurement of installer | Written confirmation | ASHTAS operative and installer course | Attendance Certificate | Site Engineer
7 | Guardrail Installation | W | Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 Guardrail Installation Checksheet | Site Engineer
8 | Guardrail Installation | M | W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
9 | Guardrail Installation | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
10 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM | Prior to trafficking, | Visual inspection | Pass inspection | Confirmation from inspector | Site Engineer | CPS
Final Inspection and Handover
11 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, CPS COR Report, NCR's and RFI's | Site Engineer
12 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: