## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | itp |  |  |  |  | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | 6efdad45-2af0-4f82-86a7-2306bb896d31
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Base of Wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material - consistency though construction
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | Records - Photos
checkpoint | 4 - Material Compliance (Geotextile)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile for rock works - Rolls delivered and delivery dockets gathered. Compliant with Terratex 750k or similar approved
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 5 - Material Compliance (Geotextile)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile for back of excavation - Rolls delivered and delivery dockets gathered. Strength class C, Filtration Class 2
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 6 - Material Compliance (Geogrid)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All rolls of Geogrid are to be checked and left in their protective wrappers until they are required for use
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any defective rolls are NOT to be used in the wall construction - return to the supplier immediately
checkpoint | 7 - Material Compliance (Geogrid)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Dockets
checkpoint | 8 - CTV Culvert
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CTV existing culvert to confirm it should be repaired rather than replaced
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Inspection Video
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Culvert Extension
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm extension connection methodology with CPS Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - submission
label | Records - Subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ground Anchors and proprietary components (plate and lock nuts) - Manufacturer’s test certificate for each batch of anchors. Testing shall be undertaken in an Australian / New Zealand Telarc certified laboratory.
label | ○ The required minimum physical material properties information are as follows: Diameter; Steel area; Ultimate load; Proof load at 0.1%; % of Elongation at yield load; Modulus of elasticity; Relaxation after 1000hr. Refer to specifications and drawings, including proof of coating galv and epoxy.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Manufacturers compliance test certificate with relevant delivery dockets
label | Records - Supplier Certificate, test results and delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout mix - Approval of grout mix design. Include method of batching and mixing and previous test results for pumpable cement grout mixture. Refer to specifications and drawings for grout details.
label | ○ The water-cement ratio shall not be less than w/c = 0.40 and no more than w/c = 0.45. The grout shall not be subject to bleeding in excess of 4% of the initial volume. Admixtures which can control bleed or retard set of the grout shall be used only when approved.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approval of Mix Design
label | Records - Grout mix and test results within subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Anchoring methodology - CPS has reviewed methodology including location, drilling method, grouting procedure, stressing and testing methods and reaction frame details
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approved subcontractor's method statement
label | Records - Subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Material Compliance (Walls)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All blocks that are delivered are to be approved for use and are compliant with the Specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - If patterns are used on walls then ensure that the correct colour blocks are ordered and instruction given to teams
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with project specification
label | Records - CS-4020 Bulk Fill Earthworks Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Fill Construction Material
label | Frequency - Each material used / borrow pit
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Repair and Underpin Box Culvert
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Repair as per drawings and specifications
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification and ecology requirements
label | Records - Photographs
checkpoint | 17 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions. Road seal may need to be cut where it is undermined.
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photographs
checkpoint | 18 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cut inspected by Geotechnical Engineer when conditions/material type change
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 19 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure cuts are staged. The slope should be trimmed in stages to maintain stability rather than cutting entire slope in one hit
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 20 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey Receipt
checkpoint | 21 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test the base of the excavation to ensure it meets Specification.
label | Frequency - Prior to backfilling, as per specification
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala and Shear Vane
label | Conformance Criteria - In accordance with specification
label | Records - Lab test result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 23 - Dewatering
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - works shall comply with the relevant consents and the projects Environmental Compliance Requirements
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Dewater in order for construction requirements
checkpoint | 24 - Undercut in areas deemed unsuitable
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cut to waste as required
label | Conformance Criteria - As required by specification and CPS engineer
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 25 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 26 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 27 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install subsoil drainage as required in accordance with specification
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 28 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Place concrete foundation including grouting starter bars as per specifications/drawings
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Concrete to meet the specifications, collect all delivery dockets
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm with CPS Engineer extent of MSE Wall vs Anchored Section
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Submission Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 30 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Permit to Lift
checkpoint | 31 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - CS-4012 MSE Wall Geogrid Checklist and Photo's
checkpoint | 32 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photographs
checkpoint | 33 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Drainage Blanket as shown on Drawings
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photos
checkpoint | 34 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Place fill material on grid layers as per drawings and compact to MSE Wall specifications and test.
label | Frequency - Every lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - As per specification
label | Records - Lab Reports
checkpoint | 36 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure line and level of front face is as per design
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 37 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install and test sacrificial test anchors, location to be determined with CPS Engineer, testing after 7 days when the Grout strength has reached 30Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 38 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Construct working bench, this will form permanent backfill
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Photos
checkpoint | 39 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill holes as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 40 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install anchors as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure lengths are that specified on the drawings, centralises in place
label | Records - Subcontractor QA Records
checkpoint | 41 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout - take sample of each batch. Note holes not to be left open for more than 24hrs
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Compression cylinders to be tested at Lab
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 42 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test of Production Anchors - after 7 days when the Grout strength has reached 30Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 43 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Extend anchors to tie in with wall face and install washers, nuts, and corrosion protection as required
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
checkpoint | 44 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 45 - Wall Reinforcement (anchored section)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check supply and installation of reinforcement in wall
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | Records - Subcontractor QA Records
checkpoint | 46 - Wall Reinforcement (anchored section)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for inspection of installed reinforcement
label | Frequency - Min 48 hours prior to pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - CS-4096 Bottom Driven Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 47 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
checkpoint | 48 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed within 1m of structures or obstructions shall be placed with care using suitable equipment and shall be placed 100mm thick and shall be 1 lift higher than the level of the surrounding fill
label | Frequency - During fill operations next to structures or obstructions
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint | 49 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | Frequency - Daily visual survey check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As built drawings
label | Records - Survey receipt
checkpoint | 50 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed in horizontal layers no greater than 250mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | Conformance Criteria - In accordance with specification
label | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint | 51 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install T-RECs tuff matting or approved equivalent
label | Frequency - As shown on drawings
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - In accordance with specification
label | Records - Photographs
checkpoint | 52 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install anchored erosion mesh as specified
label | Frequency - Details as per anchoring ITP Section
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual, Measure, Testing's
label | Conformance Criteria - In accordance with specification
label | Records - Subcontractor QA Records
checkpoint | 53 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mesh - Greenax steel mesh or similar approved product installed and joined as per manufacturers guidelines. Fixed to anchor heads correctly, and fix to wall
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - During installation
label | Conformance Criteria - Visual inspection, extent to be confirmed on site with CPS Engineer
label | Records - Delivery dockets, Photographic evidence
checkpoint | 54 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material on batters is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked.
label | ○ Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material. geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 55 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pavement construction and tie in as per specification
label | Frequency - As Required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification
checkpoint | 56 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guardrail Installation installed as per manufacturers requirements
label | Frequency - As Required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification
checkpoint | 57 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 58 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure correct no. of test sets performed for fill testing
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Test results and calculations of fill volume
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 59 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into M-Files
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 60 - Construction Report
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Construction Report identifying the actual types of materials and methods of construction used throughout the Contract Works.
label | a) Explain the problems and defects encountered during the construction of the Contract Works, and how these were overcome or put right;
label | b) Comment on the remedial and corrective actions taken;
label | c) Comment on any construction outcomes that will impact on future maintenance;
label | d) Include a complete record of all laboratory (and other relevant testing) information for all Materials used in the Contract Works;
label | e) Include mill certificates for all reinforcing steel, pre-stressing strand structural steel and anchors used in the Contract Works;
label | f) As-built survey along the highway centreline, providing co-ordinates and levels of the highway, at maximum 10 metre intervals, certified by a Registered Surveyor. The survey shall be in terms of an established LINZ datum;
label | g) Material warranties;
label | h) All information pertaining to the construction of the Reinforced Soil Slope (RSS), MSE retaining walls and scour protection, and any future maintenance requirements.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 61 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | itp |  |  |  |  | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | 9f633b7a-3c5c-4843-94a3-aa84728eea43
section | Guardrail & Wire Rope Barriers
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Design Check
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All materials to be sourced from registered suppliers
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Registered suppliers
label | Records - Materials register
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Best practice
label | Records - Approved / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | Frequency - On Procurement of installer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | Conformance Criteria - ASHTAS operative and installer course
label | Records - Attendance Certificate
checkpoint | 7 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117 Guardrail Installation Checksheet
checkpoint | 8 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 9 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 10 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person. System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM.
label | Frequency - Prior to trafficking,
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pass inspection
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
section | Final Inspection and Handover
checkpoint | 11 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, CPS COR Report, NCR's and RFI's
checkpoint | 12 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction | itp |  |  |  |  | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction | f3cbf27c-bd31-431e-a580-9c262f9e9028
section | Survey Setout
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
section | Sub Grade
checkpoint | 2 - Sub Grade Strength
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Determine Bearing strength of Sub Grade
label | Frequency - After Dig out Every 5m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Min. 4 blows /100mm
label | Records - QA measurement Sheet (CS-4000) 1m Scala
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Proof Roll of subgrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | Frequency - Prior to Sub Base Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sub base
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for Subbase stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 6 - Saw cutting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - proposed Sawcut line to be inspected by the engineer
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - project spec 6.6
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 8 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Carry out a Level Check on the trimmed Sub base
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm
label | Records - QA measurement Sheet
checkpoint | 9 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | Records - Pavement Lab Testing Spreadsheet
checkpoint | 10 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to base course Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
section | Base Course Construction
checkpoint | 11 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for base Course stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 13 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mat sampling of Basecourse Material
label | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | Conformance Criteria - Grading to comply with specification
label | Records - Mat sample lab test result
checkpoint | 14 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 15 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Carry out a Level Check on the trimmed Basecourse
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm
label | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | Records - QA measurement Sheet
checkpoint | 16 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
checkpoint | 17 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Site photos, Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sealing
checkpoint | 19 - Seal design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal design to be reviewed prior to sealing
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Records - Emails/NTE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Location/Size Confirmation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mark up extent of Chipseal
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | Records - Photos
checkpoint | 21 - Surface Cleanliness
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | Frequency - Prior to application of binder
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photos
checkpoint | 22 - Binder Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Binder application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 23 - Chip Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Chip application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 24 - Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At completion of rolling
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | Records - Photos, QA measurement Sheet
checkpoint | 25 - Photos, QA measurement Sheet
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Removal of excess chip
label | Frequency - Within 48 Hours of Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | Records - Photos, Site logs
checkpoint | 26 - Compaction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - After sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Road Marking
checkpoint | 27 - Road Marking
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | Frequency - Prior to the final line marking
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Hydroseeding
checkpoint | 28 - Hydroseeding
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Final Inspection and Handover
checkpoint | 29 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 30 - Completion Sign Off From Fields Below
label | Records - Signatures