## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | itp |  |  |  |  | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Base of Wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material - consistency though construction
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | Records - Photos
checkpoint | 4 - Material Compliance (Geotextile)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile for rock works - Rolls delivered and delivery dockets gathered. Compliant with Terratex 750k or similar approved
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 5 - Material Compliance (Geotextile)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile for back of excavation - Rolls delivered and delivery dockets gathered. Strength class C, Filtration Class 2
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 6 - Material Compliance (Geogrid)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All rolls of Geogrid are to be checked and left in their protective wrappers until they are required for use
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any defective rolls are NOT to be used in the wall construction - return to the supplier immediately
checkpoint | 7 - Material Compliance (Geogrid)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Dockets
checkpoint | 8 - CTV Culvert
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CTV existing culvert to confirm it should be repaired rather than replaced
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Inspection Video
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Culvert Extension
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm extension connection methodology with CPS Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - submission
label | Records - Subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ground Anchors and proprietary components (plate and lock nuts) - Manufacturer’s test certificate for each batch of anchors. Testing shall be undertaken in an Australian / New Zealand Telarc certified laboratory.
label | ○ The required minimum physical material properties information are as follows: Diameter; Steel area; Ultimate load; Proof load at 0.1%; % of Elongation at yield load; Modulus of elasticity; Relaxation after 1000hr. Refer to specifications and drawings, including proof of coating galv and epoxy.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Manufacturers compliance test certificate with relevant delivery dockets
label | Records - Supplier Certificate, test results and delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout mix - Approval of grout mix design. Include method of batching and mixing and previous test results for pumpable cement grout mixture. Refer to specifications and drawings for grout details.
label | ○ The water-cement ratio shall not be less than w/c = 0.40 and no more than w/c = 0.45. The grout shall not be subject to bleeding in excess of 4% of the initial volume. Admixtures which can control bleed or retard set of the grout shall be used only when approved.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approval of Mix Design
label | Records - Grout mix and test results within subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Material Compliance (Anchors)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Anchoring methodology - CPS has reviewed methodology including location, drilling method, grouting procedure, stressing and testing methods and reaction frame details
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approved subcontractor's method statement
label | Records - Subcontractor's method statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Material Compliance (Walls)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All blocks that are delivered are to be approved for use and are compliant with the Specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - If patterns are used on walls then ensure that the correct colour blocks are ordered and instruction given to teams
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with project specification
label | Records - CS-4020 Bulk Fill Earthworks Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Fill Construction Material
label | Frequency - Each material used / borrow pit
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Repair and Underpin Box Culvert
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Repair as per drawings and specifications
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification and ecology requirements
label | Records - Photographs
checkpoint | 17 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions. Road seal may need to be cut where it is undermined.
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photographs
checkpoint | 18 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cut inspected by Geotechnical Engineer when conditions/material type change
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 19 - Excavation / remove temporary fill material
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure cuts are staged. The slope should be trimmed in stages to maintain stability rather than cutting entire slope in one hit
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 20 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey Receipt
checkpoint | 21 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test the base of the excavation to ensure it meets Specification.
label | Frequency - Prior to backfilling, as per specification
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala and Shear Vane
label | Conformance Criteria - In accordance with specification
label | Records - Lab test result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 23 - Dewatering
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - works shall comply with the relevant consents and the projects Environmental Compliance Requirements
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Dewater in order for construction requirements
checkpoint | 24 - Undercut in areas deemed unsuitable
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cut to waste as required
label | Conformance Criteria - As required by specification and CPS engineer
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 25 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 26 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 27 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install subsoil drainage as required in accordance with specification
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 28 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Place concrete foundation including grouting starter bars as per specifications/drawings
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Concrete to meet the specifications, collect all delivery dockets
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm with CPS Engineer extent of MSE Wall vs Anchored Section
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Submission Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 30 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Permit to Lift
checkpoint | 31 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - CS-4012 MSE Wall Geogrid Checklist and Photo's
checkpoint | 32 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photographs
checkpoint | 33 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Drainage Blanket as shown on Drawings
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photos
checkpoint | 34 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Place fill material on grid layers as per drawings and compact to MSE Wall specifications and test.
label | Frequency - Every lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - As per specification
label | Records - Lab Reports
checkpoint | 36 - Construct MSE Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure line and level of front face is as per design
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 37 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install and test sacrificial test anchors, location to be determined with CPS Engineer, testing after 7 days when the Grout strength has reached 30Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 38 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Construct working bench, this will form permanent backfill
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Photos
checkpoint | 39 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill holes as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 40 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install anchors as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure lengths are that specified on the drawings, centralises in place
label | Records - Subcontractor QA Records
checkpoint | 41 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout - take sample of each batch. Note holes not to be left open for more than 24hrs
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Compression cylinders to be tested at Lab
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 42 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test of Production Anchors - after 7 days when the Grout strength has reached 30Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 43 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Extend anchors to tie in with wall face and install washers, nuts, and corrosion protection as required
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
checkpoint | 44 - Installation of anchors
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 45 - Wall Reinforcement (anchored section)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check supply and installation of reinforcement in wall
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | Records - Subcontractor QA Records
checkpoint | 46 - Wall Reinforcement (anchored section)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for inspection of installed reinforcement
label | Frequency - Min 48 hours prior to pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - CS-4096 Bottom Driven Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 47 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
checkpoint | 48 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed within 1m of structures or obstructions shall be placed with care using suitable equipment and shall be placed 100mm thick and shall be 1 lift higher than the level of the surrounding fill
label | Frequency - During fill operations next to structures or obstructions
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint | 49 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | Frequency - Daily visual survey check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As built drawings
label | Records - Survey receipt
checkpoint | 50 - Slope Filling Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed in horizontal layers no greater than 250mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | Conformance Criteria - In accordance with specification
label | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint | 51 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install T-RECs tuff matting or approved equivalent
label | Frequency - As shown on drawings
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - In accordance with specification
label | Records - Photographs
checkpoint | 52 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install anchored erosion mesh as specified
label | Frequency - Details as per anchoring ITP Section
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual, Measure, Testing's
label | Conformance Criteria - In accordance with specification
label | Records - Subcontractor QA Records
checkpoint | 53 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mesh - Greenax steel mesh or similar approved product installed and joined as per manufacturers guidelines. Fixed to anchor heads correctly, and fix to wall
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - During installation
label | Conformance Criteria - Visual inspection, extent to be confirmed on site with CPS Engineer
label | Records - Delivery dockets, Photographic evidence
checkpoint | 54 - Install Erosion Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material on batters is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked.
label | ○ Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material. geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
checkpoint | 55 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pavement construction and tie in as per specification
label | Frequency - As Required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification
checkpoint | 56 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guardrail Installation installed as per manufacturers requirements
label | Frequency - As Required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - As per specification
checkpoint | 57 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 58 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure correct no. of test sets performed for fill testing
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Test results and calculations of fill volume
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 59 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into M-Files
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 60 - Construction Report
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Construction Report identifying the actual types of materials and methods of construction used throughout the Contract Works.
label | a) Explain the problems and defects encountered during the construction of the Contract Works, and how these were overcome or put right;
label | b) Comment on the remedial and corrective actions taken;
label | c) Comment on any construction outcomes that will impact on future maintenance;
label | d) Include a complete record of all laboratory (and other relevant testing) information for all Materials used in the Contract Works;
label | e) Include mill certificates for all reinforcing steel, pre-stressing strand structural steel and anchors used in the Contract Works;
label | f) As-built survey along the highway centreline, providing co-ordinates and levels of the highway, at maximum 10 metre intervals, certified by a Registered Surveyor. The survey shall be in terms of an established LINZ datum;
label | g) Material warranties;
label | h) All information pertaining to the construction of the Reinforced Soil Slope (RSS), MSE retaining walls and scour protection, and any future maintenance requirements.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 61 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT