## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | itp |  |  |  |  | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers
section | Guardrail & Wire Rope Barriers
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Design Check
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All materials to be sourced from registered suppliers
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Registered suppliers
label | Records - Materials register
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Best practice
label | Records - Approved / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | Frequency - On Procurement of installer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | Conformance Criteria - ASHTAS operative and installer course
label | Records - Attendance Certificate
checkpoint | 7 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117 Guardrail Installation Checksheet
checkpoint | 8 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 9 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 10 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person. System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM.
label | Frequency - Prior to trafficking,
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pass inspection
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
section | Final Inspection and Handover
checkpoint | 11 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, CPS COR Report, NCR's and RFI's
checkpoint | 12 - Completion Sign Off From Fields Below
label | Records - Signatures