## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction | itp |  |  |  |  | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction
section | Survey Setout
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
section | Sub Grade
checkpoint | 2 - Sub Grade Strength
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Determine Bearing strength of Sub Grade
label | Frequency - After Dig out Every 5m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Min. 4 blows /100mm
label | Records - QA measurement Sheet (CS-4000) 1m Scala
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Proof Roll of subgrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | Frequency - Prior to Sub Base Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sub base
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for Subbase stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 6 - Saw cutting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - proposed Sawcut line to be inspected by the engineer
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - project spec 6.6
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 8 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Carry out a Level Check on the trimmed Sub base
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm
label | Records - QA measurement Sheet
checkpoint | 9 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | Records - Pavement Lab Testing Spreadsheet
checkpoint | 10 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to base course Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
section | Base Course Construction
checkpoint | 11 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for base Course stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 13 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mat sampling of Basecourse Material
label | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | Conformance Criteria - Grading to comply with specification
label | Records - Mat sample lab test result
checkpoint | 14 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 15 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Carry out a Level Check on the trimmed Basecourse
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm
label | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | Records - QA measurement Sheet
checkpoint | 16 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
checkpoint | 17 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Site photos, Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sealing
checkpoint | 19 - Seal design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal design to be reviewed prior to sealing
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Records - Emails/NTE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Location/Size Confirmation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mark up extent of Chipseal
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | Records - Photos
checkpoint | 21 - Surface Cleanliness
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | Frequency - Prior to application of binder
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photos
checkpoint | 22 - Binder Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Binder application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 23 - Chip Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Chip application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 24 - Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At completion of rolling
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | Records - Photos, QA measurement Sheet
checkpoint | 25 - Photos, QA measurement Sheet
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Removal of excess chip
label | Frequency - Within 48 Hours of Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | Records - Photos, Site logs
checkpoint | 26 - Compaction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - After sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Road Marking
checkpoint | 27 - Road Marking
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | Frequency - Prior to the final line marking
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Hydroseeding
checkpoint | 28 - Hydroseeding
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | Final Inspection and Handover
checkpoint | 29 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 30 - Completion Sign Off From Fields Below
label | Records - Signatures