## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - S - Precast Spandrel Panel Installation | 00c0c10b-e29f-4c72-ba01-1c60aa680b1e
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Footing Excavation |  |  |  |  | Yes | QA - Footing Excavation | 07b266d9-1b84-46c1-9d24-d9bdcc84af46
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | 851170ec-9c04-5224-8deb-1383eb5b7fc3 |  | tickbox | Location accurate
boolean | a0362e4a-3493-5ab8-b3ac-a69ca17cf89e |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 69ca979a-1a34-5f6f-9de1-fa6e5370a989 |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Excavation completed, reviewed and approved
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | SYS - Compliance Documentation Checklist |  |  |  |  | Yes | SYS - Compliance Documentation Checklist | 0f0c2d17-ece8-4074-a36c-84ac451f8e97
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 1edbbaa1-05e2-5ef8-a571-784e5153c4dd |  | button | PS3 - Completed and Attached | Yes, N/A
button | 8fd06f18-36cd-58a2-a956-71165f3a8f31 |  | button | LBP Memorandum/ Record of works | Yes, N/A
button | 7918c4de-468c-56a5-a167-ed401c428954 |  | button | Concrete Test Results & Mill Certs | Yes, N/A
button | d31f9cf9-7245-530b-a456-1ac391f6d3d3 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | a8b500ed-5650-5530-9aee-e2868003b77e |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - S - Precast Shell Beam Lintel Installation | 0f3c5fea-c576-40f9-a956-35f0c6e1bff8
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Beam Installation |  |  |  |  | Yes | ST - S - Precast Beam Installation | 18cd2679-470b-4045-8dd6-081d3e529080
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Reinforcing |  |  |  |  | Yes | QA - Reinforcing | 18d9ba24-9132-4aae-8111-391c6216b20c
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Construction Joint (location, Roughened and clean)
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers/flange nuts installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length and spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Area cleaned and all debris removed
checkpoint-status |  |  | checkpoint | Consideration for welding certificates (sited and attached)
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved (including couplers & flange nuts)
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
label | da7a5fd1-664c-53a2-8e4c-27255bf91519 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Remedial: |  |  |  |  | Yes | I - C - MV Remedial Item Checklist | 1be3be93-f3f1-4bd3-ba3d-1c0c53465e1f
checkpoint-status |  |  | checkpoint | Remedial Status (MV to "Pass" once satisfied)
text | c724e993-fff6-5253-ad02-b76eff526d98 |  | textbox | Location of Remedial
text | 8deb9ae8-99f5-5800-9687-6d4b6839edcc |  | textbox | Remedial Description
text | 233bb5c5-6089-50b7-9d8d-3444150bb470 |  | textbox | Action Required
holdpoint |  |  | signoff | Request MV Signoff on Remedial
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | ST - S - Precast Flat Slab Installation | 24739000-878a-48f5-b946-5fa8d956be97
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Foundations) |  |  |  |  | Yes | QA - Concrete Pour (Foundations) | 2b418ff0-12b1-4ae2-8311-c423b8c51139
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | 87a0d4fc-b17e-5439-a5c3-fba70d728108 |  | textbox | Area to be poured
text | 9ae91ee1-ebf3-5816-9464-690468ddb24f |  | textbox | Date of pour
boolean | a34a735d-0414-5b4a-8864-18d003ff0dcb |  | tickbox | Latest drawings available, checked and referenced
boolean | 68ac47ed-5dd8-50ca-9f15-8f2fee855ec4 |  | tickbox | Marked up drawing of area to be poured completed & attached
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Cold joints set up correctly
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate, sufficiently fixed in place/braced)
checkpoint-status |  |  | checkpoint | Engineer inspection completed & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Council inspection completed (if required) & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Concrete Supplier Specifics & Test Results
checkpoint-status |  |  | checkpoint | Concrete Supplier Details
text | c934cc8c-ef73-5ed8-a8b9-9938f33daf11 |  | textbox | Supplier Name
text | d2f6f0ee-eae7-5c58-aa44-d4c8350ba3f9 |  | textbox | Specified concrete strength
text | 18c26790-7702-56e7-ab7a-7c2ef5bcac8d |  | textbox | Concrete strength ordered
text | 923b91b4-f41a-543b-b44f-0c0188bb1cb4 |  | textbox | Concrete quantity ordered
button | afdf3499-3956-5a8c-8510-50c2c8224919 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & acceptable
boolean | 94968603-8c70-57a1-9ca2-6619d16d56fa |  | tickbox | Correct specifications & strength
checkpoint-status |  |  | checkpoint | All concrete dockets photographed & attached here
label | 56696cf0-1511-5765-9c42-4cf6c8ebafad |  | note | "PASS" only once all concrete dockets relating to this pour have been attached here
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | 5e7e0b9a-8035-58f5-b423-9e21e3ddb1a6 |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | 3034c0a0-f1c3-5238-826b-0121293313c7 |  | button | 7 day test results recorded | Yes, No, N/A
text | 36c63bbc-d06b-5f1e-8417-47cf03018624 |  | textbox | 7 day test - strength achieved
button | 13557d5c-7fd0-51eb-80d5-dc9eadc0b4b5 |  | button | 28 day test results recorded | Yes, No, N/A
text | 1fd09eb9-2b3b-5de9-8d22-985400846663 |  | textbox | 28 day test - strength achieved
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | Concrete Distribution Details
text | 124172e5-a4c9-521f-ad7f-8c429cc25817 |  | textbox | Who is distributing/pumping the concrete
text | 99459aa1-27a7-549a-bae1-3ceebacef9b8 |  | textbox | How is the concrete distributed
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Concrete Placement
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 1daed683-d757-5b9d-a834-8f0270ad37b9 |  | textbox | Who is placing the concrete
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
label | 703255a8-bcae-5480-8e6a-82265ceae594 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
label | 7e5aa409-23dd-5429-ac8f-02f5534701e6 |  | note | Select "N/A" if there is no remedial work identified
label | 550c3b84-b468-511a-a73e-aac1b812d3f0 |  | note | Select "FAIL" if there is remedial work identified and "PASS" once it has been resolved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
label | dbe08fde-fcbc-5d5a-bf08-a27f1f0d81ec |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Formwork |  |  |  |  | Yes | QA - Formwork | 2ee0c8cc-10d2-4faa-b6f8-9d36d2585759
checkpoint-status |  |  | checkpoint | Fines placed to specification and area clear for polythene
checkpoint-status |  |  | checkpoint | DPM placed correctly
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
boolean | 1b0f3db4-6708-513f-9431-7a838376b579 |  | tickbox | Sufficiently braced
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
label | 94f9d951-fd6c-5496-b3c6-b8a64361a8d0 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | ST - S - Precast Flat Slab Installation | 40e6c14d-16af-4b4f-b409-29652d82d63a
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Blockwork |  |  |  |  | Yes | QA - Blockwork | 5ea43b6b-d0d5-46ed-b9d8-9a109254f853
checkpoint-group |  |  | section | Blockwork Setout/Pre Start QA
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately
checkpoint-status |  |  | checkpoint | RL reference/TOW confirmed
checkpoint-status |  |  | checkpoint | Starter bars correct (location, length and strength)
checkpoint-status |  |  | checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint-status |  |  | checkpoint | Blockwork reinforcing steel delivered correct and accessible (attach photos of respective reinforcing docket)
checkpoint-status |  |  | checkpoint | Any additional pre start observations
checkpoint-status |  |  | checkpoint | Approval given to start laying blockwork
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pre Pour
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/size/splicing etc)
checkpoint-status |  |  | checkpoint | Ties/Control joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Any additional observations/inspections attached
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
label | 05bab4d4-98ba-5fdb-8935-2c448119bae7 |  | note | Mortar Joints installed within tolerances
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pour
checkpoint-status |  |  | checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
text | 6426cde7-1211-508c-a756-4f0ec21f85bb |  | textbox | Method used to pour concrete (e.g. boom/line pump):
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | 730fcfd9-8fd8-51ae-80a3-46bb70e7746d |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | cc562b37-3106-5f2f-a865-519cc2313f7d |  | button | 7 day test results recorded | Yes, No, N/A
text | 651b4028-515a-5988-9972-ecc10cd9a515 |  | textbox | 7 day test - strength achieved
button | 4687fc46-ec75-564d-b217-639e3a10ace0 |  | button | 28 day test results recorded | Yes, No, N/A
text | 17e11ce2-c5b0-5568-9522-094578b1896c |  | textbox | 28 day test - strength achieved
checkpoint-status |  |  | checkpoint | General photos and any additional observations
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block (if applicable)
checkpoint-status |  |  | checkpoint | Any concrete spillage/splatter cleaned up
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification (2-3 photos uploaded)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Foundations) |  |  |  |  | Yes | QA - Concrete Pour (Foundations) | 64c5db10-4ffd-4988-87df-e5d2fd77b186
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | 8697767d-a39f-5fe1-94c2-cbc06cf11ec8 |  | textbox | Area to be poured
text | b8d8f56d-1ae1-5ef2-8374-a3beb96318f5 |  | textbox | Date of pour
boolean | ebb18bf6-be62-5e4a-91e6-a5560a49d713 |  | tickbox | Latest drawings available, checked and referenced
boolean | 66d6c69e-97ba-513d-8f73-86e2865cba84 |  | tickbox | Marked up drawing of area to be poured completed & attached
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Cold joints set up correctly
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate, sufficiently fixed in place/braced)
checkpoint-status |  |  | checkpoint | Engineer inspection completed & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Council inspection completed (if required) & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Concrete Supplier Specifics & Test Results
checkpoint-status |  |  | checkpoint | Concrete Supplier Details
text | 5eda2e2f-43cb-5d25-a33e-919b4ad6944f |  | textbox | Supplier Name
text | 467f25de-7d3d-5a49-87f2-6d7119e52e7b |  | textbox | Specified concrete strength
text | 329436f4-588b-56f4-86b4-72042e1615d2 |  | textbox | Concrete strength ordered
text | 07925379-d543-5b4d-bac6-c72a7ccf44ac |  | textbox | Concrete quantity ordered
button | c58923dd-707d-5bd7-9eca-a1f3145aa1aa |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & acceptable
boolean | c82ac456-9691-5f7b-a24d-18c1ae9ebb28 |  | tickbox | Correct specifications & strength
checkpoint-status |  |  | checkpoint | All concrete dockets photographed & attached here
label | 9c04d882-69d5-55f7-a578-c193b4dc547f |  | note | "PASS" only once all concrete dockets relating to this pour have been attached here
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | 0c30b278-017f-5c77-8597-f1e1cfb8365f |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | 072f24b7-3641-5fb5-96ff-8d14e9fa70e6 |  | button | 7 day test results recorded | Yes, No, N/A
text | ebdaf75e-8f86-5f24-b7ab-575971e56573 |  | textbox | 7 day test - strength achieved
button | 3fdb03dd-abc1-5671-abac-895cb0ec862f |  | button | 28 day test results recorded | Yes, No, N/A
text | f860282a-f897-51cd-914e-3bd6cac6e358 |  | textbox | 28 day test - strength achieved
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | Concrete Distribution Details
text | 41bc3bad-9fee-5247-b7ae-16dc5f9a627f |  | textbox | Who is distributing/pumping the concrete
text | 406016e3-5c90-596c-b492-91fe679ea4dc |  | textbox | How is the concrete distributed
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Concrete Placement
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | e4e3dfad-25dd-568d-aec5-c804c71051bb |  | textbox | Who is placing the concrete
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
label | 67a00f0f-cae8-50ee-b212-eddbfa5ec267 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
label | 4629828a-8580-56ac-9a92-9c45edf5585b |  | note | Select "N/A" if there is no remedial work identified
label | 705ac8b8-7b6d-5a6a-ac69-f03a0c3ad9c1 |  | note | Select "FAIL" if there is remedial work identified and "PASS" once it has been resolved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
label | 2f9e65e6-dfbd-50e3-8a78-551f0cadba19 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Insitu Stich Joints |  |  |  |  | Yes | QA - Insitu Stich Joints | 67e44d58-93ff-415c-aa87-cdd8092c6a55
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | 3b912a5d-24d6-5f5b-bcf6-6c2a6841e513 |  | textbox | Area to be poured:
text | 7024e35b-2c27-5023-b4a4-e9d7baac07e9 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete Strength Test Records
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Compliance Documents |  |  |  |  | Yes | I - C - MV Compliance Documents | 73352d89-ae68-4e06-981c-d1d0555adf54
checkpoint-status |  |  | checkpoint | Compliance Documents
boolean | 6a3ccff8-1dfc-5aa9-ab74-f25d027a4af4 |  | tickbox | LBP Memorandum
boolean | 6484e59b-182f-5b5f-8e83-4adea293e101 |  | tickbox | Mill Certificates
boolean | 9e113645-aa7d-5357-b69a-6d2c9367a36c |  | tickbox | Concrete Dockets
boolean | 5c3298b1-b39e-57ea-bb71-0518d8d2fcef |  | tickbox | Concrete Strength Test Results
checkpoint-status |  |  | checkpoint | Mitchell Vranjes PS4 Attached
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Blockwork Footings) |  |  |  |  | Yes | QA - Concrete Pour (Blockwork Footings) | 73441b7d-efb7-475a-b055-0084b390e99c
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
label | 156369cc-8cad-53dc-89ed-7515888b07ec |  | note | Size and type correct to specification
label | 6be9721b-14f0-53fc-84fb-60ef595a067b |  | note | Reinforcing spacing and location correct
label | 7f67748a-96c4-5ac7-98be-fc393271d6ad |  | note | Specified covers checked/correct
label | 6fb5e497-6a84-564d-a21d-6398e36d67e4 |  | note | Splice laps checked/correct
label | d8a7dfc7-4012-5667-9af0-3ab21f74edaa |  | note | Any starter bars are installed correctly (location, size and spacing )
label | afc4074b-bb28-5898-8529-ce683fa3c5cc |  | note | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Pre Pour completed - Approval to pour
label | 3af85507-a026-5007-af97-19313f084981 |  | note | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | 71c10e80-0094-5fd6-a1fe-91b6d73d56eb |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | abda6ca9-bfc0-52e6-84ec-7273d7e03a52 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Blockwork |  |  |  |  | Yes | QA - Blockwork | 774aba29-af05-45ac-ac10-726cade81973
checkpoint-group |  |  | section | Blockwork Setout/Pre Start QA
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately
checkpoint-status |  |  | checkpoint | RL reference/TOW confirmed
checkpoint-status |  |  | checkpoint | Starter bars correct (location, length and strength)
checkpoint-status |  |  | checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint-status |  |  | checkpoint | Blockwork reinforcing steel delivered correct and accessible (attach photos of respective reinforcing docket)
checkpoint-status |  |  | checkpoint | Any additional pre start observations
checkpoint-status |  |  | checkpoint | Approval given to start laying blockwork
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pre Pour
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/size/splicing etc)
checkpoint-status |  |  | checkpoint | Ties/Control joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Any additional observations/inspections attached
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
label | b5b8e40e-99b8-5dfb-8dca-f08c507e977b |  | note | Mortar Joints installed within tolerances
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pour
checkpoint-status |  |  | checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
text | 24d7dd62-bbce-561b-88ba-b4317147f4da |  | textbox | Method used to pour concrete (e.g. boom/line pump):
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | 3c9c7741-f274-5230-beb5-6cd03a50ddbd |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | 18fa0520-57d8-5dce-ad0c-868de83c814e |  | button | 7 day test results recorded | Yes, No, N/A
text | 327a6927-938b-5709-9bfa-a55ab1720b0c |  | textbox | 7 day test - strength achieved
button | 4d7c1aa2-266e-5110-b61c-c986196fd2b4 |  | button | 28 day test results recorded | Yes, No, N/A
text | 0204b0a1-086e-56f8-90d9-903c0c5541ae |  | textbox | 28 day test - strength achieved
checkpoint-status |  |  | checkpoint | General photos and any additional observations
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block (if applicable)
checkpoint-status |  |  | checkpoint | Any concrete spillage/splatter cleaned up
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification (2-3 photos uploaded)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | MV Site Visit Report - |  |  |  |  | Yes | I - C - MV Consultant Site Visit Report | 85cfd035-b13a-459f-9d67-090508471813
checkpoint-group |  |  | section | Site Inspection Details
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | 60ef59fe-14df-58e0-a35a-eedd7ac6b741 |  | textbox | Building Consent No.
text | 50a23467-0aab-5691-8cf1-e947a90b32f2 |  | textbox | Date site visit occurred
text | 4ebd846e-3694-56d8-ab51-90859989005b |  | textbox | Tom on site (include start and end times)
text | 36cdb572-f69d-54dd-8ed2-041f8fa7e899 |  | textbox | Report prepared by - Engineer's name
text | 7f78d0be-deb2-5b77-a589-ceaa899a7758 |  | textbox | Additional personnel accompanying engineer
button | 9fa7dc57-30cf-5416-bf84-33741bf5728f |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | f33deb96-11e5-5266-84e9-796765665a54 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | 94612d96-c97b-5e54-8148-77b502780929 |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-group |  |  | section | Inspection Specifics
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or reinspection required to defective elements (select Fail - Works Cannot Proceed)
text | 34c54d48-41a9-57e5-b270-a021645af2c9 |  | textbox | Remedial(s) - Recorded and Closed Out
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Blockwork Footings) |  |  |  |  | Yes | QA - Concrete Pour (Blockwork Footings) | 8bc63657-3d77-4887-bf63-d522fb23cd72
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
label | 5d70bf73-1f63-548e-9ad9-4a5a7ba81963 |  | note | Size and type correct to specification
label | b70ab53e-30ef-5a67-9a2c-64e795bd24d6 |  | note | Reinforcing spacing and location correct
label | b053daae-7213-524e-99a9-1b4abd584f37 |  | note | Specified covers checked/correct
label | 8076148a-4884-5084-9270-26eaaafa3b9f |  | note | Splice laps checked/correct
label | 5d8d359a-dcef-533c-be74-adb2afcbb1a3 |  | note | Any starter bars are installed correctly (location, size and spacing )
label | 79509afd-f82a-5277-9e4e-d8c502529b71 |  | note | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Pre Pour completed - Approval to pour
label | ce43ad5b-221b-5254-b919-0dabc867c7a6 |  | note | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | 83dc37da-82cb-5a79-af89-2ebf255b2984 |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | c624e44e-2b44-59bd-9468-095f8a23ff0c |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Insitu Stich Joints |  |  |  |  | Yes | QA - Insitu Stich Joints | 91ca5049-a578-4805-973f-10d25b820c76
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | 1dcd5b2f-f8d5-5ac1-a717-bc2f24814263 |  | textbox | Area to be poured:
text | 6385a0ed-d1a9-5774-a188-8b57dfabf76c |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete Strength Test Records
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Edge Beams Installation |  |  |  |  | Yes | ST - S - Precast Edge Beams Installation | 99ad2673-2501-4efd-ac79-52b66f1b60b1
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Edge Beams installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | Rib & Infill Installation | a07a0ea4-0e0c-46e2-b915-dcf369c74154
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Infill Panel Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Edge Beams Installation |  |  |  |  | Yes | ST - S - Precast Edge Beams Installation | ab83ac56-ee62-492b-9897-067b9a2542c5
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Edge Beams installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | ST - S - Precast Wall Panel Installation | abd81b53-c7b2-417a-9482-3322f6f740d1
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Beam Installation |  |  |  |  | Yes | ST - S - Precast Beam Installation | bcb7932c-e548-4096-b90b-ed8581771b07
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-status |  |  | checklist | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS |  |  |  |  | Yes | Holdpoint | cc927810-5f54-4a41-9b2a-bf3d39b8ed60
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Reinforcing |  |  |  |  | Yes | QA - Reinforcing | d0f3ab36-dce0-4f63-9c6e-5b2f29946834
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Construction Joint (location, Roughened and clean)
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers/flange nuts installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length and spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Area cleaned and all debris removed
checkpoint-status |  |  | checkpoint | Consideration for welding certificates (sited and attached)
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved (including couplers & flange nuts)
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
label | 9f512b64-f687-5ea3-9ff1-73684cc45606 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - S - Precast Wall Bracket Installation | d210f7e8-37be-4888-b970-fa5114183fca
checkpoint-status |  |  | checkpoint | Bracket correct size as per drawing
checkpoint-status |  |  | checkpoint | Cast in weld plate in correct position
checkpoint-status |  |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status |  |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status |  |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status |  |  | checkpoint | Paint repair completed
checkpoint-status |  |  | checkpoint | Bracket installation completed correctly (checked location & level)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | Rib & Infill Installation | d8ce281c-2d85-4cd3-84be-ce1a98551ba1
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Infill Panel Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | ST - S - Precast Wall Panel Installation | d98c90bb-6fa9-4248-9e45-d9f74791e751
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - S - Precast Shell Beam Lintel Installation | eb778cbd-861b-4ccf-9962-22afe0d851ec
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Footing Excavation |  |  |  |  | Yes | QA - Footing Excavation | eb98d860-bb7c-4c97-bfba-3574558a40dc
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | c7f54a28-6461-5bfb-a91b-5f986ea0d0ed |  | tickbox | Location accurate
boolean | 716d7b4e-3102-5f3f-b28c-51e1f119c2a7 |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 5c71827e-9524-5301-a316-0a8c2281f430 |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Excavation completed, reviewed and approved
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - S - Precast Wall Bracket Installation | ef9510bd-d269-4d17-b5a5-4f0ba0211f99
checkpoint-status |  |  | checkpoint | Bracket correct size as per drawing
checkpoint-status |  |  | checkpoint | Cast in weld plate in correct position
checkpoint-status |  |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status |  |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status |  |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status |  |  | checkpoint | Paint repair completed
checkpoint-status |  |  | checkpoint | Bracket installation completed correctly (checked location & level)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | QA - Formwork |  |  |  |  | Yes | QA - Formwork | f0f8a37d-d368-4cd9-b84d-08c84d13746f
checkpoint-status |  |  | checkpoint | Fines placed to specification and area clear for polythene
checkpoint-status |  |  | checkpoint | DPM placed correctly
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
boolean | 4df036bc-33ae-52db-b5f1-20ae1268e97c |  | tickbox | Sufficiently braced
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
label | bd0e7ad3-3c0e-5aa0-9ceb-ccf8fb41a3f7 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - S - Precast Spandrel Panel Installation | fc8e7a9e-4551-4ae9-8171-31779bca277c
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS