## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Chipseal
| Scope |  |  | Chipseal
Rows
|  | Chipseal | grouping | Chipseal
|  | Raukokere Hill III A |  | Raukokere Hill III A | Chipseal
|  | Raukokere Hill III |  | Raukokere Hill III | Chipseal
|  | Ruakokore Hill |  | Ruakokore Hill | Chipseal
|  | Ruakokore Hill I |  | Ruakokore Hill I | Chipseal
|  | Te Waiti Bridge West |  | Te Waiti Bridge West | Chipseal
|  | Raukokere West I |  | Raukokere West I | Chipseal
|  | Pirikaraka Bridge West I |  | Pirikaraka Bridge West I | Chipseal
|  | Kukumoa Bridge East I |  | Kukumoa Bridge East I | Chipseal
|  | Huntress creek SCRIM SITE |  | Huntress creek SCRIM SITE | Chipseal
|  | Rest Area - Lookout II |  | Rest Area - Lookout II | Chipseal
|  | Rankin Road SCRIM |  | Rankin Road SCRIM | Chipseal
|  | Lysaghts Bridge SCRIM |  | Lysaghts Bridge SCRIM | Chipseal
|  | Lysaghts Bridge East SCRIM |  | Lysaghts Bridge East SCRIM | Chipseal
|  | Lysaghts Bridge East |  | Lysaghts Bridge East | Chipseal
|  | Nukuhou North I |  | Nukuhou North I | Chipseal
|  | Wainui Swamp |  | Wainui Swamp | Chipseal
|  | Waimana Straight East 16/17 RS |  | Waimana Straight East 16/17 RS | Chipseal
|  | Gun Shop Hill III |  | Gun Shop Hill III | Chipseal
|  | Scout Hall to Timber Yard C |  | Scout Hall to Timber Yard C | Chipseal
|  | Onepu Spring Rd to Railway A |  | Onepu Spring Rd to Railway A | Chipseal
|  | Onepu Spring Rd to Railway B |  | Onepu Spring Rd to Railway B | Chipseal
|  | Onepu Spring Rd to Railway C |  | Onepu Spring Rd to Railway C | Chipseal
|  | Strawberry Garden |  | Strawberry Garden | Chipseal
|  | Braemar Road West |  | Braemar Road West | Chipseal
|  | Otipa Curves |  | Otipa Curves | Chipseal
|  | McKee Overbridge East |  | McKee Overbridge East | Chipseal
|  | Sub-station |  | Sub-station | Chipseal
|  | Sub-station A |  | Sub-station A | Chipseal
|  | Sub-station II |  | Sub-station II | Chipseal
|  | Fletcher Avenue East |  | Fletcher Avenue East | Chipseal
|  | Short Street Inter./West |  | Short Street Inter./West | Chipseal
|  | Valley Rd |  | Valley Rd | Chipseal
|  | Tui Glen Forest |  | Tui Glen Forest | Chipseal
|  | Awaiti to Edgecumbe 2015/16 RS |  | Awaiti to Edgecumbe 2015/16 RS | Chipseal
|  | Omeheu Canal Bridge West 2015/16 |  | Omeheu Canal Bridge West 2015/16 | Chipseal
|  | Omeheu Canal Bridge East 2015/16 |  | Omeheu Canal Bridge East 2015/16 | Chipseal
|  | Ice sign to Frosty |  | Ice sign to Frosty | Chipseal
|  | Frosty to Stoclpile I |  | Frosty to Stoclpile I | Chipseal
|  | Frosty to Stockpile II |  | Frosty to Stockpile II | Chipseal
|  | Anaputu Point |  | Anaputu Point | Chipseal
|  | Ruato Rock Bluff |  | Ruato Rock Bluff | Chipseal
|  | Te Puia Rd East |  | Te Puia Rd East | Chipseal
|  | Ludgates Hill- Okawa Bay- Takinga |  | Ludgates Hill- Okawa Bay- Takinga | Chipseal
|  | Okawa Bay |  | Okawa Bay | Chipseal
|  | Mourea |  | Mourea | Chipseal
|  | Kingi Rd II |  | Kingi Rd II | Chipseal
|  | Sun Valley Nth |  | Sun Valley Nth | Chipseal
|  | Sun Valley Curves 2013/14 RHAB |  | Sun Valley Curves 2013/14 RHAB | Chipseal
|  | Sun Valley Nth II |  | Sun Valley Nth II | Chipseal
|  | Sun Valley Curves II 2013/14 RHAB |  | Sun Valley Curves II 2013/14 RHAB | Chipseal
|  | Pakeha St I |  | Pakeha St I | Chipseal
|  | Pakeha St II |  | Pakeha St II | Chipseal
|  | Pakeha St-Manawahe Rd |  | Pakeha St-Manawahe Rd | Chipseal
|  | Manawahe Road Intersection |  | Manawahe Road Intersection | Chipseal
|  | Pine View Lane |  | Pine View Lane | Chipseal
|  | Angle Road North |  | Angle Road North | Chipseal
|  | Fortunes Road East |  | Fortunes Road East | Chipseal
|  | Leonard Rd Curves I |  | Leonard Rd Curves I | Chipseal
|  | Awakeri West |  | Awakeri West | Chipseal
|  | Western Drain East |  | Western Drain East | Chipseal
|  | Hydro Road East |  | Hydro Road East | Chipseal
|  | Thirteen Curves |  | Thirteen Curves | Chipseal
|  | Opato Bridge West II A |  | Opato Bridge West II A | Chipseal
|  | Opato Bridge |  | Opato Bridge | Chipseal
|  | Opato Bridge East |  | Opato Bridge East | Chipseal
|  | Apirana dTIMS Site |  | Apirana dTIMS Site | Chipseal
|  | Pekepeke OBridge East I |  | Pekepeke OBridge East I | Chipseal
|  | Phillips Cattle Underpass |  | Phillips Cattle Underpass | Chipseal
|  | Frosts |  | Frosts | Chipseal
|  | Regional Boundary West 1 |  | Regional Boundary West 1 | Chipseal
|  | Kaharoa Rd South 1 |  | Kaharoa Rd South 1 | Chipseal
|  | Jackson SCRIM SITE |  | Jackson SCRIM SITE | Chipseal
|  | Tupapakurua 1 |  | Tupapakurua 1 | Chipseal
|  | Tupapakurua 3 |  | Tupapakurua 3 | Chipseal
|  | Ngongotaha Rd Straight |  | Ngongotaha Rd Straight | Chipseal
|  | Waiotapu I D |  | Waiotapu I D | Chipseal
|  | Wharepapa Bridge South II |  | Wharepapa Bridge South II | Chipseal
|  | Boundary |  | Boundary | Chipseal
Columns
|  | 1.0 Pre-Works - Binder Penetration Grade |  | Binder Penetration Grade | 1.0 Pre-Works (Off Site)
|  | 1.0 Pre-Works - Production Property - Cleaness Value |  | Production Property - Cleaness Value | 1.0 Pre-Works (Off Site)
|  | 1.0 Pre-Works - Stakeholder Management Requirements met |  | Stakeholder Management Requirements met | 1.0 Pre-Works (Off Site)
|  | 1.0 Pre-Works - Confirm if any environmental protection is required |  | Confirm if any environmental protection is required | 1.0 Pre-Works (Off Site)
|  | 1.0 Pre-Works - Daily work briefing, confirm scope, all staff/materials/plant needed to complete work |  | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work | 1.0 Pre-Works (Off Site)
|  | 2.0 Pre-Construction - Job start, identify risks & controls, communicated to team |  | Job start, identify risks and controls, communicated to team | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Establish traffic management to plan |  | Establish traffic management to plan | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Confirm site is on approved programme |  | Confirm site is on approved programme | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Confirm site extents |  | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Stockpiled sealing chip is clean & suitable for sealing |  | Stockpiled sealing chip is clean and suitable for sealing | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Stockpiled sealing chip is same grade(s) in chipseal design |  | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Record & photograph environmental protection measures installed |  | Record & photograph environmental protection measures installed | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Binder application rate |  | Binder application rate | 2.0 Pre-Construction (On Site)
|  | 2.0 Pre-Construction - Pre-Sealing surface condition |  | Pre-Sealing surface condition | 2.0 Pre-Construction (On Site)
|  | 3.0 Construction - Start spraying Temp >10°C |  | Start spraying Temp >10°C | 3.0 Construction
|  | 3.0 Construction - Binder application variation |  | Binder application variation | 3.0 Construction
|  | 3.0 Construction - Sealing chip application |  | Sealing chip application | 3.0 Construction
|  | 3.0 Construction - PTR Rolling pattern |  | PTR Rolling pattern | 3.0 Construction
|  | 3.0 Construction - Traffickating |  | Traffickating | 3.0 Construction
|  | 3.0 Construction - Tagging for line marking |  | Tagging for line marking | 3.0 Construction
|  | 3.0 Construction - Post-Sealing Surfacing Condition |  | Post-Sealing Surfacing Condition | 3.0 Construction
|  | 4.0 Post-Construction - Linemarking & RRPM Reinstated |  | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing | 4.0 Post-Construction
|  | 4.0 Post-Construction - Spray Sheet/s Checked & Supplied for Claiming |  | Spray Sheet/s Checked & Supplied for Claiming | 4.0 Post-Construction
|  | 4.0 Post-Construction - Collect & Upload RAMM data |  | Collect & Upload RAMM data | 4.0 Post-Construction
|  | 5.0 Out Of Season Sealing - Out of Season Sealing |  | Out of Season Sealing | 5.0 Out Of Season Sealing
AC
| Scope |  |  | AC
Rows
|  | AC | grouping | AC
|  | Sala street |  | Sala street | AC
|  | Puarenga Bridge East - D |  | Puarenga Bridge East - D | AC
|  | Puarenga Bridge - I |  | Puarenga Bridge - I | AC
|  | Hamiora place D and I |  | Hamiora place D and I | AC
|  | Ngapuna - I |  | Ngapuna - I | AC
|  | Tarawera to Tennyson |  | Tarawera to Tennyson | AC
|  | Eruera street |  | Eruera street | AC
|  | Cochrane St Pedestrian Xing |  | Cochrane St Pedestrian Xing | AC
|  | Rainbow Farm to Cochrane |  | Rainbow Farm to Cochrane | AC
|  | Dunn Rd Intersection I |  | Dunn Rd Intersection I | AC
|  | Goudies Rd Intersection |  | Goudies Rd Intersection | AC
|  | Fishermans bend |  | Fishermans bend | AC
|  | Balls Bluff Waterfall |  | Balls Bluff Waterfall | AC
|  | St John Rab |  | St John Rab | AC
|  | Gauging station corner |  | Gauging station corner | AC
|  | Reids Road I |  | Reids Road I | AC
|  | Overarching ITP items |  | Overarching ITP items | AC
Columns
|  | 1.0 Pre-Work - Approved Design Report |  | Approved Design Report | 1.0 Pre-Work
|  | 1.0 Pre-Work - Pre seal inspection completed: |  | Pre seal inspection completed: | 1.0 Pre-Work
|  | 1.0 Pre-Work - Stakeholder Management Requirements met |  | Stakeholder Management Requirements met | 1.0 Pre-Work
|  | 1.0 Pre-Work - Daily work briefing, confirm scope, all staff/materials/plant needed to complete work & weather forecast compliant |  | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used | 1.0 Pre-Work
|  | 1.0 Pre-Work - Confirm Traffic management requirements met |  | Confirm Traffic management requirements met | 1.0 Pre-Work
|  | 2.0 Site set up - Ambient Conditions |  | Ambient Conditions: Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above | 2.0 Site set up
|  | 2.0 Site set up - Method/Test Required - Temperature Gun Check | Method/Test Required - Temperature Gun Check | Ambient Conditions: Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above | 2.0 Site set up
|  | 2.0 Site set up - Job start, identify risks & controls, communicated to team |  | Job start, identify risks and controls, communicated to team | 2.0 Site set up
|  | 2.0 Site set up - Establish traffic management to plan |  | Establish traffic management to plan | 2.0 Site set up
|  | 2.0 Site set up - Identification of Services |  | Identification of Services: Service Plans on-site, Shallow Services marked | 2.0 Site set up
|  | 2.0 Site set up - Photograph environmental protection measures installed |  | Photograph environmental protection measures installed | 2.0 Site set up
|  | 3.0 Milling - Milling undertaken to correct depth: up to +10mm nominal thickness for each layer |  | Milling undertaken to correct depth: up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report | 3.0 Milling (If Required)
|  | 3.0 Milling - Proofrolling to be done on milled surface |  | Proofrolling to be done on milled surface: Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost. | 3.0 Milling (If Required)
|  | 4.0 Membrane - Application as per Design Requirements (Chip size/binder application rate) |  | Application as per Design Requirements (Chip size / binder application rate) | 4.0 Membrane (If Required)
|  | 5.0 Strengthening Repairs - Delivery & compaction temperature |  | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. | 5.0 Strengthening Repairs (If Required)
|  | 5.0 Strengthening Repairs - Method/Test Required - Temperature Gun Check | Method/Test Required - Temperature Gun Check | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. | 5.0 Strengthening Repairs (If Required)
|  | 5.0 Strengthening Repairs - Structural Asphalt Layer Thickness |  | Structural Asphalt Layer Thickness: Each Layer >80mm with a max discrepency of +10mm nominal thickness | 5.0 Strengthening Repairs (If Required)
|  | 5.0 Strengthening Repairs - Compaction & Air Voids |  | Compaction and Air Voids | 5.0 Strengthening Repairs (If Required)
|  | 5.0 Strengthening Repairs - Proven layer thickness & compaction |  | Proven layer thickness and compaction | 5.0 Strengthening Repairs (If Required)
|  | 7.0 Wearing Course - Delivery & compaction temperature |  | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. | 7.0 Wearing Course
|  | 7.0 Wearing Course - Method/Test Required - Temperature Gun Check | Method/Test Required - Temperature Gun Check | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. | 7.0 Wearing Course
|  | 7.0 Wearing Course - Surface layer thickness |  | Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness. If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report. | 7.0 Wearing Course
|  | 7.0 Wearing Course - Compaction & Air Voids |  | Compaction and Air Voids | 7.0 Wearing Course
|  | 7.0 Wearing Course - Proven layer thickness & compaction |  | Proven layer thickness and compaction | 7.0 Wearing Course
|  | 8.0 Post-Construction - Supervisor to provide an update regarding site completion per shift |  | Supervisor to provide an update regarding site completion per shift | 8.0 Post-Construction
|  | 8.0 Post-Construction - Linemarking & RRPM Reinstated: Matches previous linemarking |  | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing | 8.0 Post-Construction
|  | 8.0 Post-Construction - Post seal inspection completed: |  | Post seal inspection completed: | 8.0 Post-Construction
|  | 8.0 Post-Construction - As-Built records – structural patches |  | As-Built records – structural patches | 8.0 Post-Construction
|  | 8.0 Post-Construction - Collect RAMM data |  | Collect RAMM data | 8.0 Post-Construction
|  | 1.0 Overarching items - ITP submitted & approved |  | ITP submitted and approved | 1.0 Overarching items
|  | 1.0 Overarching items - QMP submitted & approved |  | QMP submitted and approved | 1.0 Overarching items
|  | 1.0 Overarching items - QA pack submitted & approved |  | QA pack submitted and approved | 1.0 Overarching items
|  | 1.0 Overarching items - Final approved program received |  | Final approved program received | 1.0 Overarching items
|  | 1.0 Overarching items - Ensure accuracy of tracker with final program |  | Ensure accuracy of tracker with final program | 1.0 Overarching items
|  | 1.0 Overarching items - Pre commencement meeting with asphalt delivery team |  | Pre commencement meeting with asphalt delivery team | 1.0 Overarching items
|  | 1.0 Overarching items - JSEA submitted & communicated to team |  | JSEA submitted and communicated to team | 1.0 Overarching items
|  | 1.0 Overarching items - Approved JMF for Strengthening Repairs Mix |  | Approved JMF for Strengthening Repairs Mix | 1.0 Overarching items
|  | 1.0 Overarching items - Production testing for strenghthening repair mix |  | Production testing for strenghthening repair mix | 1.0 Overarching items
|  | 1.0 Overarching items - Approved JMF for Wearing Course Mix |  | Approved JMF for Wearing Course Mix | 1.0 Overarching items
|  | 1.0 Overarching items - Production testing for wearing course mixes |  | Production testing for wearing course mixes | 1.0 Overarching items
|  | 1.0 Overarching items - Confirm or establish , NDM offset & rolling patterns |  | Confirm or establish , NDM offset and rolling patterns | 1.0 Overarching items
|  | 1.0 Overarching items - Post construction drive over |  | Post construction drive over | 1.0 Overarching items
|  | 2.0 Out Of Season Paving - Out of Season Paving |  | Out of Season Paving | 2.0 Out Of Season Paving
|  | 2.0 Out Of Season Paving - Dispatching Temperature compliance |  | Dispatching Temperature compliance | 2.0 Out Of Season Paving
Rehabs
| Scope |  |  | Rehabs
Rows
|  | Rehabs | dynamic | Rehabs
Columns
|  | 1. Procurement |  | 1. Procurement
|  | 2. Pre-Implementation |  | 2. Pre-Implementation
|  | 3. Construction - Pre-treatment Digouts |  | 3. Construction - Pre-treatment Digouts
|  | 4. Construction - Granular make up and In-situ Modification |  | 4. Construction - Granular make up and In-situ Modification
|  | 5. Chip Sealing - 5.1. Procurement |  | 5. Chip Sealing - 5.1. Procurement
|  | 5. Chip Sealing - 5.2. Construction |  | 5. Chip Sealing - 5.2. Construction
|  | 5. Chip Sealing - 5.3. Post Construction |  | 5. Chip Sealing - 5.3. Post Construction
|  | 6. Close Out |  | 6. Close Out