## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Partitions ITP Overview
| Scope |  |  | Site QA | Partitions
Rows
|  | B9 | dynamic | Site QA | B9
|  | B8 | dynamic | Site QA | B8
|  | B7 | dynamic | Site QA | B7
|  | B6 | dynamic | Site QA | B6
|  | B5 | dynamic | Site QA | B5
|  | B4 | dynamic | Site QA | B4
|  | B3 | dynamic | Site QA | B3
|  | B2 | dynamic | Site QA | B2
|  | B1 | dynamic | Site QA | B1
|  | L0 | dynamic | Site QA | L0
|  | L1 | dynamic | Site QA | L1
|  | L2 | dynamic | Site QA | L2
|  | L3 | dynamic | Site QA | L3
Columns
|  | Set out - Partitions set out plans current revisions checked & wall set out completed as per the current plans |  | Partitions set out plans current revisions checked and wall set out completed as per the current plans | Set out
|  | Set out - Minimum/critical dimensions (face to face) on drawings checked |  | Minimum/critical dimensions (face to face) on drawings checked | Set out
|  | Stud Framing - Base & Head tracks fixed in accordance with steel stud partition design. Typically ≤600mm centres & 100mm from ends |  | Base & Head tracks fixed in accordance with steel stud partition design. Typically ≤600mm centres and 100mm from ends | Stud Framing
|  | Stud Framing - Fixing to post tensioned concrete: Maximum embedment for fixings = 50mm |  | Fixing to post tensioned concrete: Maximum embedment for fixings = 50mm | Stud Framing
|  | Stud Framing - Stud spacings correct as per steel stud partition design. Noting max 450 centres for wet area sheeting. |  | Stud spacings correct as per steel stud partition design. Noting max 450 centres for wet area sheeting. | Stud Framing
|  | Stud Framing - Fixing to post tensioned concrete: Maximum embedment for fixings = 50mm |  | Fixing to post tensioned concrete: Maximum embedment for fixings = 50mm | Stud Framing
|  | Stud Framing - Door frame openings as per Rondo design |  | Door frame openings as per Rondo design | Stud Framing
|  | Stud Framing - Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm. |  | Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm. | Stud Framing
|  | Stud Framing - Rotate intermediate studs into tracks for friction fixing |  | Rotate intermediate studs into tracks for friction fixing | Stud Framing
|  | Stud Framing - Structural floor control joints: Disconnect partitions over joints with detached double studs & ensure bottom tracks, bracing & top tracks are not fastened across joints |  | Structural floor control joints: Disconnect partitions over joints with detached double studs and ensure bottom tracks, bracing and top tracks are not fastened across joints | Stud Framing
|  | Stud Framing - Stud service holes: Splice additional stiffening to studs if site cut service holes exceed 1/3 the width of the member |  | Stud service holes: Splice additional stiffening to studs if site cut service holes exceed 1/3 the width of the member | Stud Framing
|  | Stud Framing - Provide fire, smoke & acoustic sealing where indicated on the drawings/details |  | Provide fire, smoke and acoustic sealing where indicated on the drawings/details | Stud Framing
|  | Stud Framing - Noggings: Fix noggings as per steel stud design. |  | Noggings: Fix noggings as per steel stud design. | Stud Framing
|  | Stud Framing - Door frames: Installed |  | Door frames: Installed | Stud Framing
|  | Bulk Insulation - Install acoustic & thermal insulation. |  | Install acoustic and thermal insulation. | Bulk Insulation
|  | Hold Point - Framing system completed – Ready for installation of sheets. |  | Framing system completed – Ready for installation of sheets. | Hold Point
|  | Board Lining - Stagger end joints in a brick pattern & locate them on framing members away from the corners of large openings |  | Stagger end joints in a brick pattern and locate them on framing members away from the corners of large openings | Board Lining
|  | Board Lining - Multiple sheet layers: Fill & flush up all joints & fixings in each layer & caulk up perimeters & penetrations before commencing succeeding layers. |  | Multiple sheet layers: Fill & flush up all joints and fixings in each layer and caulk up perimeters and penetrations before commencing succeeding layers. | Board Lining
|  | Board Lining - Butt joints staggered on adjoining sheets & opposite sides of wall. |  | Butt joints staggered on adjoining sheets and opposite sides of wall. | Board Lining
|  | Board Lining - Fire rated recess joints staggered on opposite sides of the wall, or backed by steel nogging |  | Fire rated recess joints staggered on opposite sides of the wall, or backed by steel nogging | Board Lining
|  | Board Lining - Tape & Bead all joints & corners as required |  | Tape & Bead all joints and corners as required | Board Lining
|  | Board Lining - Provide sealants at junctions between partition systems & with other building elements |  | Provide sealants at junctions between partition systems and with other building elements | Board Lining
|  | Board Lining - Provide trim such as beads, moulding & stops to make neat junctions between lining components, finishes & adjacent surfaces |  | Provide trim such as beads, moulding and stops to make neat junctions between lining components, finishes and adjacent surfaces | Board Lining
|  | Control Joints - Control joints to coincide with structural control joints |  | Control joints to coincide with structural control joints | Control Joints
|  | Control Joints - Provide control joints as follows: |  | Provide control joints as follows: | Control Joints
|  | Control Joints - Plasterboard lined partitions: 12m centres |  | Plasterboard lined partitions: 12m centres | Control Joints
|  | Control Joints - Fibre-cement board lined partitions: 7.2m centres |  | Fibre-cement board lined partitions: 7.2m centres | Control Joints
|  | Control Joints - Board lined partitions in wet areas: To suit joints required in tiling & at max 4.2m centres |  | Board lined partitions in wet areas: To suit joints required in tiling and at max 4.2m centres | Control Joints
|  | Tolerances - Flatness, twist, winding & bow: Maximum 1.5mm deviation from a 1.5m straightedge |  | Flatness, twist, winding and bow: Maximum 1.5mm deviation from a 1.5m straightedge | Tolerances
|  | Additional checks for Fire Walls - Installed as per board suppliers design & install specification |  | Installed as per board suppliers design & install specification | Additional checks for Fire Walls
|  | Additional checks for Fire Walls - Correct FRL achieved |  | Correct FRL achieved | Additional checks for Fire Walls
|  | Additional checks for Fire Walls - Perimeter fire rated sealant completed. |  | Perimeter fire rated sealant completed. | Additional checks for Fire Walls
|  | Additional checks for Fire Walls - All penetrations through fire walls below & above ceiling protected/sealed – Service penetrations sealing by others |  | All penetrations through fire walls below and above ceiling protected/sealed – Service penetrations sealing by others | Additional checks for Fire Walls
|  | Additional checks for Fire Walls - Fire door frames installed |  | Fire door frames installed | Additional checks for Fire Walls
|  | Additional Checks for Smoke Walls - Deflection heads & all joints sealed, taped & set (Sealant is approved prior) |  | Deflection heads and all joints sealed, taped and set (Sealant is approved prior) | Additional Checks for Smoke Walls
|  | Additional Checks for Smoke Walls - All penetrations through smoke walls below & above ceiling protected/sealed |  | All penetrations through smoke walls below and above ceiling protected/sealed | Additional Checks for Smoke Walls
|  | Additional Checks for Acoustic Walls - Deflection heads & all joints sealed, taped & set (Sealant is approved prior) |  | Deflection heads and all joints sealed, taped and set (Sealant is approved prior) | Additional Checks for Acoustic Walls
|  | Additional Checks for Acoustic Walls - All penetrations through acoustic walls below & above ceiling protected/sealed |  | All penetrations through acoustic walls below and above ceiling protected/sealed | Additional Checks for Acoustic Walls
|  | Access panels - Installed with consideration for required acoustic, smoke & fire rating. |  | Installed with consideration for required acoustic, smoke & fire rating. | Access panels