## B04
Devonport Road - TCC Building
Level | Area | Area | Apartments
Basement |  | Underslab Drainage
Stormwater Underslab
Stormwater Sleeves
Sanitary Underslab
Services Underslab
Channel Drainage
Pump Station
Dewatering

## Checklists
type | name | values
checklist | Underfloor check
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check set out from builders
section | Install QA
checkpoint | Sleeves installed though Structural Foundations Beams correct
checkpoint | Hot Water System (relief drain)
checkpoint | Correct Floor wastes set up for Grates and Grills in different areas
checkpoint | Correct Sumps installed with grates to heights
checkpoint | Pump Station pipe work installed correctly ready for pour
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped though floor
checkpoint | Pipes tested for inspection
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Water needed in floor for 1st fix
checkpoint | Work completed as per spec and tidied up
Checklist | In slab Pipe Work
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped/ lagged though floor correctly
checkpoint | Check Set out of all risers and inline with drawings
checkpoint | Pipe work clipped correctly to reo and fixed
checklist | First Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check Plans for correct sizing and pipe material
section | First fix checks
checkpoint | Sanitary fixtures and fittings specifications received for set out
checkpoint | Acoustic Wrap installed
checkpoint | All Pipes silicone though noggs
checkpoint | Vents install though roof
checkpoint | Floor Flanges and Grates installed and Capped
checkpoint | All stud stiffeners installed
checkpoint | Marshall flashings installed
checkpoint | All pipes pressure tested to 1500KPA (Fusiotherm refer to test procedures)
checkpoint | Seismic restrains installed
checkpoint | Water Meters installed and BMS Ready
checkpoint | Hot Water Cylinder Set Up
checkpoint | Noggs installed for fixing of sanitary fixtures and fittings
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Work completed as per spec and tidied up
checkpoint | Council Inspection Passed
checklist | Second Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
section | Second fix checks
checkpoint | Fixtures and fittings checked for damage
checkpoint | Flanges installed on all penetrations
checkpoint | All fixtures sealed with silicone as required
checkpoint | All fittings checked for leaks
checkpoint | Hot Water system commissioned
checkpoint | Pumps Install and Commission correctly
checkpoint | System commissioned
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Work completed as per spec and tidied up
Drainage
Check Point | Storm Water
Check Point | Plans correct issue and construction set
Check Point | Check set out from builders
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Cesspits, Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | Pipes tested for inspection
Check Point | Rainwater Tank installed as per engineers report
Check Point | Photos Taken
Check Point | Inspection passed
Check Point | Engineer Inspected
Check Point | Mark up drawings Done
Check Point
Check Point | Sewer
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | All ORG and RE installed as per plan
Check Point | Pipes tested for inspection
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken
Check Point
Check Point | Water Mains and Infrastructure
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | EF welding completed by a certified welder
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
Check Point | Pipes tested for inspection
Check Point | Chlorination of Pipe work completed as per TCC IDC Code
Check Point | E Coli Test done and Passed
Check Point | Warning tape installed
Check Point | All Trenches compacted with compactor
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken
Section | Dewatering
Checkpoint | Pumps supplied able to do flow rates required
Checkpoint | Wells installed to heights slightly lower than cut
Checkpoint | Storage tanks install and linked dup to prevent overflow to street
Checkpoint | Valves installed on tanks for Sludge removal
Checkpoint | Water Quanilty Monitored and checked daily
Checkpoint | Balance pipes installed between tanks
Checkpoint | Water Flow rate checked daily
Checkpoint | Power supply checked for reliability
Checkpoint