## B04
90 Devonport Road - TCC Building
Level | Area | Area | Apartments
Drainage
Storm Water Drainage
Sewer Drainage
Water Mains
Sewer Connection
Stomrwater Connection including Drilling
Water Connection
RainWater Tank
Rainwater Pump Station
Underslab Drainage
Stormwater Underslab
Stormwater Sleeves
Sanitary Underslab
Services Underslab
Channel Drainage
1st Fix and 2nd Fix
Ground Floor |  | Saintary Stacks
Stormwater Stacks
EOT Bathroom
Retail Bathroom
Booster Pump Set Up
EOT Hot Water Plant
Non-potable Water Plant Room
Water Pipe work in Ceiling
1st Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
2nd Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
3rd Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
4th Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
5th Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
6th Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
7th Floor
Saintary Stacks
Stormwater Stacks
Office Floor Bathroom
8th Floor/Plant Decks
Water Piping
StromWater Stacks
Sanitary Stacks
Roof Plant
Santary Stacks
Stormwater Stacks

## Checklists
type | name | values
checklist | Underfloor check
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check set out from builders
section | Install QA
checkpoint | Sleeves installed though Structural Foundations Beams correct
checkpoint | Hot Water System (relief drain)
checkpoint | Correct Floor watses set up for Grates and Grills in different areas
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped though floor
checkpoint | Pipes tested for inspection
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Water needed in floor for 1st fix
checkpoint | Work completed as per spec and tidied up
Checklist | In slab Pipe Work
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped/ lagged though floor correctly
checkpoint | Check Set out of all risers and inline with drawings
checkpoint | Pipe work clipped correctly to reo and fixed
checklist | First Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check Plans for correct sizing and pipe material
section | First fix checks
checkpoint | Sanitary fixtures and fittings specifications received for set out
checkpoint | Acoustic Wrap installed
checkpoint | All Pipes silicone though noggs
checkpoint | Vents install though roof
checkpoint | Floor Flanges and Grates installed and Capped
checkpoint | All stud stiffeners installed
checkpoint | Marshall flashings installed
checkpoint | All pipes pressure tested to 1500KPA (Fusiotherm refer to test procedures)
checkpoint | Seismic restrains installed
checkpoint | Water Meters installed and BMS Ready
checkpoint | Hot Water Cylinder Set Up
checkpoint | Noggs installed for fixing of sanitary fixtures and fittings
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Work completed as per spec and tidied up
checkpoint | Council Inspection Passed
checklist | Second Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
section | Second fix checks
checkpoint | Fixtures and fittings checked for damage
checkpoint | Flanges installed on all penetrations
checkpoint | All fixtures sealed with silicone as required
checkpoint | All fittings checked for leaks
checkpoint | Hot Water system commissioned
checkpoint | Pumps Install and Commission correctly
checkpoint | System commissioned
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Work completed as per spec and tidied up
Drainage
Check Point | Storm Water
Check Point | Plans correct issue and construction set
Check Point | Check set out from builders
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Cesspits, Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | Pipes tested for inspection
Check Point | Rainwater Tank installed as per engineers report
Check Point | Photos Taken
Check Point | Inspection passed
Check Point | Engineer Inspected
Check Point | Mark up drawings Done
Check Point
Check Point | Sewer
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | All ORG and RE installed as per plan
Check Point | Pipes tested for inspection
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken
Check Point
Check Point | Water Mains and Infrastructure
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | EF welding completed by a certified welder
Check Point | Subgrade Scala test ever 10m - 3 Blows per 100mm
Check Point | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
Check Point | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
Check Point | Pipes tested for inspection
Check Point | Chlorination of Pipe work completed as per TCC IDC Code
Check Point | E Coli Test done and Passed
Check Point | Warning tape installed
Check Point | All Trenches compacted with compactor
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken