## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Door Installation ITP |  |  |  |  | Yes | Door Installation ITP | 312d8244-e7d9-4194-b6cb-11db551f99a8
checkpoint-status |  |  | checkpoint | Doors have good, consistent perimeter and no binding
checkpoint-status |  |  | checkpoint | For hollow core doors, hinge and lock sides are correct. For fire doors, the top hinge (T.H) side is correct
checkpoint-status |  |  | checkpoint | Door free of scratches and damages
checklist-flat |  |  | checklist | Door Hardware Installation ITP |  |  |  |  | Yes | Door Hardware Installation ITP | 3b596ec7-02fd-4698-a73d-c7d72b8496d8
checkpoint-status |  |  | checkpoint | Door latching correctly
checkpoint-status |  |  | checkpoint | Locking mechanism working
checkpoint-status |  |  | checkpoint | Closer working at an optimum level of speed & force
checkpoint-status |  |  | checkpoint | Seals are not impeding the closure/opening of the door while still maintaining a tight seal
checklist-flat |  |  | checklist | Rigid Board |  |  |  |  | Yes | Rigid Board | 45b7fb28-2b70-4407-956d-73abdb1f1207
checkpoint-status |  |  | checkpoint | Install Rigid Board
checkpoint-status |  |  | checkpoint | Tape & Seal
checkpoint-status |  |  | checkpoint | Clean up
checklist-flat |  |  | checklist | ACP+LIN |  |  |  |  | Yes | ACP+LIN | 524b613c-66c0-4773-baef-e1ae0c272c9f
checkpoint-status |  |  | checkpoint | Woven image and whiteboard installed correctly
checkpoint-status |  |  | checkpoint | Woven image and whiteboard damage free
checkpoint-status |  |  | checkpoint | Aluminium angle installed and damage free
checklist-flat |  |  | checklist | Suspended Ceiling |  |  |  |  | Yes | Suspended Ceiling | 52657fc2-fa33-4e90-87e5-8412a5483641
checkpoint-status |  |  | checkpoint | Frame ceiling and bulkheads
checkpoint-status |  |  | checkpoint | Trim out access panel
checkpoint-status |  |  | checkpoint | Noggins kitchen, robes, blinds, shower screen and any mark up
checkpoint-status |  |  | checkpoint | Service check for Pre install of sheets
checkpoint-status |  |  | checkpoint | Insulation to ceiling.
checkpoint-status |  |  | checkpoint | Sheet ceilings
checkpoint-status |  |  | checkpoint | Fit Access panels
checkpoint-status |  |  | checkpoint | Stop & Sand all Walls and Ceilings
checklist-flat |  |  | checklist | Add-As-You-Go Trimming Checklist |  |  |  |  | Yes | Add-As-You-Go Trimming Checklist | 52beb62d-b33c-4433-b7f7-b38101a9cbcb
checkpoint-status |  |  | checkpoint | Trimming Complete
checklist-flat |  |  | checklist | Partition Wall |  |  |  |  | Yes | Partition Wall | 8757a222-0730-4e3c-8215-e259a39d75a6
checkpoint-status |  |  | checkpoint | Set out walls
checkpoint-status |  |  | checkpoint | Metal Wall framing
checkpoint-status |  |  | checkpoint | Noggins
checkpoint-status |  |  | checkpoint | Check insulation in walls
checkpoint-status |  |  | checkpoint | Service check for pre install of sheets
checkpoint-status |  |  | checkpoint | Sheet fire walls and caulk
checkpoint-status |  |  | checkpoint | Sheet all walls
checkpoint-status |  |  | checkpoint | Skirting flushed & Installed
checkpoint-status |  |  | checkpoint | Check Walls for Patch
checkpoint-status |  |  | checkpoint | Final caulking
checklist-flat |  |  | checklist | Infills |  |  |  |  | Yes | Infills | 89c87be3-8c91-4499-841f-d29dc0954f4d
checkpoint-status |  |  | checkpoint | Correct insulation installed - appropriately fire rated
checkpoint-status |  |  | checkpoint | Sheeting
checkpoint-status |  |  | checkpoint | Caulking
checklist-flat |  |  | checklist | Speedpanel |  |  |  |  | Yes | Speedpanel | 96ac7ff9-6c3b-44cb-af71-2e7634bb8848
checkpoint-status |  |  | checkpoint | Set out Speedpanel walls
checkpoint-status |  |  | checkpoint | Install Speedpanel
checkpoint-status |  |  | checkpoint | Caulking
checkpoint-status |  |  | checkpoint | Clean up
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
checklist-flat |  |  | checklist | Sundries Installation ITP |  |  |  |  | Yes | Sundries Installation ITP | b54d2424-c42e-48ab-9da8-8e18d4cc9b1d
checkpoint-status |  |  | checkpoint | All sundries are at correct height
checkpoint-status |  |  | checkpoint | All sundries are level
checkpoint-status |  |  | checkpoint | All sundries are fastened correctly
checkpoint-status |  |  | checkpoint | All sundries are free of damage
checklist-flat |  |  | checklist | Frames Installation ITP |  |  |  |  | Yes | Frames Installation ITP | b9cc26b2-ae8e-4f2a-8d86-ce38ed7e14b1
checkpoint-status |  |  | checkpoint | All door frames are plumb
checkpoint-status |  |  | checkpoint | All door frames are Level
checkpoint-status |  |  | checkpoint | All door frames are wine
checkpoint-status |  |  | checkpoint | All door frames are damage free
checklist-flat |  |  | checklist | Incoming Goods |  |  |  |  | Yes | Incoming Goods | dfd790db-ffcd-46e2-bd98-f559c50e4a38
checkpoint-status |  |  | checkpoint | Check the items
checkpoint-status |  |  | checkpoint | Check Quantity
checkpoint-status |  |  | checkpoint | Check the label
checkpoint-status |  |  | checkpoint | Material Receipt Inspection
checklist-sectioned |  |  | checklist | Trimming |  |  |  |  | Yes | Trimming | ed90134b-1e1c-4fa0-84a5-83433acf38c8
checkpoint-group |  |  | section | Male WC
checkpoint-status |  |  | checkpoint | North wall
checkpoint-status |  |  | checkpoint | East Wall
checkpoint-status |  |  | checkpoint | South Wall
checkpoint-status |  |  | checkpoint | West Wall
checkpoint-group |  |  | section | Female WC
checkpoint-status |  |  | checkpoint | North wall
checkpoint-status |  |  | checkpoint | East Wall
checkpoint-status |  |  | checkpoint | South Wall
checkpoint-status |  |  | checkpoint | West Wall
checkpoint-group |  |  | section | DDA WC
checkpoint-status |  |  | checkpoint | North wall
checkpoint-status |  |  | checkpoint | East Wall
checkpoint-status |  |  | checkpoint | South Wall
checkpoint-status |  |  | checkpoint | West Wall
checkpoint-group |  |  | section | Various Trimming
checkpoint-status |  |  | checkpoint | North wall
checkpoint-status |  |  | checkpoint | East Wall
checkpoint-status |  |  | checkpoint | South Wall
checkpoint-status |  |  | checkpoint | West Wall