## Cycle Lane Separators
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
01.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence | Downer | Construction Pack | Prior to Works | H | PE
01.01.02 | Inspection and Test Plan | Aprroval of ITP | Downer | Acceptance Correspondence & Approved ITP | Prior to Works | H | ENG
01.01.04 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to Works | H | PE
SECTION 2 – Separator Construction
2.01 | Construction
02.01.01 | Approval of Concrete Material | Materials as per Contract Specifications | NZS 3109 | Concrete Mix design | Proir to works | R | SE
02.01.02 | Form release agent | Materials as per Contract Specifications | NZS 3109 | Material data sheet | Proir to works | R | SE
02.01.03 | Cast in items | Materials as per Contract Specifications | NZS 3109 | Certificate of Origin | Proir to works | R | SE
02.01.04 | Pre pour inspection | Pre pour inspection checking reinforcing, formwork rebar, dowels | As per drawings/NZS 3109 | Pre pour check sheet | Each pour | H | SE
02.01.05 | Concrete placing | Concrete placed to specifications and NZS 3109 | NZS 3109 | Delivery dockets | Each pour | R | SE
02.01.06 | Concrete - testing | Ensure Mix is at correct MPA | NZS 3109 | Concrete cylinder test | Once | R | SE
02.01.07 | Post Pour Inspection | Engineer to inspect before installation | NZS 3109 | Post pour inspection sheet | After each pour | H | SE
SECTION 04 – Seperator Install
3.01 | Install
3.01.01 | Materials - Bolts | Materials as per Contract Specifcations | As per drawings | Delivery dockets | Before installing Separators | H | SE
3.01.02 | Materials - Epoxy | Materials as per Contract Specifcations | As per drawings | Delivery dockets | Before installing Separators | H | SE
3.01.03 | Separator set out | Set out as per contract drawings | As per drawings | Correspondence of Approval | Before installing Separators | H | ENG
3.01.04 | Separator installation | Separators installed as per drawings | As per drawings | Daily check sheet | Ongoing during installation | R | SE
3.01.05 | Redline Drawings | Asbuilt / Redline Drawings to be provided | As per drawings | Redline Drawings | Ongoing during installation | R | SE