## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Cycle Lane Separators - Build and Install | itp |  |  |  |  | ITP - Cycle Lane Separators - Build and Install
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 01.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.02 - Inspection and Test Plan
label | Acceptance / Conformance Criteria - Aprroval of ITP
label | Standard / Specification - Downer
label | Verifying Document - Acceptance Correspondence & Approved ITP
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
checkpoint | 01.01.04 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 2 – Separator Construction
checkpoint | 02.01.01 - Approval of Concrete Material
label | Acceptance / Conformance Criteria - Materials as per Contract Specifications
label | Standard / Specification - NZS 3109
label | Verifying Document - Concrete Mix design
label | Frequency - Proir to works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.02 - Form release agent
label | Acceptance / Conformance Criteria - Materials as per Contract Specifications
label | Standard / Specification - NZS 3109
label | Verifying Document - Material data sheet
label | Frequency - Proir to works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.03 - Cast in items
label | Acceptance / Conformance Criteria - Materials as per Contract Specifications
label | Standard / Specification - NZS 3109
label | Verifying Document - Certificate of Origin
label | Frequency - Proir to works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.04 - Pre pour inspection
label | Acceptance / Conformance Criteria - Pre pour inspection checking reinforcing, formwork rebar, dowels
label | Standard / Specification - As per drawings/NZS 3109
label | Verifying Document - Pre pour check sheet
label | Frequency - Each pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 02.01.05 - Concrete placing
label | Acceptance / Conformance Criteria - Concrete placed to specifications and NZS 3109
label | Standard / Specification - NZS 3109
label | Verifying Document - Delivery dockets
label | Frequency - Each pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.06 - Concrete - testing
label | Acceptance / Conformance Criteria - Ensure Mix is at correct MPA
label | Standard / Specification - NZS 3109
label | Verifying Document - Concrete cylinder test
label | Frequency - Once
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.07 - Post Pour Inspection
label | Acceptance / Conformance Criteria - Engineer to inspect before installation
label | Standard / Specification - NZS 3109
label | Verifying Document - Post pour inspection sheet
label | Frequency - After each pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 04 – Seperator Install
checkpoint | 3.01.01 - Materials - Bolts
label | Acceptance / Conformance Criteria - Materials as per Contract Specifcations
label | Standard / Specification - As per drawings
label | Verifying Document - Delivery dockets
label | Frequency - Before installing Separators
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Materials - Epoxy
label | Acceptance / Conformance Criteria - Materials as per Contract Specifcations
label | Standard / Specification - As per drawings
label | Verifying Document - Delivery dockets
label | Frequency - Before installing Separators
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.03 - Separator set out
label | Acceptance / Conformance Criteria - Set out as per contract drawings
label | Standard / Specification - As per drawings
label | Verifying Document - Correspondence of Approval
label | Frequency - Before installing Separators
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
checkpoint | 3.01.04 - Separator installation
label | Acceptance / Conformance Criteria - Separators installed as per drawings
label | Standard / Specification - As per drawings
label | Verifying Document - Daily check sheet
label | Frequency - Ongoing during installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 3.01.05 - Redline Drawings
label | Acceptance / Conformance Criteria - Asbuilt / Redline Drawings to be provided
label | Standard / Specification - As per drawings
label | Verifying Document - Redline Drawings
label | Frequency - Ongoing during installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature