## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Room Construction
Sign Off | checklist |  |  | Tier 2: Room Construction Checklist
Sign Off | checklist |  |  | Tier 2: QA Documentation
| step |  |  | Tier 1: Frame Construction
Sign Off | checklist |  |  | Tier 2: Frame Construction Checklist
Sign Off | checklist |  |  | Tier 2: Coastal Services QA Documentation
| step |  |  | Tier 1: Floor, Duct Penetrations
| step |  |  | Tier 2: Flooring, Penetrations Checklist
| step |  |  | Tier 3: Floor Cable Penetrations
| step |  |  | Tier 3: Floor Covering
| step |  |  | Tier 1: Cable Supports
| step |  |  | Tier 2: Cable Support Checklists
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 3: Cable Ladder
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 3: Uni Tray
| step |  |  | Tier 1: LV Lighting, Power, DATA & Accessories
| step |  |  | Tier 2: Lighting Checklist
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Internal 5ft Emergency Light 01
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Internal 5ft LED Light 02
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Internal 5ft LED Light 03
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Internal 5ft LED Emergency Light 04
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: 2 Way Light Switch 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: 2 Way Light Switch 02
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Emergency Exit Light 05
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Emergency Exit Light 06
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Exterior Flood Light 07
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Exterior Flood Light 08
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: PIR Sensor 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: PIR Sensor 02
| step |  |  | Tier 2: Power Checklist
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: Double Socket Outlet GPO01
| step |  |  | Tier 1: HVAC
| step |  |  | Tier 2: AC01
ITR-E-55 HVAC System | checklist |  |  | Tier 3: Indoor Unit
ITR-E-55 HVAC System | checklist |  |  | Tier 3: Outdoor Unit
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: AC Controller
| step |  |  | Tier 2: AC02
ITR-E-55 HVAC System | checklist |  |  | Tier 3: Indoor Unit
ITR-E-55 HVAC System | checklist |  |  | Tier 3: Outdoor Unit
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: AC Controller
| step |  |  | Tier 1: Equipment and Installation
| step |  |  | Tier 2: Panels
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 3: MCC
ITR-E-34A Low Voltage Switch Board | checklist |  |  | Tier 3: LV AC Distribution Board
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 3: 355KW VSD
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 3: Harmonic Filter
| step |  |  | Tier 2: Pressurization Unit
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 3: Pressurization Unit
| step |  |  | Tier 2: Earth Bar
ITR-E-40A Bus Bar | checklist |  |  | Tier 3: Switchroom Earth bar
| step |  |  | Tier 1: Cable Installation - Building Services
| step |  |  | Tier 2: Lighting
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-003; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-004; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
| step |  |  | Tier 2: AC Power
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-001; Tier 4: 6.0mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-002; Tier 4: 6.0mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-005; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-006; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: *; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
| step |  |  | Tier 2: HVAC Power
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-218; Tier 4: 6.0mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-219; Tier 4: 6.0mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-220; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-221; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
| step |  |  | Tier 2: HVAC Control
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: C-001; Tier 4: 0.5mm ES PVC/PVC 1PR
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: C-002; Tier 4: 0.5mm ES PVC/PVC 1PR
| step |  |  | Tier 2: Earthing
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-001; Tier 4: 120mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-002; Tier 4: 120mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-003; Tier 4: 120mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-004; Tier 4: 35mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-005; Tier 4: 35mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-006; Tier 4: 25mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-007; Tier 4: 16mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-008; Tier 4: 16mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-009; Tier 4: 120mm 1C CU GRN/YLW PVC
ITR-E-12 Electrical earthing | checklist |  |  | Tier 3: E-010; Tier 4: 120mm 1C CU GRN/YLW PVC
| step |  |  | Tier 1: Building Access
Sign Off | checklist |  |  | Tier 2: Stairs
Sign Off | checklist |  |  | Tier 2: Platform
| step |  |  | Tier 1: COC, ESC
Certificate of compliance (COC) | checklist |  |  | Tier 2: COC
Electrical Safety Ceritificate (ESC) | checklist |  |  | Tier 2: ESC
Test Equipment Details | checklist |  |  | Tier 2: Test Equipment
| step |  |  | Tier 1: Punchlist Walkdown
Sign Off | checklist |  |  | Tier 2: Sign Off
| step |  |  | Tier 1: Punchlist work Complete Acceptance
Sign Off | checklist |  |  | Tier 2: Sign Off
| step |  |  | Tier 1: Switchroom Complete
ITR-E-09 Electrical Switch Rooms | checklist |  |  | Tier 2: Entec Project Engineer
| step |  |  | Tier 1: As Built Drawings Complete
Sign Off | checklist |  |  | Tier 2: Entec Supervisor
| step |  |  | Tier 1: Workpack Completion Sign Off
Sign Off | checklist |  |  | Tier 2: Entec Project Engineer
Sign Off | checklist |  |  | Tier 2: TOP Energy Client representative