## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Mt Richmond - Building 6
Level 0
Open Plan Office - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 1 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 2 - 62-03
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 3 - 62.02
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
QT Pod 1 - 62.02
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
P/C Area/ Storage - 61-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Server - 64-06
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Under stairs
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Retain Sampling Room
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Rework Room
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Lobby
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
WH Office 1
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
WH Office 2
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Level 1
Breakout Lunch - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 4 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
QT Pod 4 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Open Plan Office - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
QT Pod 2 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
QT Pod 5 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 5 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
P/C Area/ Storage - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
QT Pod 3 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Meeting 65 - 65-01
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
Stairs - 69-03
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation
checkpoint | Check Area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Apply Moisture Fix if required for job
checkpoint | Disc purged material
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply prep compound
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Install as per specification - Carry out vinyl installation as per spec
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required as per plan
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Install carpet tiles as per specifications
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.